13 December 2004

To: Distribution

From: Wayne Reiersen

Subject: Minutes of 13 December Critical Activities Meeting

The weekly Critical Activities Meeting was held on 13 December at 10am.  Attendees included Tom Brown, Brad Nelson, Jim Chrzanowski, Larry Dudek, Phil Heitzenroeder, Greg Pitonak, Bob Simmons, and Wayne Reiersen.  The purpose of this weekly meeting is to review those ongoing activities that are on or near the critical path, identify and expeditiously resolve any issues, and to review what needs to be done in the coming week.  Critical activities are listed and discussed below.  The meeting time is limited to one hour.  Unfortunately, we did not have time to status all the action items.  In the paragraphs which follow, action items are noted in blue.  Priorities for the next meeting are highlighted in yellow.

- Twisted Racetrack Coil Design (part of Job 1403) and Fabrication (part of Job 1410).  Good progress continues to be reported on the TRC.  Coil winding was completed.  Measurements have been taken.  The conductor has been removed.  Application of cladding has begun.

  - WP distortion and shim requirements. Nelson has the lead in determining the winding pack distortion and the required shimming.  Nelson has constructed Pro/E models from the measurements but needs the ball measurements in order to reference the reconstructed winding to the reference winding.  Nelson to get ball measurements from Raftopoulos and establish shim requirements.

  - Shim design.  Chrzanowski proposed using hard shims between one or two layers instead of distributing soft fiberglass cloth between every layer.  The motivation for using the hard shims is two-fold: to improve dimensional control and facilitate fabrication.  There was considerable discussion of this option.  It was agreed that this option should be pursued.  Nelson will coordinate thermal and structural analysis of the hard shim option.  Assuming there are no showstoppers, we would need to have the shims fabricated.  Chrzanowski will provide Dudek with a table of standard shim sizes and thicknesses that we be used for fabricating these parts.

There had been discussion of what would happen if we did not do any shimming at all.  Could we still produce a plasma with adequate performance and flexibility? Maybe, but nobody was convinced that we could prove it in our lifetimes, much less before we needed to start winding coils, so we decided not to pursue this option any longer.

  - Fabrication of piece parts.  Following the meeting, Dudek reported that it was critical that fabrication of the chill plates and fringe commence immediately if they are to be available on time.  Fabrication drawings of these parts still have not been received from ORNL.  Nelson to expedite completion of fabrication drawings so part fabrication can commence.

  - Cost and schedule control.  Fabrication of the TRC is schedule critical.  The application of the cladding and winding will be done on an extended working schedule.  The technicians working on the straight tee have stopped to help prep the cladding so the pieces are ready when Anderson and Terlitz need them.  Because of the schedule critical nature of this job and the uncertainty in how long each step will take, Chrzanowski agreed to develop a more detailed schedule that he will use to report progress and forecast when the TRC will be finished.  Because we plan to use OT to get this job done within the time allowed, Chrzanowski will provide Strykowsky with updated cost and schedule information consistent with this revised plan.  This information should explicitly identify any outside procurements that need to be placed, e.g. the cladding and chill plates for the production coils.

  - Safety.  On Tuesday following the CA meeting, the ACC participated in the management safety walk-through of the MCMF.  The ACC had no significant findings.  The key was that Chrzanowski was prepared and provided a notebook for the ACC with all of the information that they would be looking for – JHAs, procedures, training, responses to recommendations, etc.  Kudos to Jim for the excellent example.

Application of the cladding and chill plates/cooling tubes are the things that most worry the technicians responsible for manufacturing the modular coils.  Cognizant design and manufacturing personnel really need to stay on top of the problems they encounter as they do these operations and strive to make refinements where dictated by the problems they encounter.  Chrzanowski is encouraged to pursue refinements in the winding station design and tools that might speed up the winding time and provide improved ergonomics for the technicians.

Brooks is investigating cooling concepts that avoid the need for cladding and chill plates.  Specifically, he has investigated an option that uses copper inserts that would be placed in a manner similar to hard shims.  These would be flat pieces of copper perhaps 1 1/2” wide and the depth of the winding pack.  The cooling tube would run straight across the top of the clamp (where it is now) without any serpentines.  The copper tabs would be connected to the cooling tube via a copper strip that is attached with pop rivets.  Brooks to report on the performance and design of this alternate concept.  Heitzenroeder has been promoting the idea of using standard cladding pieces with commercial clips instead of custom cladding pieces to facilitate assembly and reduce cost.  Chrzanowski has been exploring options using copper braid instead of copper sheet and will contact Brooks to evaluate its performance when the concept has reached an appropriate level of maturity.  If any of these concepts appear to be a quantum improvement, we may want to consider winding the second side of the TRC using a revised cladding/chill plate design.  Nelson to propose end game for alternate cooling concepts.

There was confusion at this week’s status meeting about whether the drawings for the production clamps (not the winding clamps) had the right dimension for the vertical legs.  Chrzanowski to fit the production clamps and determine if they are the correct length..

- TF Design and Procurement.  Continuing down the path of procuring the TF coils from an outside vendor places a burden on us to assure that the TF coils are built to exacting quality standards while staying within our budget and meeting our schedule objectives.  Kalish to update design data on Manufacturing Web (see Tyrrell) to reflect current design and notify potential suppliers (foreign and domestic) of the update.

Kalish is planning on conducting an information meeting for potential suppliers for Conventional Coils (WBS 13) in January.  Kalish to finalize arrangements for information meeting.

Results from CTD on the insulation tests did not provide very conclusive data.  Most of the test samples broke before they were removed from the mold.  Nelson suggested that the insulation scheme be re-thought, perhaps wrapping the conductor in Kapton to ensure the electrical integrity and providing a thick ground wrap (a pseudo-case) to provide increased mechanical stiffness.  Subsequent analysis by Myatt, based on the assumption of a slip plane between the insulation and conductor, supported the conjecture that the winding would be less stiff but that some of this loss could be regained by making the ground wrap thicker.  Kalish to update plans for design and analysis to support upcoming design reviews.

Kalish is planning to test a straight beam using conductor that is representative of the conductor used in the conventional coils.  He would subject the conductor to repeated thermal stresses and perform mechanical and electrical tests to verify that the insulation performance does not degrade under repeated thermal cycling.  Plans are to fabricate and test the specimen right after straight tee specimen is fabricated to test modular coil VPI process.  The results would be available for the FDR.

The TF is near the critical path.  It is imperative that the FDR in February be held on schedule.  To do so requires that the PDR be held in early January.  Kalish to contact Reiersen re setting a date once PDR deliverables are well in hand.

- VV Field Weld Joint R&D (Job 1206).  Additional samples have been welded.  Dudek reported last week that [1] there is little hope of avoiding a crack when welding from only one side and [2] it was difficult with the current weld prep to get the tungsten to the root of the weld.

Nelson suggested that a one-sided V-groove would provide better access than a one-sided J-groove and avoid the fit-up problems introduced by a 2-sided weld prep.  He also thought that a deeper weld would decrease the load eccentricity and reduce stresses.  Nelson and Dudek to resolve final weld configuration.

Tensile samples have been prepared from the plates that were welded together.  Dudek reported (via e-mail) on an initial pull test that was very positive, showing a strength of 10x the design stress.  Nelson tempered the optimism with the observation from Freudenberg’s analysis that the tensile load is eccentric with the tensile stresses being substantially higher than the average section stresses where the weld is located.  Subsequent to the meeting, Goranson provided more detailed guidance on the mechanical loading at the weld.  Analysis indicates that a tensile load on the weld sample in the range of 1725-1860 lbs per inch of perimeter (thickness of sample) will give an equivalent stress to the results predicted by the ANSYS model. This assumes a weld depth of 0.44 inches and an offset in the pull specimen of 0.155 inches, which is pulling symetrically on the ¾” wide section.  These loads are basically due to the vacuum vessel being under vacuum.  I was unable to find any requirement for the expected number of vents and pumpdowns.  I think 500 is generous number.  This is basically once per week for 10 years.  The fatigue requirement (which does not strictly apply due to the low number of cycles) calls for a factor of 2 on stress and 20 on life.  20 on life would be only 10,000 cycles.  Kozub reported that the initial tests were suspended after almost 250,000 cycles.  This is overkill.  What do strictly apply are the crack growth criteria.  Dudek to report on testing plans and progress.

The requisition of the full scale test article was cancelled because of the protracted deliberations for finalizing the weld joint configuration.  The full scale test article would be quite expensive to procure, with a contract (unloaded) price tag of $125K.  Cheaper alternatives might exist such as [1] just welding flange pieces together cut from Inconel plate or [2] replacing the rolled Inconel sheet with stainless steel.  ORNL (Nelson/Goranson) and Dudek are asked to propose lower cost alternatives.

- VV port extensions welds.  MTM reported a concern that when they weld the large, thick (1/2”) port extensions for the NB ports and the adjacent large ports (Port #4) to the thinner (3/8”) shell, the shell will locally pucker in by perhaps 5/8”.  MTM has asked the project to re-visit the tolerance requirements around these large ports.  The project considered the issue and identified a concern about potentially creating an interference with the neutral beams.  Cole was asked to quantify what relief could be given without impacting the neutral beams and discuss possible paths forward with MTM.

- Modular Coil Testing

  - Conductor Testing (Job 1406).  Kozub has reportedly pulled the long racetrack coil to failure – it failed at 23,000 lbs.  This information will be used to set the parameters for additional cyclic testing to be performed in January.  Chrzanowski reported that torsion tests are done, but problems were encountered with transverse compression test.  Chrzanowski to provide results for torsion test and update on transverse compression tests.  The NSTX work that Kozub was planning on doing appears to be slipping.  Chrzanowski suggested to Kozub slipping the NCSX cyclic tests forward to right after the holidays.

  - Beam Testing (Job 1403).  ORNL reported on the 3-point bending tests at least week’s Wednesday telecon.  The results are being analyzed by Fan.  Torsion testing of the beam is next on the agenda.  Nelson to expedite testing at ORNL and report on how Fan’s results should be used in the analysis effort.

  - MCWF Fracture Analysis (Job 1404).  The data from the NHFML had seven orders of magnitude of scatter with some points better and some worse than our reference CF8M data.  The pedigree of the data has been sorted out.  It was determined that the samples were cut from risers and other places not representative of the high stress regions.  Additional samples will be cut from the EIO prototype coil (around port openings) and tested.  Heitzenroeder to work with Strykowsky to add this additional testing to our plans.  (A simplified VV full scale weld test article would be a possible source term for the funding required.)  We have been awaiting a proposal from EIO on using the prototype as the first production article.  Nelson to report on plans for fabricating and testing the new samples.

- Modular Coil Design (Job 1403).  A recent study by Brown suggested that reaming all of the holes for assembling the modular coils into a shell may be very difficult.  It was not clear that reaming all of the holes was necessary.  It was also clear that a means of positively locking the bolts was required.  Nelson to report on progress resolving this issue.

Analysis efforts in modular coils are taking more time than budgeted.  Nelson and Williamson met with Fan, Freudenberg, Brooks et al and established an analysis end game.  Plans need to be updated accordingly (Williamson)

- Vacuum Vessel Final Design (Job 1203).  This is a mirror of the analysis issue in modular coils.  Analysis efforts are taking more time than budgeted.  Nelson met with Goranson, Freudenberg, Dahlgren, Brooks et al this week to establish analysis end game.  Plans should be updated accordingly (Goranson).

- PF Solenoid Make, Buy, or Scavenge.  There has been discussion lately about making the solenoid coils in-house in the first part of CY05 ore even re-using the excessed PF1A coils from NSTX.  Reiersen did a study which indicated that the PF1A might be used in place of PF1-3.  Zarnstorff to perform simulation modeling to confirm conclusions.  If we choose to go this way, Kalish will have to add a PF1A refurbishment task to his scope and Ramakrishnan will have to revise his plans accordingly.

Neilson concluded that there is insufficient management reserve available to commit to building the solenoid coils in house at this time, so that option has gone away.  We still need to decide between re-using the PF1A coils and buying new solenoid coils, but the urgency of that decision has abated.

- Test Cell Preparations and Machine Assembly (WBS 7 jobs).  In discussions regarding machine assembly, a question arose regarding when we would know what the upgraded crane capacity would be.  It is expected that the “break point” for the upgraded crane capacity will be between 40 and 45 tons, but we will likely not know for a year or so.  It would be prudent therefore to plan on 40 tons.  Cole to update our assessment of the maximum weight of a FPA to determine what margins exist.

- STEP file creation.  Brown previously reported a problem with updating STEP files, but that this problem could be overcome by using commercially available PowerGrip software.  Brown to report on status of STEP file issue.

- Upcoming Design Reviews.

  - TF PDR – now TBD.  Kalish to re-schedule.

  - MC Turning Fixture PDR – 23 Dec 04. No preparations apparent as of 14 Dec (Brown).

  - Platform and Support Stands for MC Installation – 17 Jan 05 (Brown)

  - VV Support Fixture PDR – 17 Jan 05 (Brown)

  - Base Support Structure and Cryostat PDR.  Gettelfinger to re-schedule for January to accommodate designer crunch in December and allow more time for design review prep.

The next meeting is scheduled for 10am next Monday, 20 December in the Engineering Conference Room.

Cc: Neilson, Strykowsky, Brown, Heitzenroeder, Chrzanowski, Nelson, Dudek, Perry, Kalish, Gettelfinger, Viola, Tyrrell, Brooks, Zarnstorff