08 November 2004

To: Distribution

From: Wayne Reiersen

Subject: Minutes of 01 November Critical Activities Meeting

The weekly Critical Activities Meeting was held on 01 November at 9am.  Attendees included Tom Brown, Brad Nelson, Larry Dudek, Jim Chrzanowski, Mike Kalish, Mike Viola, and Wayne Reiersen.  The purpose of this weekly meeting is to review those ongoing activities that are on or near the critical path, identify and expeditiously resolve any issues, and to review what needs to be done in the coming week.  Critical activities are listed and discussed below.  Action items are noted in blue.

- FPA Tooling (Job 1803) and Assembly (Jobs 1808 and 1810).  Tom Brown has led a working group on field period assembly (including Viola, Cole, Nelson, and Raftopoulos) to define the process for FPA; the tooling required; and the resource and schedule requirements.  The plan appears to be an excellent one.  It appears that we are back in the box on schedule but still out of the box on cost by $194K.  (This does not consider any changes in hardware costs, but rather recognizes them as cost risks.)  Strykowsky determined that the existing staff of technicians can provide adequate coverage for crane operations so this number can be reduced a bit.  Additional potential offsets were discussed in the subsequent SIT meeting and will be pursued.

- Test Cell Preparations and Machine Assembly (WBS 7 jobs).  This has been identified as an area where potential offsets might be found.  The scope of ancillary systems (including diagnostics, heating systems, and I&C) has been cut drastically.  There should be some ripple effect in WBS 7.  The scope in the area should be down.  Direct and oversight efforts should be less than they were with the original scope for ancillary systems.  It is not clear that providing a platform as part of the MIE is needed or cost effective.

Brown and Perry have developed a plan for final assembly that identifies the steps required in their proper sequence.  Perry is resource loading the plan.  We would like to have an internal review of the revised plan as soon as possible.  Time is of the essence for approving the ECP that will formally adopt the changes that we will be using as the basis for October cost reporting and presentations at the Lehman review next month.  Strykowsky to fold in changes in WBS 7 and determine if any schedule milestones are impacted.  Reiersen to arrange a review with Perry and Brown.

- Twisted Racetrack Coil Design (part of Job 1403) and Fabrication (part of Job 1410).  Good progress was reported on the TRC.  The studs were installed.  Measurements are being completed.  Cole asked for additional data for reverse engineering the part.  Raftopoulos reported some difficulties using the laser scanner, but that their solution seemed reachable in a day or so.  Clamp installation should begin Tuesday.  The trial winding should begin Wednesday.  Chrzanowski to get authorization from Dudek to proceed with the trial winding.  It was suggested that next week would be a good time for ORNL to visit to witness the trial winding.  The week after Thanksgiving would be a good time to visit to witness the installation of the cladding.  Nelson to arrange for ORNL participation.

ORNL has provided all of the drawings required except for a signed drawing of the terminal detail.  PPPL is working off a sketch at the present time.  ORNL to provide drawing of the terminal detail.

Chrzanowski has posted two procedures, the MIT/QA Plan, and the MC Manufacturing Facility Operations Plan for ORNL review on Simmons FTP site.  ORNL to review.

The current plan calls for doing a trial winding of both sides of the TRC.  We anticipate getting substantial distortion/keystoning of the winding pack in the regions of sharp twist and curvature.  It appears that we have an adequate plan for taking the measurements needed to quantify the distortion/keystoning.  However, we still need to figure out how we are going to measure and shim the TRC during the actual winding to control the location of the current center to within the prescribed tolerance.  The window of opportunity for doing this is while we are applying the cladding.

The biggest concern of the technicians winding the TRC is not the winding process, but the application of the chill plates and cooling tubes.  It is not clear in their minds that this is do-able and if so, within the schedule provided.  ORNL should be present at key times during the TRC fabrication to witness any difficulties that might arise.  It might also be prudent to consider further refinements to the design so that if problems do arise, we might have potential solutions in hand.

- TF Design and Procurement.  Continuing down the path of procuring the TF coils from an outside vendor places a burden on us to assure that the TF coils are built to exacting quality standards while staying within our budget and meeting our schedule objectives.  Kalish is planning hold an information meeting around the time the RFP is released.  Kalish to provide a plan and a schedule for developing a base of qualified suppliers.

Neilson provided (via e-mail) some interesting leads on European coil manufacturers based on conversations with the staff at Greifswald.  Kalish has been and will continue to follow up on these new foreign options.

A draft SRD was circulated this week for review.  One of the recent changes was a 3mm tolerance requirement on the current center location.  At the CA meeting, there was concern that [1] any coil of this size wound on a winding form would spring by order 1” (Chrzanowski comment on NSTX experience) and [2] in order to meet this tolerance, we might have to keep the winding on the winding form a la the modular coils (Nelson comment).  Kalish to finalize tolerance requirements with Brooks and address how this risk is being mitigated in the design of the TF coils.

- VV Field Weld Joint R&D (Job 1206).  It was decided to hold up the procurement of the full-scale test article for two weeks pending resolution of the joint configuration.  Viola contacted Arlene White to hold up the procurement.  However, there was again no progress reported on resolving this issue.  Welding of additional samples had not yet been done.  Dudek thought that the welding of the small samples could be completed this week.  Dudek to expedite completion of the additional sample welds.  Nelson reported that he had received nothing from Dahlgren who is tied up on an NSTX analysis task.  Chrzanowski thought Dahlgren was within two days of finishing, but that story has not changed in the last couple of weeks.

There was good, frank discussion of this issue at the meeting.  Dudek and Viola believe that with an enforced gap, you cannot guarantee that a crack on the back side will not exist.  The crack might be smaller and regions of complete fusion larger, but it is unrealistic to believe that the cracks will go away entirely.  Although there was no news from Dahlgren or ORNL regarding analysis of the weld joint, it was generally believed that the results have shown (and will continue to show) regions of low tensile stress across the weld joint.  The issue is whether this is acceptable in the presence of a crack.  If so, we go with it.  If not, we might have to pursue a 2-sided weld prep or an alternate weld configuration.  Nelson to provide determination regarding whether the presence of a crack is acceptable or not.

- Modular Coil Testing

  - Conductor Testing (Job 1406).  The testing remaining to be completed now appears in this job.  Kozub is responsible for completing the transverse compression tests, single conductor torsion tests, and 4-turn racetrack coil tests.  Kozub’s plans have now been incorporated into the PMB.  Chrzanowski reported that all tests should be completed this week except for the fatigue tests of the racetrack coils.

  - Beam Testing (Job 1403).  ORNL is responsible for testing the straight tee (beam) sections.  No progress this week due to unavailability of Rick Batiste.  Nelson to expedite testing at ORNL.

  - MCWF Fracture Analysis (Job 1404).  Nelson reviewed the data from the HFML.  The data had seven orders of magnitude of scatter with some points better and some worse than our reference CF8M data.  Nelson to work with Bob Walsh (NHFML) to sort out pedigree and relevance of the sample data.

- Upcoming FY05 Design Reviews.

  - Closed Loop LN2 System FDR – 10 Nov 04.  The charge for the FDR is to ensure that [1] the requirements are documented, [2] the design satisfies the requirements, [3] the design has appropriate safety features incorporated, and [4] the design documentation is adequate and appropriate to complete the installation.  Gettelfinger has set up the FDR for 10 November at 2pm in the Engineering Conference Room.  Erik Perry to chair the review committee.

  - TF PDR – 15 Nov 04.  Reiersen to review objectives and deliverables with Kalish, confirm date.

  - MC Platform and Support Stands PDR – 13 Dec 04.  The PDRs and FDRs are packed closely together in Brown’s schedule, typically 2 weeks.  More time should be allotted between the two.  Brown to revise schedule, keeping at least a month between the PDR and FDR for responding to PDR recommendations, finalizing and checking drawings, and preparing for the FDR.

  - Base Support Structure and Cryostat PDR – 15 Dec 04

  - MC Turning Fixture PDR – 17 Jan 05

  - VV Prep Station PDR – 18 Jan 05

  - VV Prep Station FDR – 01 Feb 05

  - MC Platform and Support Stands FDR – 07 Feb 05

  - Type C MC FDR – 10 Feb 05

  - MC Turning Fixture FDR – 15 Jan 05

  - TF FDR – 15 Feb 05

  - Comprehensive VV FDR – 28 Feb 05

  - Complete MCMF ACC Review – 28 Feb 05

  - Power Systems CDR – 15 Mar 05

  - Half Period Assembly PDR – 21 Mar 05

  - Half period Assembly FDR – 12 Apr 05

  - Structures PDR – 29 Apr 05

  - Type B MC FDR – 04 May 05

  - Base Support Structure FDR – 01 Jun 05

  - Power Systems PDR – 06 Jun 05

  - Structures FDR – 18 Jul 05

  - Type A MC FDR – 10 Aug 05

  - Power Systems FDR – 15 Aug 05

  - PF and CS Assembly PDR – 08 Sep 05

  - Trim Coil PDR – 08 Sep 05

  - Cryostat FDR – 14 Oct 05

The next meeting is scheduled for 10am next Monday, 15 November in the Engineering Conference Room.  The meeting will adjourn by 11am for the subsequent SIT meeting.

Cc: Neilson, Strykowsky, Brown, Heitzenroeder, Chrzanowski, Nelson, Dudek, Perry, Kalish, Gettelfinger, Viola