## Make
[11 empty] | Rate | per Hr
| Assumptions: | [9 empty] | EM | 165
| 1) Conductors will arrive in 90to 100 ft. length spools | [9 empty] | SM | 108
| 2) Conductors need to be primed | [9 empty] | TB | 79
| 3) Induction Braze joints | [9 empty] | DM | 108
| 4) Four conductor spools per TF coil | [9 empty] | per R. Strykowsky 10/5/04
|  |  | Duration | Start | End | EAEM | EETB | EADM | EMSM | EMSM | EMTB | M&S
| TASK DESCRIPTION |  |  |  |  | Engr | Tech | Designer |  | machinist | Tech
|  |  | Days |  |  | hours | hours | hours | hours | hours | hours | w/o G&A | w/G&A
1 | ENGINEERING and OVERSIGHT
| Design tooling and winding facility |  |  |  |  | 288 |  | 720
| LOE FY05 |  |  |  |  | 240 |  |  | 240
| LOE FY06 |  |  |  |  | 576 |  |  | 240
| LOE FY07 |  |  |  |  | 144 |  |  | 80 |  |  |  |  | Total Cost
| Sub total (hours) |  |  |  |  | 1248 |  | 720 | 560 |  |  |  |  | 344160
| Sub total cost |  |  |  |  | 205920 |  | 77760 | 60480
2 | Braze Qualification Program
| Fabricate work coils | [8 empty] | 40 | 60
| Prepare braze samples | [8 empty] | 80
| Develop braze technique | [9 empty] | 60
| Braze conductor samples | [9 empty] | 60 |  |  | Total cost | 35820
| Test brazed samples | [7 empty] | 80
| Sub total (hours) | [7 empty] | 80 | 120 | 180
| Sub total cost | [7 empty] | 8640 | 12960 | 14220
|  |  | Duration | Start | End | EAEM | EETB | EADM | EMSM | EMSM | EMTB | M&S
| TASK DESCRIPTION |  |  |  |  | Engr | Tech | Designer |  | machinist | Tech
|  |  | Days |  |  | hours | hours | hours | hours | hours | hours | w/o G&A | w/G&A
3 | EQUIPMENT and TOOLING COSTS
Fabricate Coil WIndingTooling/Fixtures
| Recondition turning fixture | [9 empty] | 360 | 5000
| Winding clamps | [8 empty] | 80 | 80 | 5000
| Taping machine conditioning | [5 empty] | 80 |  |  | 80 | 160 | 1000
| Winding mandrel | [8 empty] | 120 | 160 | 5000
| Miscellaneous tools and equipment | [10 empty] | 3000
| TF mold (2) | [8 empty] | 360 | 360 | 10000
| Braze unit | [10 empty] | 85000 |  | Total cost
| Sub total (hours) | [8 empty] | 640 | 1120 |  |  | 295540
| Sub total cost | [8 empty] | 69120 | 88480 | 114000 | 137940
4 | AREA PREPARATION
| Setup winding facility in the RESA building | [7 empty] | 320 | 0 | 480 | 5000 | 6050
Install winding table
Setup copper delivery system
Install taping machine
Complete setup of facility
| Build cleanroom | [7 empty] | 320 |  | 700 | 10000 | 12100 | Total Cost
| Sub total (hours) | [7 empty] | 320 | 0 | 1180 |  |  | 137920.5
| Sub total cost | [7 empty] | 25280 | 0 | 93220 | 15000 | 19420.5
5 | MATERIAL & SUPPLIES
5a | Coil Supplies
| 1) Insulation [t/t and groundwrap] | [10 empty] | 40000
| 2) Epoxy- CTD-101K | [10 empty] | 60000
[8 gallons per coil @ $1500.00 per kit- assume 20 injections]
| 5) Copper conductor | [10 empty] | 80000
| 6) G-11 fillers [Fillers for transitions and leads] | [8 empty] | 800 | 80 | 4000
| 7) Lead blocks | [8 empty] | 800 | 120 | 10000
| 8) Safety and PPE equipment and supplies | [10 empty] | 8000
| 9) Miscellaneous supplies [Includes rags, hardware, braze material etc.] | [10 empty] | 10000
| 10) Primer | [10 empty] | 8000
5b | VPI Supplies
| 1) Misc VPI supplies | [10 empty] | 8000
| 2) Disposable VPI hardware | [9 empty] | 800
| valves | [10 empty] | 10000
| High & low temperature vac. Tubing | [10 empty] | 20000
| Copper tubing | [10 empty] | 5000 |  | Total Cost
| Sub total (hours) | [8 empty] | 1600 | 1000 | 263000 | 318230 | 570030
| Sub total cost | [8 empty] | 172800 | 79000
Task | TASK DESCRIPTION |  | Working | Shifts | No. of | EMTB
No. |  |  | Days | per day | Tech. | man-hours
6 | Station No. 1- Conductor Preparation |  | 57 | Total working days
6a | Receive conductors | [7 empty] | Hours | Cost
| Unload and sample measure each spool |  | 3 | 1 | 2 | 48 |  | TOTAL | 912 | 72048
6b | Flush inner bore |  | 18 | 1 | 2 | 288
6c | Clean, prime and bag conductor |  | 36 | 1 | 2 | 576
Task | TASK DESCRIPTION |  | Working | Shifts | No. of | No. of |  | Working | Shifts | No. of | No. of | No. of | Man-hrs | Total
No. |  |  | Days | per day | Tech. | man-hours |  | Days | per day | Tech. | man-hours | Items | 2 thru 18 | Man-hrs
7 | Station No. 2- Coil Winding |  | 15 | Total working days 1st. coil |  |  |  | 9 | Total working days coils 2 thru 18
7a | Prepare winding station for winding TF coil |  | 3 |  |  | 72 |  | 1 |  |  | 24 | 17 | 408 | 480
| Install and prepare mandral |  | 3 | 1 | 3 | 72 |  | 1 | 1 | 3 | 24
3
7b | Wind TF coil |  | 12 |  |  | 176 |  | 8 |  |  | 136 | 17 | 2312 | 2488
| Position starting conductor & wind layer #1 |  | 2 | 1 | 2 | 32 |  | 1 | 1 | 2 | 16 | 17
| Braze lead spur |  | 1 | 1 | 2 | 16 |  | 0.5 | 1 | 2 | 8
| Position 2nd. Conductor and braze layer 1 to 2 |  | 2 | 1 | 2 | 32 |  | 1 | 1 | 2 | 16
| Wind layer #2 - |  | 2 | 1 | 2 | 32 |  | 1 | 1 | 2 | 16
| Position 3rd. Conductor & wind layer 3 |  | 1 | 1 | 2 | 16 |  | 1 | 1 | 2 | 16
| Perform locking braze layers 2 to 3 |  | 1 | 1 | 2 | 16 |  | 1 | 1 | 2 | 16
| Position 4nd. Conductor and braze layer 3 to 4 |  | 1 | 1 | 2 | 16 |  | 1 | 1 | 2 | 16
| Wind layer #4/ Torch braze |  | 1 | 1 | 2 | 16 |  | 0.5 | 1 | 2 | 8 |  |  | 2968
| Secure and transfer TF coil to station #3 |  | 1 | 1 | 3 | 24 |  | 1 | 1 | 3 | 24 |  | Total | 234472
8 | Station No. 3- Ground wrapping & Mold Application |  | 7 | Total working days 1st. coil |  |  |  | 4.5 | Total working days coils 2 thru 18
8a | Ground wrap TF coil |  | 2 | 1 | 2 | 32 |  | 1.5 | 1 | 2 | 24 | 17 | 408 | 440
Notes:
1) 2-man teams can apply approximately 5 wraps per minute. (2" wide tape)
2) (6) half-lapped layers of glass & (2) half-lapped layers of glass/Kapton
3) Circumference: approx. 353 inches
4) Approximately 70 minutes to complete (1) half-lapped layer
5) Approximately 10 hours to complete groudwrap operation
8b | Install TF coil in mold |  | 4 | 1 | 3 | 96 |  | 2 | 1 | 3 | 48 | 17 | 816 | 912
8c | Transport TF to NCSX Coil Facility |  | 1 | 1 | 3 | 24 |  | 1 | 1 | 3 | 24 | 17 | 408 | 432
1784
[13 empty] | Total | 140936
Task | TASK DESCRIPTION |  | Working | Shifts | No. of | No. of |  | No. of | Total
No. |  |  | Days | per day | Tech. | man-hours |  | Items | Manhrs
9 | VPI TF Coil |  | 10 | Total working days per coil
Assumption: VPI (2) TF coils together
9a | Transfer TF coil to Autoclave |  | 1 | 1 | 4 | 32 |  | 18 | 576
9b | Prepare TF coil for VPI | [7 empty] | 0
| Connect fill lines, manifolds, hookup thermocouples & leak check |  | 2 | 1 | 4 | 64 |  | 18 | 1152
0
9c | VPI TF coil |  | 9 | [5 empty] | 0
| Vacuum pumpdown mold and autoclave |  | 1 | 1 | 3 | 24 |  | 9 | 216
| Epoxy fill coil |  | 1 | 2 | 4 | 64 |  | 9 | 576
| Temperature rampup and Cure |  | 1 | 3 | 1 | 24 |  | 9 | 216
| [parallel activity] Station cleanup during cure |  | 1 | 1 | 3 | 24 |  | 9 | 216
| Temperature rampup and Post cure |  | 1 | 2 | 1 | 16 |  | 9 | 144
| Temperature rampdown |  | 1 | 1 | 1 | 8 |  | 9 | 72 |  | Hours | Cost
| Cleanup & ready autoclave |  | 2 | 1 | 2 | 32 |  | 9 | 288 | Total | 4032 | 318528
| Remove TF coil from mold/clean mold |  | 2 | 1 | 2 | 32 |  | 18 | 576
10 | Station No. 6- Electrical Test Station |  | 1
[11 empty] | Hours | Cost
| Perform electrical & Pressure Tests |  | 1 | 1 | 2 | 16 | 0 | 18 | 288 | Total | 288 | 22752
Warm tests (room temperature) only
|  | Engineering & Oversight |  |  | 344160 | 15.84% | 17.49% |  |  | 17.49%
|  | Brazing qualification |  |  | 35820 | 1.649% |  |  |  | 19.95%
|  | Equip. & Tooling |  |  | 295540 | 13.61% | 19.95% | Equip & Tooling |  | 26.24%
|  | Area Preparation |  |  | 137920.5 | 6.349% |  |  |  | 36.31%
|  | Materials & supplies |  |  | 570030 | 26.24% | 26.24% | M&S
|  | Conductor prep |  |  | 72048 | 3.317%
|  | Coil winding |  |  | 234472 | 10.79% | 36.31% | Fabrication
|  | Ground wrap/mold |  |  | 140936 | 6.488%
|  | VPI |  |  | 318528 | 14.66%
|  | Testing |  |  | 22752 | 1.047%
|  | Total TF Fabrication |  |  | 2172206.5 | 100%

## Make or Buy
Cost Comparison Make or Buy
BUY | MAKE
1326 | 2172 | Base Costs
-324 |  | Wedge Casting Fabrication and Assembly
133 |  | Engineering Coverage
| -324 | Savings to Modular Coil Fabrication
| -100 | Brazing Unit Paid for out of Infrastrucure $$
1135 | 1748 | Sub Total
|  | 613 | Additional Cost for Fabrication In House
133 |  | Additional Engineering Coverage
18 |  | Travel
1286 | 1748 | Total
|  | 462 | Additional Cost for Fabrication In House
Includes Cost of Increased Oversight at Vendor