## Sheet2
 | time axis 2005-08-19 to 2006-01-16
1 | Receive MCWF C1 | bar: 2005-09-23
2 | Winding form preparation | bar: 2005-09-26 to 2005-09-30; 2005-10-03 to 2005-10-07; 2005-10-10
3 | Pre-fit leads enclosure | bar: 2005-10-11 to 2005-10-12
4 | Install cladding | bar: 2005-10-13 to 2005-10-14; 2005-10-17 to 2005-10-20
5 | Install groundwrap | bar: 2005-08-19 to 2006-01-16
6 | Wind coil side-A | bar: 2005-10-31 to 2005-11-04; 2005-11-07 to 2005-11-10
7 | Wind coil side-B | bar: 2005-11-11; 2005-11-14 to 2005-11-18; 2005-11-21 to 2005-11-23
8 | Install chill plates | bar: 2005-08-19 to 2006-01-16
9 | Install VPI mold | bar: 2006-01-02 to 2006-01-06; 2006-01-09 to 2006-01-13
10 | Ready for VPI | bar: 2006-01-16
TYPE-C MODULAR COIL ASSEMBLY | bar: 2005-09-09; 2005-09-12 to 2005-09-16; 2005-09-19 to 2005-09-23
MOD COIL WINDING FORM ASM TYPE-C
PRODUCTION WINDING FORM TYPE-C
POL BREAK SHIM ASM TYPE-C
STUD, 1.375-6UNC-2A X 9.5 LG
NUT, 12PT HEX 1.375-6UNC-2B
WASHER, 2.75 OD X 1.66 ID X 0.5 THK
TYPE-C WINDING FORM MODS ASM | bar: 2005-08-19; 2005-08-22 to 2005-08-26
TYPE-C LEAD BLOCKS PRE-FIT ASM | bar: 2005-08-24 to 2005-08-26; 2005-08-29 to 2005-09-02; 2005-09-06
TYPE-C COIL SIDE-A LOWER LEAD BLOCK
TYPE-C COIL SIDE-B LOWER LEAD BLOCK
TYPE-C COIL SIDE-A UPPER LEAD BLOCK
TYPE-C COIL SIDE-B UPPER LEAD BLOCK
TYPE-C COIL LEADS ENCLOSURE TOP PLATE
FILLER STRIP
TYPE-C COIL LEADS AREA CHILL PLATE
TYPE-C COIL SIDE-A LEADS SIDE PLATE
TYPE-C COIL SIDE-B LEADS SIDE PLATE
LEADS TERMINAL ASSEMBLY | bar: 2005-09-01 to 2005-09-02; 2005-09-06 to 2005-09-09; 2005-09-12 to 2005-09-13
JUMPERS BASE BLOCK
TERMINAL JUMPER #1
TERMINAL JUMPER #2
TERMINAL JUMPER #3
TERMINAL JUMPER #4
STUD, 3/8-16UNC X 3 LG
TERMINAL LUG, SHORT
TERMINAL LUG, LONG
TERMINAL SPLICE PLATE #1
CABLE END CONNECTOR ASM
COOLING TUBE ASM
TYPE-C COIL SIDE-A ASSEMBLY
TYPE-C COIL SIDE-A UPPER CLADDING ASM | bar: 2005-08-19; 2005-08-22 to 2005-08-26; 2005-08-29
TYPE-C COIL SIDE-A LOWER CLADDING ASM | bar: 2005-08-22 to 2005-08-26; 2005-08-29 to 2005-08-30
TYPE-C COIL SIDE-A UPPER CHILL PLATE ASM | bar: 2005-09-06 to 2005-09-09; 2005-09-12 to 2005-09-16
TYPE-C COIL SIDE-A LOWER CHILL PLATE ASM | bar: 2005-09-14 to 2005-09-16; 2005-09-19 to 2005-09-26
TYPE-C COIL SIDE-B ASSEMBLY
TYPE-C COIL SIDE-B UPPER CLADDING ASM | bar: 2005-08-19; 2005-08-22 to 2005-08-26; 2005-08-29 to 2005-08-31
TYPE-C COIL SIDE-B LOWER CLADDING ASM | bar: 2005-08-29 to 2005-09-02; 2005-09-06 to 2005-09-08
TYPE-C COIL SIDE-B UPPER CHILL PLATE ASM | bar: 2005-08-19; 2005-08-22 to 2005-08-26; 2005-08-29 to 2005-09-02; 2005-09-06
TYPE-C COIL SIDE-B LOWER CHILL PLATE ASM | bar: 2005-09-01 to 2005-09-02; 2005-09-06 to 2005-09-09; 2005-09-12 to 2005-09-14
TYPE-C VPI ASSEMBLY
CLAMP ASSEMBLY | bar: 2005-08-19; 2005-08-22 to 2005-08-26; 2005-08-29 to 2005-09-02
CLAMP BAR
BUSHING, SPACER
WASHER, SPHERICAL CONVEX
WASHER, SPHERICAL CONCAVE
KEEPER
LEAD BLOCK MOUNT WELDING FIXTURE | bar: 2005-08-19; 2005-08-22 to 2005-08-26; 2005-08-29 to 2005-09-02; 2005-09-06 to 2005-09-09
POST-VPI MODIFICATIONS
I&C, PREP FOR COLD TEST
ROGOWSKI COIL INSTALLATION
COIL-COIL FLANGE BUSHING INST

## Sheet1
DRAWING NO. | REV | REL DATE | MODEL NO. | PART NO. | QTY | DESCRIPTION | MATERIAL / SPECIFICATION | WEIGHT (LBS) | FIND NO. | NEXT ASM | STATUS | ETC (HRS) | DESIGN CHECKING |  | READY TO BE CHECKED | RELEASED FOR FAB | REQ / SHOP INSTR ISSUED | PO ISSUED |  | FORECAST DELIVERY | REC'D AND INSPECTED
SE140-103 | 0 | WIP | SE140-103 | -1 | AR | TYPE-C MODULAR COIL ASSEMBLY | --- | TBD | 1 | SE140-003 | In progress. | 80 | GL / DW |  | 2005-09-19 | 2005-09-23
|  |  | SE141-103 | SE141-103 | 1 | MOD COIL WINDING FORM ASM TYPE-C | --- | --- | 2
|  |  | SE142C-080 | SE142C-080 | 1 | LEAD BLOCKS PRE-FIT ASM |  |  | 3
|  |  | SE142C-050 | SE142C-050 | 1 | LEADS TERMINAL ASSEMBLY | --- | --- | 4
|  |  | SE142C-241 | SE142C-241 | 1 | TYPE-C COIL SIDE-B ASSEMBLY | --- | --- | 5
|  |  | SE142C-251 | SE142C-251 | 1 | TYPE-C COIL SIDE-A ASSEMBLY | --- | --- | 6
|  |  | SE142C-291 | SE142C-291 | 1 | TYPE-C VPI ASSEMBLY | --- | --- | 7
|  |  | SE142C-270 | SE142C-270 | 1 | CLAMP ASSEMBLY | --- | --- | 8
SE141-103 | 2 | 2005-08-05 | SE141-103 | -1 | AR | MOD COIL WINDING FORM ASM TYPE-C | --- | 5092 | 1 | SE140-103 | Released for fabrication. | 0 | [7 empty] | 2005-09-23
|  |  | SE141-116 | SE141-116 | 1 | PRODUCTION WINDING FORM TYPE-C | --- | --- | 2
|  |  | SE141-078 | SE141-078 | 1 | POL BREAK SHIM ASM TYPE-C | --- | --- | 3
|  |  | SE141-071 SE141-075 | -4 | 2 | INS SHEET, 32 X 15 X .063 THK | NEMA GRADE G-11CR | --- | 4
|  |  | SE141-074 | -5 | 14 | INS BUSHING, 1.63 OD X 1.38 ID X 1.68 LG | NEMA GRADE G-11CR | --- | 5
|  |  | SE141-036 | DS141-036 | 7 | STUD, 1.375-6UNC-2A X 9.5 LG | --- | --- | 6
|  |  | SE141-080 | -7 | 2 | INS SHEET, 26 X 3 X .063 THK | NEMA GRADE G-11CR | --- | 7
|  |  | SE141-060 | DS141-060 | 14 | NUT, 12PT HEX 1.375-6UNC-2B | --- | --- | 8
|  |  | SE141-079 | DS141-079 | 14 | WASHER, 2.75 OD X 1.66 ID X 0.5 THK | --- | --- | 9
SE141-116 | 6 | 2005-08-05 | SE141-116 | -1 | AR | PRODUCTION WINDING FORM TYPE-C | SS, CSPEC-141-03 | --- | 1 | SE141-103 | Released for fabrication. | 0
SE141-078 | 1 | 2004-09-23 | SE141-078 | -1 | AR | POL BREAK SHIM ASM TYPE-C | --- | 129 | 1 | SE141-103 | Released for fabrication. | 0
|  |  | SE141-073 | -2 | 1 | POLOIDAL BREAK SHIM | SS, CSPEC-141-03 | --- | 2
|  |  | SE141-077 | -3 | 7 | INS BUSHING, 1.63 OD X 1.38 ID X 2.19 LG | NEMA GRADE G-11CR | --- | 3
DS141-036 | 1 | 2005-08-05 | SE141-036 | -1 | AR | STUD, 1.375-6UNC-2A X 9.5 LG | ASTM A286 | --- | 1 | SE141-103 | Released for fabrication. | 0
DS141-060 | 0 | 2004-07-20 | SE141-060 | -1 | AR | NUT, 12PT HEX 1.375-6UNC-2B | ASTM A286 | --- | 1 | SE141-103 | Released for fabrication. | 0
DS141-079 | 0 | 2004-07-20 | SE141-079 | -1 | AR | WASHER, 2.75 OD X 1.66 ID X 0.5 THK | ASTM A286 | --- | 1 | SE141-103 | Released for fabrication. | 0
SE141-123 | 0 | WIP | SE141-123 | -1 | AR | TYPE-C WINDING FORM MODS ASM | --- | TBD | 1 | SE140-103 | Drawing in progress. | 20 | GL / MC |  | 2005-08-23 | 2005-08-26
|  |  | SE141-123 | -2 | 1 | LAWTON STOCKED MCWF | --- | --- | 2
|  |  | TBD | -3 | 1 | POL BREAK SHIM ASSEMBLY | --- | --- | 3
|  |  | TBD | -4 | 1 | POL BREAK BOLT ASSEMBLY | --- | --- | 4
|  |  | SE141-123 | -5 | 184 | STUD, 3/8-16UNC X 2.5 LG | SS, UNS S31600 | --- | 5 | [7 empty] | 2005-08-31 |  | P | 2005-09-16 |  | D
|  |  | SE141-124 | -6 | 10 | ADAPTER, 1 DIA X .84 LG | SS, UNS S31600 | --- | 6 | [7 empty] | 2005-08-31 |  | R |  | 2005-09-21 | D
|  |  | SE141-126 | -7 | 1 | LEAD BLOCK MOUNT #1 | SS, UNS S31600 | --- | 7 | [7 empty] | 2005-08-31 |  | R |  | 2005-09-21 | D
|  |  | SE141-126 | -8 | 1 | LEAD BLOCK MOUNT #2 | SS, UNS S31600 | --- | 8 | [7 empty] | 2005-08-31 |  | R |  | 2005-09-21 | D
|  |  | SE141-126 | -9 | 1 | LEAD BLOCK MOUNT #3 | SS, UNS S31600 | --- | 9 | [7 empty] | 2005-08-31 |  | R |  | 2005-09-21 | D
|  |  | SE141-126 | -10 | 1 | LEAD BLOCK MOUNT #4 | SS, UNS S31600 | --- | 10 | [7 empty] | 2005-08-31 |  | R |  | 2005-09-21 | D
|  |  | SE141-127 | TBD | AR | METROLOGY TARGET | --- | --- | 11 |  | Fabrication complete. |  |  | Q | [6 empty] | COMPLETE
SE142C-080 | 0 | WIP | SE142C-080 | -1 | AR | TYPE-C LEAD BLOCKS PRE-FIT ASM | --- | TBD | 1 | SE140-103 |  | 50 | DW / MC |  | 2005-08-30 | 2005-09-02
|  |  |  | -2 |  | WINDING FORM | SS, CSPEC-141-03 | --- | 2
|  |  | SE142C-134 | SE142C-134 |  | TYPE-C SIDE-A LOWER LEAD BLOCK | --- | --- | 3
|  |  | SE142C-135 | SE142C-135 |  | TYPE-C SIDE-B LOWER LEAD BLOCK | --- | --- | 4
|  |  | TBD | -5 |  | SCREW | SS, UNS S31600 | --- | 5
|  |  | SE142C-136 | SE142C-136 |  | TYPE-C SIDE-A UPPER LEAD BLOCK | --- | --- | 6
|  |  | SE142C-137 | SE142C-137 |  | TYPE-C SIDE-B UPPER LEAD BLOCK | --- | --- | 7
|  |  | TBD | -8 |  | SCREW | SS, UNS S31600 | --- | 8
|  |  | TBD | -9 |  | BUSHING | SS, UNS S31600 | --- | 9
|  |  | SE142C-184 | SE142C-184 |  | TYPE-C LEADS ENCLOSURE TOP PLATE | --- | --- | 10
|  |  | TBD | -11 |  | SCREW | SS, UNS S31600 | --- | 11
|  |  | TBD | TBD |  | FILLER STRIP |  | --- | 12
|  |  | TBD | TBD |  | TYPE-C LEADS AREA CHILL PLATE |  | --- | 13
|  |  | TBD | -14 |  | TUBING |  | --- | 14
|  |  | TBD | -15 |  | CONNECTOR |  | --- | 15
|  |  | SE142C-220 | SE142C-220 |  | TYPE-C COIL SIDE-A LEADS SIDE PLATE | --- | --- | 16
|  |  | SE142C-221 | SE142C-221 |  | TYPE-C COIL SIDE-B LEADS SIDE PLATE | --- | --- | 17
|  |  | TBD | -8 |  | SCREW | SS, UNS S31600 | --- | 18
SE142C-134 | 0 / 1 | 2005-08-12 | SE142C-134 | -1 | AR | TYPE-C COIL SIDE-A LOWER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1 | SE142C-080 | Drw applies to C1, C2. Modifications required. | 0 |  |  |  | 2005-06-09 |  | PE005952 ($3,700) |  | 2005-08-19
SE142C-134 | 2 | WIP | SE142C-134 | -1 | AR | TYPE-C COIL SIDE-A LOWER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1 | SE142C-080 | Rev pending to change MCWF attachment. Drw applies to C3-C6. | 20 | GL / DW |  | 2005-08-26 | 2005-08-31 | R403063 ($10k)
SE142C-134 | 2 | WIP | SE142C-134 | -1 | AR | TYPE-C COIL SIDE-A LOWER LEAD BLOCK | ABS / POLYCARBONATE | --- | 1 | SE142C-080 | STL model from quickparts.com | 4 | PF |  | 2005-08-19 | 2005-08-22 |  |  |  | 2005-09-02
SE142C-135 | 0 | 2005-06-09 | SE142C-135 | -1 | AR | TYPE-C COIL SIDE-B LOWER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1 | SE142C-080 | Drw applies to C1, C2. Modifications required. | 0 | 0 |  |  | 2005-06-09 |  | PE005952 ($3,700) |  | 2005-08-19
SE142C-135 | 1 | 2005-06-09 | SE142C-135 | -1 | AR | TYPE-C COIL SIDE-B LOWER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1 | SE142C-080 | Rev pending to change MCWF attachment. Drw applies to C3-C6. | 20 | GL / DW |  | 2005-08-26 | 2005-08-31 | R403063 ($10k)
SE142C-135 | 1 | 2005-06-09 | SE142C-135 | -1 | AR | TYPE-C COIL SIDE-B LOWER LEAD BLOCK | ABS / POLYCARBONATE | --- | 1 | SE142C-080 | STL model from quickparts.com | 4 | PF |  | 2005-08-19 | 2005-08-22 |  |  |  | 2005-09-02
SE142C-136 | 0 | 2005-07-08 | SE142C-136 | -1 | AR | TYPE-C COIL SIDE-A UPPER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1 | SE142C-080 | Released for fabrication. Drw applies to C1-C6. | 0
SE142C-136 | 0 | 2005-07-08 | SE142C-136 | -1 | AR | TYPE-C COIL SIDE-A UPPER LEAD BLOCK | ABS / POLYCARBONATE | --- | 1 | SE142C-080 | STL model from quickparts.com | 4 | PF |  | 2005-08-19 | 2005-08-22 |  |  |  | 2005-09-02
SE142C-137 | 0 | 2005-07-08 | SE142C-137 | -1 | AR | TYPE-C COIL SIDE-B UPPER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1 | SE142C-080 | Released for fabrication. Drw applies to C1-C6. | 0
SE142C-137 | 0 | 2005-07-08 | SE142C-137 | -1 | AR | TYPE-C COIL SIDE-B UPPER LEAD BLOCK | ABS / POLYCARBONATE | --- | 1 | SE142C-080 | STL model from quickparts.com | 4
SE142C-184 | 0 | 2005-07-20 | SE142C-184 | -1 | AR | TYPE-C COIL LEADS ENCLOSURE TOP PLATE | NEMA GRADE G-11CR | --- | 1 | SE142C-080 | Released for fabrication. Drw applies to C1-C6. | 0
SE142C-184 | 0 | 2005-07-20 | SE142C-184 | -1 | AR | TYPE-C COIL LEADS ENCLOSURE TOP PLATE | ABS / POLYCARBONATE | --- | 1 | SE142C-080 | STL model from quickparts.com | 4 | PF |  | 2005-08-19 | 2005-08-22 |  |  |  | 2005-09-02
SE142C-226 | 0 | WIP | SE142C-226 | -1 | AR | FILLER STRIP | COPPER, ANNEALED UNS C10100, C10200 | --- | 1 | SE142C-080 | In progress. | 8
SE142C-183 | 0 | WIP | SE142C-183 | -1 | AR | TYPE-C COIL LEADS AREA CHILL PLATE | COPPER, ANNEALED UNS C10100, C10200 | --- | 1 | SE142C-080 | In progress. | 8
SE142C-220 | 0 | 2005-07-26 | SE142C-220 | -1 | AR | TYPE-C COIL SIDE-A LEADS SIDE PLATE | NEMA GRADE G-11CR | --- | 1 | SE142C-080 | Released for fabrication. Drw applies to C1-C6. | 0
SE142C-221 | 0 | 2005-07-26 | SE142C-221 | -1 | AR | TYPE-C COIL SIDE-B LEADS SIDE PLATE | NEMA GRADE G-11CR | --- | 1 | SE142C-080 | Released for fabrication. Drw applies to C1-C6. | 0
SE142C-050 | 0 | WIP | SE142C-050 | -1 | AR | LEADS TERMINAL ASSEMBLY | --- | TBD | 1 | SE140-103 | Asm drawing in progress. Some parts released. | 20
|  |  | SE142C-211 | -2 | AR | INS SHEET, 3.47 X 12.38 X .063 THK | NEMA GRADE G-11CR | --- | 2
|  |  | SE142C-047 | SE142C-047 | 1 | JUMPERS BASE BLOCK ASM | --- | --- | 3
|  |  | SE142C-049 | -4 | 3 | INS SHEET, 1.5 X 8 X 0.13 THK | NEMA GRADE G-11CR | --- | 4
|  |  | SE142C-051 | SE142C-051 | 1 | TERMINAL JUMPER #1 | --- | --- | 5
|  |  | SE142C-052 | SE142C-052 | 1 | TERMINAL JUMPER #2 | --- | --- | 6
|  |  | SE142C-053 | SE142C-053 | 1 | TERMINAL JUMPER #3 | --- | --- | 7
|  |  | SE142C-054 | SE142C-054 | 1 | TERMINAL JUMPER #4 | --- | --- | 8
|  |  | SE142C-069 | -9 | 3 | INS BUSHING, 0.5 OD X .38 ID X 1.69 LG | NEMA GRADE G-11CR | --- | 9
|  |  | SE142C-069 | SE142C-069 | 3 | STUD, 3/8-16UNC X 3 LG | --- | --- | 10
|  |  | NS151359 | -11 |  | WASHER, BELLEVILLE .515 ID X 1.29 OD X .129 HT, .029 DEF, 3200-LBS | INCONEL 718 SOLON #8H98718 | --- | 11
|  |  | SE142C-225 | -12 |  | WASHER, .406 ID X .813 OD X .063 THK | SS, UNS S31600 MCARR 91950A031 | --- | 12
|  |  | 150260 | -13 |  | NUT, 3/8-16UNC STANDARD HEX | SS, UNS S31600 | --- | 13
|  |  | SE142C-055 | SE142C-055 | 1 | TERMINAL LUG, SHORT | --- | --- | 14
|  |  | SE142C-056 | SE142C-056 | 1 | TERMINAL LUG, LONG | --- | --- | 15
|  |  | SE142C-212 | -16 | 1 | INS SHEET, 3.34 X 5.75 X 0.13 THK | NEMA GRADE G-11CR | --- | 16
|  |  | SE142C-263 | SE142C-263 | 2 | TERMINAL SPLICE PLATE #1 | --- | --- | 17
|  |  | 150741 | -18 | 10 | SCREW, 3/8-16UNC X 1.25 LG HEX SOC HD CAP | --- | --- | 18
|  |  | SE142C-060 | SE142C-060 | 16 | CABLE END CONNECTOR ASM | --- | --- | 19
|  |  | SE142C-065 | -20 | 16 | WASHER, .531 ID X .875 OD X .063 THK | SS, UNS S31600 MCARR 90107A033 | --- | 20
|  |  | 150262 | -21 | 16 | NUT, 1/2-13UNC STANDARD HEX | SS, UNS S31600 | --- | 21
|  |  | SE142C-045 | SE142C-045 | 2 | COOLING TUBE ASM |  | --- | 22
SE142C-047 | 0 | WIP | SE142C-047 | -1 | AR | JUMPERS BASE BLOCK | --- | 2.5 | 1 | SE142C-050 | In progress. | 10
|  |  | SE142C-047 | -2 | 1 | BLOCK, 3.5 X 13.8 X 0.7 THK | NEMA GRADE G-11CR | --- | 2
|  |  | SE142C-047 | -3 | 7 | INSERT, BUSHING-TYPE, THREADED | SS, UNS S31600 TAP-LOK HM-37516-50 | --- | 3
SE142C-051 | 0 | 2005-08-12 | SE142C-051 | -1 | AR | TERMINAL JUMPER #1 | OF COPPER, UNS C10200 | --- | 1 |  | Released for fabrication. Make C1, C2 in-house. | 0
SE142C-052 | 0 | 2005-08-12 | SE142C-052 | -1 | AR | TERMINAL JUMPER #2 | OF COPPER, UNS C10200 | --- | 1 |  | Released for fabrication. Make C1, C2 in-house. | 0
SE142C-053 | 0 | 2005-08-12 | SE142C-053 | -1 | AR | TERMINAL JUMPER #3 | OF COPPER, UNS C10200 | --- | 1 |  | Released for fabrication. Make C1, C2 in-house. | 0
SE142C-054 | 0 | 2005-08-12 | SE142C-054 | -1 | AR | TERMINAL JUMPER #4 | OF COPPER, UNS C10200 | --- | 1 |  | Released for fabrication. Make C1, C2 in-house. | 0
SE142C-069 | 0 | WIP | SE142C-069 | -1 | AR | STUD, 3/8-16UNC X 3 LG | SS, UNS S31600 | --- | 1 |  | In progress. | 4
SE142C-055 | 0 | WIP | SE142C-055 | -1 | AR | TERMINAL LUG, SHORT | OF COPPER, UNS C10200 | --- | 1 |  | In progress. | 4
SE142C-056 | 0 | WIP | SE142C-056 | -1 | AR | TERMINAL LUG, LONG | OF COPPER, UNS C10200 | --- | 1 |  | In progress. | 4
SE142C-263 | 0 | WIP | SE142C-263 | -1 | AR | TERMINAL SPLICE PLATE #1 | OF COPPER, UNS C10200 | --- | 1 |  | In progress. | 4
SE142C-060 | 0 | WIP | SE142C-060 | -1 | AR | CABLE END CONNECTOR ASM |  | TBD | 1 | SE142C-050 | Need to release cond drw. | 4
|  |  | SE142C-059 | SE142C-059 | 1 | CABLE CONNECTOR |  | --- | 2
|  |  | SE142C-046 | SE142C-046 | 1 | CONDUCTOR |  | --- | 3
SE142C-059 | 0 | 2005-07-25 | SE142C-059 | -1 |  | CABLE CONNECTOR | AG BEARING COPPER, UNS C10300/105/107 | --- | 1 |  | Released for fabrication. Make C1, C2 in-house. | 0
SE142C-059 | 1 | 2005-07-25 | SE142C-059 | -1 |  | CABLE CONNECTOR | AG BEARING COPPER, UNS C10300/105/107 | --- | 1 |  | Rev to add plating note, leadin chamfer. | 10
SE142C-046 | 0 | WIP | SE142C-046 | -1 | AR | CONDUCTOR | COPPER, CSPEC-142-03 | --- | 1
SE142C-045 | 0 | WIP | SE142C-045 | -1 | AR | COOLING TUBE ASM |  | TBD | 1 | SE142C-050 | In progress. | 4
|  |  | SE142C-066 | -2 | 1 | SWAGE-LOK CONNECTOR |  | --- | 2
|  |  | SE142C-047 | -3 | 1 | TUBE |  | --- | 3
SE142C-251 | 0 | WIP | SE142C-251 | -1 | AR | TYPE-C COIL SIDE-A ASSEMBLY | --- | TBD | 1 | SE140-103 | In progress. | 40
|  |  | TBD | SE142C-382 | 1 | TYPE-C COIL SIDE-A UPPER CLADDING ASM | --- | --- | 2
|  |  | TBD | SE142C-384 | 1 | TYPE-C COIL SIDE-A LOWER CLADDING ASM | --- | --- | 3
|  |  | SE142C-253 | -4 | 1 | TYPE-C COIL SIDE-A GROUNDWRAP | TBD | --- | 4
|  |  | TBD | -5 | 1 | TYPE-C COIL SIDE-A WINDING PACK | TBD | --- | 5
|  |  | TBD | SE142C-386 | 1 | TYPE-C COIL SIDE-A UPPER CHILL PLATE ASM | --- | --- | 6
|  |  | TBD | SE142C-388 | 1 | TYPE-C COIL SIDE-A LOWER CHILL PLATE ASM | --- | --- | 7
|  |  | TBD | -8 | 2 | WIRE, MINERAL INSULATED | TBD | --- | 8
|  |  | TBD | -9 | 1 | TUBING | TBD | --- | 9
SE142C-382 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-A UPPER CLADDING ASM | --- | TBD | 1 | SE142C-251 | In progress. Plan to release before -251. | 20 | GM / MC |  | 2005-08-23 | 2005-08-29
|  |  | SE142C-382* (21 GEN) | -2 | 191 | CLADDING PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2
SE142C-384 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-A LOWER CLADDING ASM | --- | TBD | 1 | SE142C-251 | In progress. Plan to release before -251. | 20 | GM / MC |  | 2005-08-25 | 2005-08-31
|  |  | SE142C-384* (21 GEN) | -2 | 191 | CLADDING PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2
SE142C-386 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-A UPPER CHILL PLATE ASM | --- | TBD | 1 | SE142C-251 | In progress. Plan to release before -251. | 50 | GM / MC
|  |  | SE142C-386* (21 GEN) | -2 | 191 | CHILL PLATE PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2
SE142C-388 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-A LOWER CHILL PLATE ASM | --- | TBD | 1 | SE142C-251 | In progress. Plan to release before -251. | 50 | GM / MC
|  |  | SE142C-388* (21 GEN) | -2 | 191 | CHILL PLATE PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2
SE142C-241 | 0 | WIP | SE142C-241 | -1 | AR | TYPE-C COIL SIDE-B ASSEMBLY | --- | TBD | 1 | SE140-103 | In progress. | 40
|  |  | TBD | SE142C-382 | 1 | TYPE-C COIL SIDE-B UPPER CLADDING ASM | --- | --- | 2
|  |  | TBD | SE142C-384 | 1 | TYPE-C COIL SIDE-B LOWER CLADDING ASM | --- | --- | 3
|  |  | SE142C-243 | -4 | 1 | TYPE-C COIL SIDE-B GROUNDWRAP | TBD | --- | 4
|  |  | TBD | -5 | 1 | TYPE-C COIL SIDE-B WINDING PACK | TBD | --- | 5
|  |  | TBD | SE142C-386 | 1 | TYPE-C COIL SIDE-B UPPER CHILL PLATE ASM | --- | --- | 6
|  |  | TBD | SE142C-388 | 1 | TYPE-C COIL SIDE-B LOWER CHILL PLATE ASM | --- | --- | 7
|  |  | TBD | -8 | 2 | WIRE, MINERAL INSULATED | TBD | --- | 8
|  |  | TBD | -9 | 1 | TUBING | TBD | --- | 9
SE142C-482 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-B UPPER CLADDING ASM | --- | TBD | 1 | SE142C-241 | In progress. Plan to release before -241. | 30 | GM / MC
|  |  | SE142C-482* (21 GEN) | -2 | 191 | CLADDING PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2
SE142C-484 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-B LOWER CLADDING ASM | --- | TBD | 1 | SE142C-241 | In progress. Plan to release before -241. | 50 | GM / MC
|  |  | SE142C-484* (21 GEN) | -2 | 191 | CLADDING PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2
SE142C-486 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-B UPPER CHILL PLATE ASM | --- | TBD | 1 | SE142C-241 | In progress. Plan to release before -241. | 50 | JR / MC
|  |  | SE142C-486* (21 GEN) | -2 | 191 | CHILL PLATE PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2
SE142C-488 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-B LOWER CHILL PLATE ASM | --- | TBD | 1 | SE142C-241 | In progress. Plan to release before -241. | 50 | JR / MC
|  |  | SE142C-488* (21 GEN) | -2 | 191 | CHILL PLATE PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2
SE142C-291 | 0 | WIP | SE142C-291 | -1 | AR | TYPE-C VPI ASSEMBLY | --- | TBD | 1 | SE140-103
SE142C-291 | 0 | WIP | TBD | -2 |  | PAD | NEMA GRADE G-11CR | --- | 2 | SE140-103
SE142C-291 | 0 | WIP | TBD | -3 |  | BAG MOLD | VULCANIZING TAPE CHOPPED GLASS | --- | 3 | SE140-103
SE142C-291 | 0 | WIP | TBD | -4 |  | SEAL TUBE | COPPER | --- | 4 | SE140-103
SE142C-270 | 0 | WIP | SE142C-270 | -1 | AR | CLAMP ASSEMBLY | --- | TBD | 1 | SE140-103 | In progress. | 20 | TH / MC
|  |  | SE142C-271 | SE142C-271 | 1 | CLAMP BAR | --- | --- | 2
|  |  | SE142C-272 | SE142C-272 | 1 | BUSHING, SPACER | --- | --- | 3
|  |  | 150743 | -4 | 1 | SCREW, 3/8-16UNC X 1.25 LG HEX SOC HD CAP | SS, UNS S31600 | --- | 4
|  |  | SE142C-273 | SE142C-273 | 2 | WASHER, SPHERICAL CONVEX | --- | --- | 5
|  |  | SE142C-274 | SE142C-274 | 2 | WASHER, SPHERICAL CONCAVE | --- | --- | 6
|  |  | NS151352 | -7 | 16 | WASHER, BELLEVILLE 3/8 ID X 3/4 OD, 114-LBS | INCONEL 718 | --- | 7
|  |  | SE142C-275 | SE142C-275 | 4 | KEEPER | --- | --- | 8
|  |  | SE142C-276 | -9 | 1 | SCREW, SHOULDER | SS, UNS S31600 | --- | 9
|  |  | SE142C-277 | -10 | 2 | SWIVEL PAD | SS, UNS S31600 VLIER SSP300 | --- | 10
|  |  | SE142C-278 | -11 | 2 | WASHER, .75 OD X .34 ID X .04 THK | SS, UNS S31600 MCARR 90107A030 | --- | 11
|  |  | NS153112 | -12 | 2 | SCREW, 1/4-20UNC X .5 LG BUTTON HD CAP | SS, UNS S31600 | --- | 12
SE142C-271 | 0 | WIP | SE142C-271 | -1 | AR | CLAMP BAR | SS, UNS S31600 | --- | 1 | SE142C-270
SE142C-272 | 0 | WIP | SE142C-272 | -1 | AR | BUSHING, SPACER | SS, UNS S31600 | --- | 1 | SE142C-270
SE142C-273 | 0 | WIP | SE142C-273 | -1 | AR | WASHER, SPHERICAL CONVEX | SS, UNS S31600 | --- | 1 | SE142C-270
SE142C-274 | 0 | WIP | SE142C-274 | -1 | AR | WASHER, SPHERICAL CONCAVE | SS, UNS S31600 | --- | 1 | SE142C-270
SE142C-275 | 0 | WIP | SE142C-275 | -1 | AR | KEEPER | SS, UNS S31600 | --- | 1 | SE142C-270
TBD | 0 | WIP | TBD | -1 | AR | LEAD BLOCK MOUNT WELDING FIXTURE | --- | TBD | 1 | --- | In progress. | 60 | PF / MC
[6 empty] | PART | MATL | --- | 2
[6 empty] | PART | MATL | --- | 3
[6 empty] | … | MATL | --- | …
TBD | 0 | WIP | TBD | -1 |  | POST-VPI MODIFICATIONS (Clamp position, studs removed, ins & covers) | MATL | --- | 1 |  | In progress. | 40 | GL / MC
TBD | 0 | WIP | TBD | -1 |  | I&C, PREP FOR COLD TEST | MATL | --- | 1 |  |  | 40
TBD | 0 | WIP | TBD | -1 |  | ROGOWSKI COIL INSTALLATION | MATL | --- | 1 |  |  | 40
TBD | 0 | WIP | TBD | -1 |  | COIL-COIL FLANGE BUSHING INST | MATL | --- | 1 |  |  | 40
930

## TYPE-C
RESP | CHK | DRAWING NO. | REV | REL DATE | MODEL NO. | PART NO. | QTY | DESCRIPTION | MATERIAL / SPECIFICATION | WEIGHT (LBS) | FIND NO. | NEXT ASM | 2005-08-19 | 2005-08-26 | 2005-09-02 | 2005-09-09 | 2005-09-16 | 2005-09-23 |  | 2005-08-18 | 2005-08-19 | 2005-08-20 | 2005-08-21 | 2005-08-22 | 2005-08-23 | 2005-08-24 | 2005-08-25 | 2005-08-26 | 2005-08-27 | 2005-08-28 | 2005-08-29 | 2005-08-30 | 2005-08-31 | 2005-09-01 | 2005-09-02 | 2005-09-03 | 2005-09-04 | 2005-09-05 | 2005-09-06 | 2005-09-07 | 2005-09-08 | 2005-09-09 | 2005-09-10 | 2005-09-11 | 2005-09-12 | 2005-09-13 | 2005-09-14 | 2005-09-15 | 2005-09-16 | 2005-09-17 | 2005-09-18 | 2005-09-19 | 2005-09-20 | 2005-09-21 | 2005-09-22 | 2005-09-23 | 2005-09-24 | 2005-09-25 | 2005-09-26
|  | SE140-103 | 0 | WIP | SE140-103 | -1 | AR | TYPE-C MODULAR COIL ASSEMBLY | --- | TBD | 1 | SE140-003
|  | SE140-103 | 0 | WIP | SE141-103 | SE141-103 | 1 | MOD COIL WINDING FORM ASM TYPE-C | --- | --- | 2 | SE140-003
|  | SE140-103 | 0 | WIP | SE142C-050 | SE142C-050 | 1 | LEADS TERMINAL ASSEMBLY | --- | --- | 3 | SE140-003
|  | SE140-103 | 0 | WIP | SE142C-241 | SE142C-241 | 1 | TYPE-C COIL SIDE-B ASSEMBLY | --- | --- | 4 | SE140-003
|  | SE140-103 | 0 | WIP | SE142C-251 | SE142C-251 | 1 | TYPE-C COIL SIDE-A ASSEMBLY | --- | --- | 5 | SE140-003
|  | SE140-103 | 0 | WIP | SE142C-281 | SE142C-281 | 1 | TYPE-C LEADS ENCLOSURE ASM | --- | --- | 6 | SE140-003
|  | SE140-103 | 0 | WIP | SE142C-291 | SE142C-291 | 1 | TYPE-C VPI ASSEMBLY | --- | --- | 7 | SE140-003
|  | SE140-103 | 0 | WIP | SE142C-270 | SE142C-270 | 1 | CLAMP ASSEMBLY | --- | --- | 8 | SE140-003
DONE |  | SE141-103 | 2 | 2005-08-05 | SE141-103 | -1 | AR | MOD COIL WINDING FORM ASM TYPE-C | --- | 5092 | 1 | SE140-103
|  | SE141-103 | 2 | 2005-08-05 | SE141-116 | SE141-116 | 1 | PRODUCTION WINDING FORM TYPE-C | --- | --- | 2 | SE140-103
|  | SE141-103 | 2 | 2005-08-05 | SE141-078 | SE141-078 | 1 | POL BREAK SHIM ASM TYPE-C | --- | --- | 3 | SE140-103
|  | SE141-103 | 2 | 2005-08-05 | SE141-071 SE141-075 | -4 | 2 | INS SHEET, 32 X 15 X .063 THK | NEMA GRADE G-11CR | --- | 4 | SE140-103
|  | SE141-103 | 2 | 2005-08-05 | SE141-074 | -5 | 14 | INS BUSHING, 1.63 OD X 1.38 ID X 1.68 LG | NEMA GRADE G-11CR | --- | 5 | SE140-103
|  | SE141-103 | 2 | 2005-08-05 | SE141-036 | DS141-036 | 7 | STUD, 1.375-6UNC-2A X 9.5 LG | --- | --- | 6 | SE140-103
|  | SE141-103 | 2 | 2005-08-05 | SE141-080 | -7 | 2 | INS SHEET, 26 X 3 X .063 THK | NEMA GRADE G-11CR | --- | 7 | SE140-103
|  | SE141-103 | 2 | 2005-08-05 | SE141-060 | DS141-060 | 14 | NUT, 12PT HEX 1.375-6UNC-2B | --- | --- | 8 | SE140-103
|  | SE141-103 | 2 | 2005-08-05 | SE141-079 | DS141-079 | 14 | WASHER, 2.75 OD X 1.66 ID X 0.5 THK | --- | --- | 9 | SE140-103
GL | MC | SE141-123 | 0 | WIP | SE141-123 | -1 | AR | TYPE-C WINDING FORM MODS ASM | --- | TBD | 1 | SE140-103 | CP | DR |  |  |  | RCVD
GL | ¦ | SE141-123 | 0 | WIP | SE141-123 | -2 | 1 | LAWTON STOCKED MCWF | --- | --- | 2 | SE140-103 | CP | DR |  |  |  | RCVD
GL | ¦ | SE141-123 | 0 | WIP | TBD | -3 | 1 | POL BREAK SHIM ASSEMBLY | --- | --- | 3 | SE140-103 | CP | DR |  |  |  | RCVD
GL | ¦ | SE141-123 | 0 | WIP | TBD | -4 | 1 | POL BREAK BOLT ASSEMBLY | --- | --- | 4 | SE140-103 | CP | DR |  |  |  | RCVD
GL | ¦ | SE141-123 | 0 | WIP | SE141-123 | -5 | 184 | STUD, 3/8-16UNC X 2.5 LG | SS, UNS S31600 | --- | 5 | SE140-103 | CP | DR |  |  |  | RCVD
GL | ¦ | SE141-123 | 0 | WIP | SE141-124 | -6 | 10 | ADAPTER, 1 DIA X .84 LG | SS, UNS S31600 | --- | 6 | SE140-103 | CP | DR |  |  |  | RCVD
GL | ¦ | SE141-123 | 0 | WIP | TBD | -7 | 1 | LEAD BLOCK MOUNT #1 | SS, UNS S31600 | --- | 7 | SE140-103 | CP | DR |  |  |  | RCVD
GL | ¦ | SE141-123 | 0 | WIP | TBD | -8 | 1 | LEAD BLOCK MOUNT #2 | SS, UNS S31600 | --- | 8 | SE140-103 | CP | DR |  |  |  | RCVD
GL | ¦ | SE141-123 | 0 | WIP | TBD | -9 | 1 | LEAD BLOCK MOUNT #3 | SS, UNS S31600 | --- | 9 | SE140-103 | CP | DR |  |  |  | RCVD
GL | ¦ | SE141-123 | 0 | WIP | TBD | -10 | 1 | LEAD BLOCK MOUNT #4 | SS, UNS S31600 | --- | 10 | SE140-103 | CP | DR |  |  |  | RCVD
DONE |  | SE141-123 | 0 | WIP | TBD | TBD | AR | METROLOGY TARGET | --- | --- | 11 | SE140-103 | [5 empty] | RCVD
PF | MC | TBD | 0 | WIP | TBD | -1 | AR | LEAD BLOCK MOUNT WELDING FIXTURE |  |  | 1
PF | ¦
PF | ¦
GL |  | SE142C-050 | 0 | WIP | SE142C-050 | -1 | AR | LEADS TERMINAL ASSEMBLY | --- | TBD | 1 | SE140-103 |  | CP | DR
GL |  | SE142C-050 | 0 | WIP | SE142C-211 | -2 | AR | INS SHEET, 3.47 X 12.38 X .063 THK | NEMA GRADE G-11CR | --- | 2 | SE140-103
GL |  | SE142C-050 | 0 | WIP | SE142C-047 | SE142C-047 | 1 | JUMPERS BASE BLOCK ASM | --- | --- | 3 | SE140-103 |  | CP | DR
GL |  | SE142C-050 | 0 | WIP | SE142C-049 | -4 | 3 | INS SHEET, 1.5 X 8 X 0.13 THK | NEMA GRADE G-11CR | --- | 4 | SE140-103
GL |  | SE142C-050 | 0 | 2005-08-12 | SE142C-051 | SE142C-051 | 1 | TERMINAL JUMPER #1 | --- | --- | 5 | SE140-103
GL |  | SE142C-050 | 0 | 2005-08-12 | SE142C-052 | SE142C-052 | 1 | TERMINAL JUMPER #2 | --- | --- | 6 | SE140-103
GL |  | SE142C-050 | 0 | 2005-08-12 | SE142C-053 | SE142C-053 | 1 | TERMINAL JUMPER #3 | --- | --- | 7 | SE140-103
GL |  | SE142C-050 | 0 | 2005-08-12 | SE142C-054 | SE142C-054 | 1 | TERMINAL JUMPER #4 | --- | --- | 8 | SE140-103
GL |  | SE142C-050 | 0 | WIP | SE142C-069 | -9 | 3 | INS BUSHING, 0.5 OD X .38 ID X 1.69 LG | NEMA GRADE G-11CR | --- | 9 | SE140-103
GL |  | SE142C-050 | 0 | WIP | SE142C-069 | SE142C-069 | 3 | STUD, 3/8-16UNC X 3 LG | --- | --- | 10 | SE140-103 |  | CP | DR
GL |  | SE142C-050 | 0 | WIP | NS151359 | -11 |  | WASHER, BELLEVILLE .515 ID X 1.29 OD X .129 HT, .029 DEF, 3200-LBS | INCONEL 718 SOLON #8H98718 | --- | 11 | SE140-103
GL |  | SE142C-050 | 0 | WIP | SE142C-225 | -12 |  | WASHER, .406 ID X .813 OD X .063 THK | SS, UNS S31600 MCARR 91950A031 | --- | 12 | SE140-103
GL |  | SE142C-050 | 0 | WIP | 150260 | -13 |  | NUT, 3/8-16UNC STANDARD HEX | SS, UNS S31600 | --- | 13 | SE140-103
GL |  | SE142C-050 | 0 | WIP | SE142C-055 | SE142C-055 | 1 | TERMINAL LUG, SHORT | --- | --- | 14 | SE140-103 |  | CP | DR
GL |  | SE142C-050 | 0 | WIP | SE142C-056 | SE142C-056 | 1 | TERMINAL LUG, LONG | --- | --- | 15 | SE140-103 |  | CP | DR
GL |  | SE142C-050 | 0 | WIP | SE142C-212 | -21 | 1 | INS SHEET, 3.34 X 5.75 X 0.13 THK | NEMA GRADE G-11CR | --- | 16 | SE140-103
GL |  | SE142C-050 | 0 | WIP | SE142C-263 | SE142C-263 | 2 | TERMINAL SPLICE PLATE #1 | --- | --- | 17 | SE140-103 |  | CP | DR
GL |  | SE142C-050 | 0 | WIP | 150741 | -17 | 10 | SCREW, 3/8-16UNC X 1.25 LG HEX SOC HD CAP | --- | --- | 18 | SE140-103
GL |  | SE142C-050 | 0 | WIP | SE142C-060 | SE142C-060 | 16 | CABLE END CONNECTOR ASM | --- | --- | 19 | SE140-103
GL |  | SE142C-050 | 0 | WIP | SE142C-065 | -11 | 16 | WASHER, .531 ID X .875 OD X .063 THK | SS, UNS S31600 MCARR 90107A033 | --- | 20 | SE140-103
GL |  | SE142C-050 | 0 | WIP | 150262 | -16 | 16 | NUT, 1/2-13UNC STANDARD HEX | SS, UNS S31600 | --- | 21 | SE140-103
GL |  | SE142C-050 | 0 | WIP | SE142C-066 | -12 | 2 | COOLING TUBE ASM |  | --- | 22 | SE140-103
GL | [7 empty] | LEAD BLOCK PRE-FIT ASSEMBLY | [7 empty] | CP | DR
GL | [7 empty] | MAG WIRE LAYOUT
POST VPI MODS
I&C DRAWING, PREP FOR COLD TEST
DIAGNOSTICS
CURRENT FEED INSULATION COVER
BUSHING INSTALLATION
|  | SE142C-241 | 0 | WIP | SE142C-241 | -1 | AR | TYPE-C COIL SIDE-B ASSEMBLY | --- | TBD | 1 | SE140-103 | [6 empty] | delay
|  | SE142C-241 | 0 | WIP | TBD | SE142C-481 | 1 | TYPE-C COIL SIDE-B UPPER CLADDING ASM | --- | --- | 2 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | SE142C-483 | 1 | TYPE-C COIL SIDE-B LOWER CLADDING ASM | --- | --- | 3 | SE140-103
|  | SE142C-241 | 0 | WIP | SE142C-243 | -4 | 1 | TYPE-C COIL SIDE-B GROUNDWRAP | TBD | --- | 4 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | -5 | 1 | TYPE-C COIL SIDE-B COND LAYER #1 | TBD | --- | 5 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | -6 | 1 | TYPE-C COIL SIDE-B COND LAYER #2 | TBD | --- | 6 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | -7 | 1 | TYPE-C COIL SIDE-B COND LAYER #3 | TBD | --- | 7 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | -8 | 1 | TYPE-C COIL SIDE-B COND LAYER #4 | TBD | --- | 8 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | SE142C-485 | 1 | TYPE-C COIL SIDE-B UPPER CHILL PLATE ASM | --- | --- | 9 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | SE142C-487 | 1 | TYPE-C COIL SIDE-B LOWER CHILL PLATE ASM | --- | --- | 10 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | -11 |  | WIRE, MINERAL INSULATED | TBD | --- | 11 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | -12 |  | TUBING | TBD | --- | 12 | SE140-103
|  | SE142C-241 | 0 | 2005-06-09 | TBD | SE142C-135 | 1 | TYPE-C COIL SIDE-B LOWER LEAD BLOCK | --- | --- | 13 | SE140-103
|  | SE142C-241 | 0 | 2005-07-08 | TBD | SE142C-137 | 1 | TYPE-C COIL SIDE-B UPPER LEAD BLOCK | --- | --- | 14 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | -15 | 2 | SCREW, | TBD | --- | 15 | SE140-103
|  | SE142C-241 | 0 | WIP | TBD | -16 | 2 | SCREW, | TBD | --- | 16 | SE140-103
|  | SE142C-251 | 0 | WIP | SE142C-251 | -1 | AR | TYPE-C COIL SIDE-A ASSEMBLY | --- | TBD | 1 | SE140-103 | [6 empty] | delay
|  | SE142C-251 | 0 | WIP | TBD | SE142C-381 | 1 | TYPE-C COIL SIDE-A UPPER CLADDING ASM | --- | --- | 2 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | SE142C-383 | 1 | TYPE-C COIL SIDE-A LOWER CLADDING ASM | --- | --- | 3 | SE140-103
|  | SE142C-251 | 0 | WIP | SE142C-253 | -4 | 1 | TYPE-C COIL SIDE-A GROUNDWRAP | TBD | --- | 4 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | -5 | 1 | TYPE-C COIL SIDE-A COND LAYER #1 | TBD | --- | 5 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | -6 | 1 | TYPE-C COIL SIDE-A COND LAYER #2 | TBD | --- | 6 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | -7 | 1 | TYPE-C COIL SIDE-A COND LAYER #3 | TBD | --- | 7 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | -8 | 1 | TYPE-C COIL SIDE-A COND LAYER #4 | TBD | --- | 8 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | SE142C-385 | 1 | TYPE-C COIL SIDE-A UPPER CHILL PLATE ASM | --- | --- | 9 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | SE142C-387 | 1 | TYPE-C COIL SIDE-A LOWER CHILL PLATE ASM | --- | --- | 10 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | -11 |  | WIRE, MINERAL INSULATED | TBD | --- | 11 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | -12 |  | TUBING | TBD | --- | 12 | SE140-103
|  | SE142C-251 | 1 | 2005-08-12 |  | SE142C-134 | 1 | TYPE-C COIL SIDE-A LOWER LEAD BLOCK | --- | --- | 13 | SE140-103
|  | SE142C-251 | 0 | 2005-06-09 | TBD | SE142C-136 | 1 | TYPE-C COIL SIDE-A UPPER LEAD BLOCK | --- | --- | 14 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | -15 | 2 | SCREW, | TBD | --- | 15 | SE140-103
|  | SE142C-251 | 0 | WIP | TBD | -16 | 2 | SCREW, | TBD | --- | 16 | SE140-103
TH |  | SE142C-270 | 0 | WIP | SE142C-270 | -1 | AR | CLAMP ASSEMBLY | --- | TBD | 1 | SE140-103 | CP | DR
|  | SE142C-270 | 0 | WIP | SE142C-271 | SE142C-271 | 1 | CLAMP BAR | --- | --- | 2 | SE140-103
|  | SE142C-270 | 0 | WIP | SE142C-272 | SE142C-272 | 1 | BUSHING, SPACER | --- | --- | 3 | SE140-103
|  | SE142C-270 | 0 | WIP | 150743 | -4 | 1 | SCREW, 3/8-16UNC X 1.25 LG HEX SOC HD CAP | SS, UNS S31600 | --- | 4 | SE140-103
|  | SE142C-270 | 0 | WIP | SE142C-273 | SE142C-273 | 2 | WASHER, SPHERICAL CONVEX | --- | --- | 5 | SE140-103
|  | SE142C-270 | 0 | WIP | SE142C-274 | SE142C-274 | 2 | WASHER, SPHERICAL CONCAVE | --- | --- | 6 | SE140-103
|  | SE142C-270 | 0 | WIP | NS151352 | -7 | 16 | WASHER, BELLEVILLE 3/8 ID X 3/4 OD, 114-LBS | INCONEL 718 | --- | 7 | SE140-103
|  | SE142C-270 | 0 | WIP | SE142C-275 | SE142C-275 | 4 | KEEPER | --- | --- | 8 | SE140-103
|  | SE142C-270 | 0 | WIP | SE142C-276 | -9 | 1 | SCREW, SHOULDER | SS, UNS S31600 | --- | 9 | SE140-103
|  | SE142C-270 | 0 | WIP | SE142C-277 | -10 | 2 | SWIVEL PAD | SS, UNS S31600 VLIER SSP300 | --- | 10 | SE140-103
|  | SE142C-270 | 0 | WIP | SE142C-278 | -11 | 2 | WASHER, .75 OD X .34 ID X .04 THK | SS, UNS S31600 MCARR 90107A030 | --- | 11 | SE140-103
|  | SE142C-270 | 0 | WIP | NS153112 | -12 | 2 | SCREW, 1/4-20UNC X .5 LG BUTTON HD CAP | SS, UNS S31600 | --- | 12 | SE140-103
|  | SE142C-281 | 0 | WIP | SE142C-281 | -1 | AR | TYPE-C LEADS ENCLOSURE ASM | --- | TBD | 1 | SE140-103 | [6 empty] | delay
|  | SE142C-281 | 0 | WIP | TBD | TBD | 8 | FILLER STRIP | --- | --- | 2 | SE140-103
|  | SE142C-281 | 0 | WIP | TBD | TBD | 2 | TYPE-C COIL LEADS AREA CHILL PLATE | --- | --- | 3 | SE140-103
|  | SE142C-281 | 0 | WIP | TBD | -4 | 2 | TUBING | COPPER | --- | 4 | SE140-103
|  | SE142C-281 | 0 | WIP | TBD | -5 | 4 | CONNECTOR | COPPER | --- | 5 | SE140-103
|  | SE142C-281 | 0 | WIP | SE142C-220 | SE142C-220 | 1 | TYPE-C COIL SIDE-A LEADS SIDE PLATE | --- | --- | 6 | SE140-103
|  | SE142C-281 | 0 | WIP | SE142C-221 | SE142C-221 | 1 | TYPE-C COIL SIDE-B LEADS SIDE PLATE | --- | --- | 7 | SE140-103
|  | SE142C-281 | 0 | WIP | TBD | -8 |  | SCREW | SS, UNS S31600 | --- | 8 | SE140-103
|  | SE142C-281 | 0 | WIP | SE142C-184 | SE142C-184 | 1 | TYPE-C COIL LEADS ENCLOSURE TOP PLATE | --- | --- | 9 | SE140-103
|  | SE142C-281 | 0 | WIP | TBD | -10 |  | SCREW | SS, UNS S31600 | --- | 10 | SE140-103
|  | SE142C-281 | 0 | WIP | SE142C-223 | -11 | 1 | BUSHING | SS, UNS S31600 | --- | 11 | SE140-103
GL |  | SE142C-291 | 0 | WIP | SE142C-291 | -1 | AR | TYPE-C VPI ASSEMBLY | --- | TBD | 1 | SE140-103 |  |  |  |  | CP | DR
|  | SE142C-291 | 0 | WIP | TBD | -2 |  | PAD | NEMA GRADE G-11CR | --- | 2 | SE140-103
|  | SE142C-291 | 0 | WIP | TBD | -3 |  | BAG MOLD | VULCANIZING TAPE CHOPPED GLASS | --- | 3 | SE140-103
|  | SE142C-291 | 0 | WIP | TBD | -4 |  | SEAL TUBE | COPPER | --- | 4 | SE140-103
|  | SE141-078 | 1 | 2004-09-23 | SE141-078 | -1 | AR | POL BREAK SHIM ASM TYPE-C | --- | 129 | 1 | SE141-103
|  | SE141-078 | 1 | 2004-09-23 | SE141-073 | -2 | 1 | POLOIDAL BREAK SHIM | SS, CSPEC-141-03 | --- | 2 | SE141-103
|  | SE141-078 | 1 | 2004-09-23 | SE141-077 | -3 | 7 | INS BUSHING, 1.63 OD X 1.38 ID X 2.19 LG | NEMA GRADE G-11CR | --- | 3 | SE141-103
|  | SE142C-045 | 0 | WIP | SE142C-045 | -1 | AR | COOLING TUBE ASM |  | TBD | 1 | SE142C-050
|  | SE142C-045 | 0 | WIP | SE142C-066 | -2 | 1 | SWAGE-LOK CONNECTOR |  | --- | 2 | SE142C-050
|  | SE142C-045 | 0 | WIP | SE142C-047 | -3 | 1 | TUBE |  | --- | 3 | SE142C-050
|  | SE142C-047 | 0 | WIP | SE142C-047 | -1 | AR | JUMPERS BASE BLOCK | --- | 2.5 | 1 | SE142C-050
|  | SE142C-047 | 0 | WIP | SE142C-047 | -2 | 1 | BLOCK, 3.5 X 13.8 X 0.7 THK | NEMA GRADE G-11CR | --- | 2 | SE142C-050
|  | SE142C-047 | 0 | WIP | SE142C-047 | -3 | 7 | INSERT, BUSHING-TYPE, THREADED | SS, UNS S31600 TAP-LOK HM-37516-50 | --- | 3 | SE142C-050
|  | SE142C-060 | 0 | WIP | SE142C-060 | -1 | AR | CABLE END CONNECTOR ASM |  | TBD | 1 | SE142C-050
|  | SE142C-060 | 0 | WIP | SE142C-059 | SE142C-059 | 1 | CABLE CONNECTOR |  | --- | 2 | SE142C-050
|  | SE142C-060 | 0 | WIP | SE142C-046 | SE142C-046 | 1 | CONDUCTOR |  | --- | 3 | SE142C-050
GM | MC | SE142C-481 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-B UPPER CLADDING ASM | --- | TBD | 1 | SE142C-241 | CP | DR
|  | SE142C-481 | 0 | WIP | SE142C-482* (21 GENERICS) | -2 | 191 | CLADDING PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2 | SE142C-241
GM | MC | SE142C-483 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-B LOWER CLADDING ASM | --- | TBD | 1 | SE142C-241 | CP | DR
|  | SE142C-483 | 0 | WIP | SE142C-484* (21 GENERICS) | -2 | 191 | CLADDING PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2 | SE142C-241
JR | MC | SE142C-485 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-B UPPER CHILL PLATE ASM | --- | TBD | 1 | SE142C-241 |  |  | CP | DR
|  | SE142C-485 | 0 | WIP | SE142C-486* (21 GENERICS) | -2 | 191 | CHILL PLATE PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2 | SE142C-241
JR | MC | SE142C-487 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-B LOWER CHILL PLATE ASM | --- | TBD | 1 | SE142C-241 |  |  |  |  | CP | DR
|  | SE142C-487 | 0 | WIP | SE142C-488* (21 GENERICS) | -2 | 191 | CHILL PLATE PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2 | SE142C-241
GM | MC | SE142C-381 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-A UPPER CLADDING ASM | --- | TBD | 1 | SE142C-251 |  | CP | DR
|  | SE142C-381 | 0 | WIP | SE142C-382* (21 GENERICS) | -2 | 191 | CLADDING PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2 | SE142C-251
GM | MC | SE142C-383 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-A LOWER CLADDING ASM | --- | TBD | 1 | SE142C-251 |  |  | CP | DR
|  | SE142C-383 | 0 | WIP | SE142C-384* (21 GENERICS) | -2 | 191 | CLADDING PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2 | SE142C-251
GM | MC | SE142C-385 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-A UPPER CHILL PLATE ASM | --- | TBD | 1 | SE142C-251 |  |  |  | CP | DR
|  | SE142C-385 | 0 | WIP | SE142C-386* (21 GENERICS) | -2 | 191 | CHILL PLATE PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2 | SE142C-251
GM | MC | SE142C-387 | 0 | WIP | NONE | -1 | AR | TYPE-C COIL SIDE-A LOWER CHILL PLATE ASM | --- | TBD | 1 | SE142C-251 |  |  |  |  | CP | DR
|  | SE142C-387 | 0 | WIP | SE142C-388* (21 GENERICS) | -2 | 191 | CHILL PLATE PARTS | COPPER, ANNEALED UNS C10100, C10200 | --- | 2 | SE142C-251
|  | DS141-036 | 1 | 2005-08-05 | SE141-036 | -1 | AR | STUD, 1.375-6UNC-2A X 9.5 LG | ASTM A286 | --- | 1
|  | DS141-060 | 0 | 2004-07-20 | SE141-060 | -1 | AR | NUT, 12PT HEX 1.375-6UNC-2B | ASTM A286 | --- | 1
|  | DS141-079 | 0 | 2004-07-20 | SE141-079 | -1 | AR | WASHER, 2.75 OD X 1.66 ID X 0.5 THK | ASTM A286 | --- | 1
|  | SE141-116 | 6 | 2005-08-05 | SE141-116 | -1 | AR | PRODUCTION WINDING FORM TYPE-C | SS, CSPEC-141-03 | --- | 1
|  | SE142C-046 | 0 | WIP | SE142C-046 | -1 | AR | CONDUCTOR | COPPER, CSPEC-142-03 | --- | 1
|  | SE142C-049 | 0 | WIP | SE142C-049 | -1 | AR | INS SHEET, 1.5 X 8 X 0.13 THK | NEMA GRADE G-11CR | --- | 1
|  | SE142C-051 | 0 | 2005-08-12 | SE142C-051 | -1 | AR | TERMINAL JUMPER #1 | OF COPPER, UNS C10200 | --- | 1
|  | SE142C-052 | 0 | 2005-08-12 | SE142C-052 | -1 | AR | TERMINAL JUMPER #2 | OF COPPER, UNS C10200 | --- | 1
|  | SE142C-053 | 0 | 2005-08-12 | SE142C-053 | -1 | AR | TERMINAL JUMPER #3 | OF COPPER, UNS C10200 | --- | 1
|  | SE142C-054 | 0 | 2005-08-12 | SE142C-054 | -1 | AR | TERMINAL JUMPER #4 | OF COPPER, UNS C10200 | --- | 1
|  | SE142C-055 | 0 | WIP | SE142C-055 | -1 | AR | TERMINAL LUG, SHORT | OF COPPER, UNS C10200 | --- | 1
|  | SE142C-056 | 0 | WIP | SE142C-056 | -1 | AR | TERMINAL LUG, LONG | OF COPPER, UNS C10200 | --- | 1
|  | SE142C-059 | 0 | 2005-07-25 | SE142C-059 | -1 |  | CABLE CONNECTOR | AG BEARING COPPER, UNS C10300/105/107 | --- | 1
|  | SE142C-134 | 1 | 2005-08-12 | SE142C-134 | -1 | AR | TYPE-C COIL SIDE-A LOWER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1
|  | SE142C-135 | 0 | 2005-06-09 | SE142C-135 | -1 | AR | TYPE-C COIL SIDE-B LOWER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1
|  | SE142C-136 | 0 | 2005-07-08 | SE142C-136 | -1 | AR | TYPE-C COIL SIDE-A UPPER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1
|  | SE142C-137 | 0 | 2005-07-08 | SE142C-137 | -1 | AR | TYPE-C COIL SIDE-B UPPER LEAD BLOCK | NEMA GRADE G-11CR | --- | 1
|  | SE142C-183 | 0 | WIP | SE142C-183 | -1 | AR | TYPE-C COIL LEADS AREA CHILL PLATE | COPPER, ANNEALED UNS C10100, C10200 | --- | 1
|  | SE142C-184 | 0 | 2005-07-20 | SE142C-184 | -1 | AR | TYPE-C COIL LEADS ENCLOSURE TOP PLATE | NEMA GRADE G-11CR | --- | 1
|  | SE142C-220 | 0 | 2005-07-26 | SE142C-220 | -1 | AR | TYPE-C COIL SIDE-A LEADS SIDE PLATE | NEMA GRADE G-11CR | --- | 1
|  | SE142C-221 | 0 | 2005-07-26 | SE142C-221 | -1 | AR | TYPE-C COIL SIDE-B LEADS SIDE PLATE | NEMA GRADE G-11CR | --- | 1
|  | SE142C-226 | 0 | WIP | SE142C-226 | -1 | AR | FILLER STRIP | COPPER, ANNEALED UNS C10100, C10200 | --- | 1
|  | SE142C-271 | 0 | WIP | SE142C-271 | -1 | AR | CLAMP BAR | SS, UNS S31600 | --- | 1
|  | SE142C-272 | 0 | WIP | SE142C-272 | -1 | AR | BUSHING, SPACER | SS, UNS S31600 | --- | 1
|  | SE142C-273 | 0 | WIP | SE142C-273 | -1 | AR | WASHER, SPHERICAL CONVEX | SS, UNS S31600 | --- | 1
|  | SE142C-274 | 0 | WIP | SE142C-274 | -1 | AR | WASHER, SPHERICAL CONCAVE | SS, UNS S31600 | --- | 1
|  | SE142C-275 | 0 | WIP | SE142C-275 | -1 | AR | KEEPER | SS, UNS S31600 | --- | 1
|  | SE142C-263 | 0 | WIP | SE142C-263 | -1 | AR | TERMINAL SPLICE PLATE #1 | OF COPPER, UNS C10200 | --- | 1

## TYPE-A
DRAWING NO. | REV | REL DATE | MODEL NO. | PART NO. | QTY | DESCRIPTION | MATERIAL / SPECIFICATION | WEIGHT (LBS) | FIND NO. | NEXT ASM
SE141-101 | 2 | 2005-08-05 | SE141-101 | -1 | AR | MOD COIL WINDING FORM ASM TYPE-A | --- | 4983 | 1 | SE140-101
SE141-101 | 2 | 2005-08-05 | SE141-114 | SE141-114 | 1 | PRODUCTION WINDING FORM TYPE-A | --- | --- | 2 | SE140-101
SE141-101 | 2 | 2005-08-05 | SE141-048 | SE141-048 | 1 | POL BREAK SHIM ASM TYPE-A | --- | --- | 3 | SE140-101
SE141-101 | 2 | 2005-08-05 | SE141-031 SE141-035 | -4 | 2 | INS SHEET, 32 X 15 X .063 THK | NEMA GRADE G-11CR | --- | 4 | SE140-101
SE141-101 | 2 | 2005-08-05 | SE141-034 | -5 | 14 | INS BUSHING, 1.63 OD X 1.38 ID X 1.74 LG | NEMA GRADE G-11CR | --- | 5 | SE140-101
SE141-101 | 2 | 2005-08-05 | SE141-036 | DS141-036 | 7 | STUD, 1.375-6UNC-2A X 9.5 LG | --- | --- | 6 | SE140-101
SE141-101 | 2 | 2005-08-05 | SE141-083 | -7 | 2 | INS SHEET, 26 X 3 X .063 THK | NEMA GRADE G-11CR | --- | 7 | SE140-101
SE141-101 | 2 | 2005-08-05 | SE141-060 | DS141-060 | 14 | NUT, 12PT HEX 1.375-6UNC-2B | --- | --- | 8 | SE140-101
SE141-101 | 2 | 2005-08-05 | SE141-079 | DS141-079 | 14 | WASHER, 2.75 OD X 1.66 ID X 0.5 THK | --- | --- | 9 | SE140-101
SE141-121 | 0 | WIP | SE141-121 | -1 | AR | TYPE-A WINDING FORM MODS ASM | --- | TBD | 1 | SE140-101
SE141-121 | 0 | WIP | SE141-121 | -2 | 1 | LAWTON STOCKED MCWF TYPE-A | --- | --- | 2 | SE140-101
SE141-121 | 0 | WIP | TBD | -3 | 1 | POL BREAK SHIM ASSEMBLY | --- | --- | 3 | SE140-101
SE141-121 | 0 | WIP | TBD | -4 | 1 | POL BREAK BOLT ASSEMBLY | --- | --- | 4 | SE140-101
SE141-121 | 0 | WIP | SE141-121 | -5 | 184 | STUD, 3/8-16UNC X 2.5 LG | SS, UNS S31600 | --- | 5 | SE140-101
SE141-121 | 0 | WIP | SE141-127 | -6 | 10 | ADAPTER, 1 DIA X .84 LG | SS, UNS S31600 | --- | 6 | SE140-101
SE141-121 | 0 | WIP | TBD | -7 | 1 | LEAD BLOCK MOUNT #1 | SS, UNS S31600 | --- | 7 | SE140-101
SE141-121 | 0 | WIP | TBD | -8 | 1 | LEAD BLOCK MOUNT #2 | SS, UNS S31600 | --- | 8 | SE140-101
SE141-121 | 0 | WIP | TBD | -9 | 1 | LEAD BLOCK MOUNT #3 | SS, UNS S31600 | --- | 9 | SE140-101
SE141-121 | 0 | WIP | TBD | -10 | 1 | LEAD BLOCK MOUNT #4 | SS, UNS S31600 | --- | 10 | SE140-101
SE141-121 | 0 | WIP | TBD | TBD | AR | METROLOGY TARGET | --- | --- | 11 | SE140-101
SE141-048 | 1 | 2004-09-23 | SE141-048 | -1 | AR | POL BREAK SHIM ASM TYPE-A | --- | 104.7 | 1 | SE141-101
SE141-048 | 1 | 2004-09-23 | SE141-033 | -2 | 1 | POLOIDAL BREAK SHIM | SS, CSPEC-141-03 | --- | 2 | SE141-101
SE141-048 | 1 | 2004-09-23 | SE141-077 | -3 | 7 | INS BUSHING, 1.63 OD X 1.38 ID X 2.19 LG | NEMA GRADE G-11CR | --- | 3 | SE141-101
SE141-058 | 1 | 2004-09-23 | SE141-058 | -1 | AR | POL BREAK SHIM ASM TYPE-B | --- | 119 | 1 | SE141-102
SE141-058 | 1 | 2004-09-23 | SE141-053 | -2 | 1 | POLOIDAL BREAK SHIM | SS, CSPEC-141-03 | --- | 2 | SE141-102
SE141-058 | 1 | 2004-09-23 | SE141-077 | -3 | 7 | INS BUSHING, 1.63 OD X 1.38 ID X 2.19 LG | NEMA GRADE G-11CR | --- | 3 | SE141-102
SE141-114 | 5 | 2005-08-05 | SE141-114 | -1 | AR | PRODUCTION WINDING FORM TYPE-A | SS, CSPEC-141-03 | --- | 1
SE141-115 | 5 | 2005-08-05 | SE141-115 | -1 | AR | PRODUCTION WINDING FORM TYPE-B | SS, CSPEC-141-03 | --- | 1

## TYPE-B
DRAWING NO. | REV | REL DATE | MODEL NO. | PART NO. | QTY | DESCRIPTION | MATERIAL / SPECIFICATION | WEIGHT (LBS) | FIND NO. | NEXT ASM
SE141-102 | 2 | 2005-08-05 | SE141-102 | -1 | AR | MOD COIL WINDING FORM ASM TYPE-B | --- | 4941 | 1 | SE140-102
SE141-102 | 2 | 2005-08-05 | SE141-115 | SE141-115 | 1 | PRODUCTION WINDING FORM TYPE-B | --- | --- | 2 | SE140-102
SE141-102 | 2 | 2005-08-05 | SE141-058 | SE141-058 | 1 | POL BREAK SHIM ASM TYPE-B | --- | --- | 3 | SE140-102
SE141-102 | 2 | 2005-08-05 | SE141-051 SE141-055 | -4 | 2 | INS SHEET, 32 X 15 X .063 THK | NEMA GRADE G-11CR | --- | 4 | SE140-102
SE141-102 | 2 | 2005-08-05 | SE141-054 | -5 | 14 | INS BUSHING, 1.63 OD X 1.38 ID X 1.68 LG | NEMA GRADE G-11CR | --- | 5 | SE140-102
SE141-102 | 2 | 2005-08-05 | SE141-036 | DS141-036 | 7 | STUD, 1.375-6UNC-2A X 9.5 LG | --- | --- | 6 | SE140-102
SE141-102 | 2 | 2005-08-05 | SE141-082 | -7 | 2 | INS SHEET, 26 X 3 X .063 THK | NEMA GRADE G-11CR | --- | 7 | SE140-102
SE141-102 | 2 | 2005-08-05 | SE141-060 | DS141-060 | 14 | NUT, 12PT HEX 1.375-6UNC-2B | --- | --- | 8 | SE140-102
SE141-102 | 2 | 2005-08-05 | SE141-079 | DS141-079 | 14 | WASHER, 2.75 OD X 1.66 ID X 0.5 THK | --- | --- | 9 | SE140-102
SE141-122 | 0 | WIP | SE141-122 | -1 | AR | TYPE-B WINDING FORM MODS ASM | --- | TBD | 1 | SE140-102
SE141-122 | 0 | WIP | SE141-122 | -2 | 1 | LAWTON STOCKED MCWF TYPE-B | --- | --- | 2 | SE140-102
SE141-122 | 0 | WIP | TBD | -3 | 1 | POL BREAK SHIM ASSEMBLY | --- | --- | 3 | SE140-102
SE141-122 | 0 | WIP | TBD | -4 | 1 | POL BREAK BOLT ASSEMBLY | --- | --- | 4 | SE140-102
SE141-122 | 0 | WIP | SE141-122 | -5 | 184 | STUD, 3/8-16UNC X 2.5 LG | SS, UNS S31600 | --- | 5 | SE140-102
SE141-122 | 0 | WIP | SE141-128 | -6 | 10 | ADAPTER, 1 DIA X .84 LG | SS, UNS S31600 | --- | 6 | SE140-102
SE141-122 | 0 | WIP | TBD | -7 | 1 | LEAD BLOCK MOUNT #1 | SS, UNS S31600 | --- | 7 | SE140-102
SE141-122 | 0 | WIP | TBD | -8 | 1 | LEAD BLOCK MOUNT #2 | SS, UNS S31600 | --- | 8 | SE140-102
SE141-122 | 0 | WIP | TBD | -9 | 1 | LEAD BLOCK MOUNT #3 | SS, UNS S31600 | --- | 9 | SE140-102
SE141-122 | 0 | WIP | TBD | -10 | 1 | LEAD BLOCK MOUNT #4 | SS, UNS S31600 | --- | 10 | SE140-102
SE141-122 | 0 | WIP | TBD | TBD | AR | METROLOGY TARGET | --- | --- | 11 | SE140-102