## Sheet1
Status of parts on SE123-049 |  | as of: | 2005-12-20 | version
Vacuum Vessel Heating and Cooling Assembly Drawing
10%
| Parts list from drawing: |  |  |  | QTY for one field period | QTY for three field periods | spares if applicable 10% | min qty to order | Part no. | Description |  | release level of drawing | test qty | all
[5 empty] | 16 | 48 | 5 | 53 | NCSX-PRL-12-004-00 | Heat tape 0.5" wide x 0.125" thick x 72" long | Brisk Heat TBD | N/A | 4
[5 empty] | 128 | 384 | 58 | 442 | 5FF-5-4 | Brazetyte reducer union | Truly tubular fittings corporation Mount Vernon, NY 10550 914-664-8686 | N/A
[5 empty] | 128 | 384 | 58 | 442 | 5182K719 | 316 SS YOR-LOK Compression Tube Fitting Coupling for 5/16" Tube OD | McMaster-Carr Atlanta, GA 30336-2852 (404) 346-7000 | N/A | 4
[5 empty] | 460 | 1380 | 207 | 1587 | 90545A030 | HEX NUT 5/16-18 UNC ASME B18.2.2 Titanium | McMaster-Carr Atlanta, GA 30336-2852 (404) 346-7000 | N/A
[5 empty] | 20 | 60 | 9 | 69 | 93190A578 | Hex Head screw 5/16-18 UNC x .5 long | McMaster-Carr Atlanta, GA 30336-2852 (404) 346-7000 | N/A
[5 empty] | 128 | 384 | 58 | 442 | 91950A027 | Flat washer .50 OD x .219 ID x 0.036 thk 316 stainless steel | McMaster-Carr Atlanta, GA 30336-2852 (404) 346-7000 | N/A
[5 empty] | 28 | 84 | 13 | 97 | 91950A030 | Flat washer .688 OD x .344 ID x 0.064 thk 316 stainless steel | McMaster-Carr Atlanta, GA 30336-2852 (404) 346-7000 | N/A
[5 empty] | 128 | 384 | 58 | 442 | 91950A030 | Slotted pan head screw #10-24UNC x .38 long | McMaster-Carr Atlanta, GA 30336-2852 (404) 346-7000 | N/A
[5 empty] | 120 | 360 | 54 | 414 | 94819A046 | hex nut 5/16-18 UNC - ASME B18.2.2 316 sst | McMaster-Carr Atlanta, GA 30336-2852 (404) 346-7000 | N/A |  | x
[5 empty] | 485 | 1455 | 218 | 1673 | -37 | 5/16 - 18 UNC x .75 long CD inconel weld stud | McMaster-Carr Atlanta, GA 30336-2852 (404) 346-7000 | N/A
[5 empty] | 128 | 384 | 58 | 442 | SE123-172-3 | Tube Mount Stop |  | Fabrication
[5 empty] | 2 | 6 | 0 | 6 | SE123-171 | support brkt B weldment |  | Fabrication |  | x
[5 empty] | 2 | 6 | 0 | 6 | SE123-170 | support brkt A weldment |  | Fabrication |  | x
[5 empty] | 64 | 192 | 29 | 221 | SE123-169-2 | VV heating/cooling supply line detail |  | Fabrication
[5 empty] | 64 | 192 | 29 | 221 | SE123-169-1 | VV heating/cooling supply line detail |  | Fabrication
[5 empty] | 8 | 24 | 4 | 28 | SE123-168-6 | U-Bracket long stop |  | Fabrication |  | x
[5 empty] | 8 | 24 | 4 | 28 | SE123-168-5 | U-Bracket long |  | Fabrication |  | x
[5 empty] | 8 | 24 | 4 | 28 | SE123-168-4 | U-bracket |  | Fabrication |  | x
[5 empty] | 8 | 24 | 4 | 28 | SE123-168-1 | header bracket standoff weldment |  | Fabrication |  | x
[5 empty] | 4 | 12 | 2 | 14 | SE123-167 | Mount flange |  | Fabrication |  | x
[5 empty] | 2 | 6 | 0 | 6 | SE123-164 | Cryostat interface flange |  | Fabrication |  | x
[5 empty] | 2 | 6 | 0 | 6 | SE123-163 | outer header B |  | Fabrication |  | x
[5 empty] | 2 | 6 | 0 | 6 | SE123-162 | outer header A |  | Fabrication |  | x
[5 empty] | 2 | 6 | 0 | 6 | SE123-161 | inner header B |  | Fabrication |  | x
[5 empty] | 2 | 6 | 0 | 6 | SE123-160 | inner header A |  | Fabrication |  | x
[5 empty] | 29 | 87 | 13 | 100 | SE123-155 | Thermocouple mounting plate |  | WIP | 6
[5 empty] | 460 | 1380 | 207 | 1587 | SE123-056 | Tube retaining washer |  | WIP
[5 empty] | 460 | 1380 | 207 | 1587 | SE123-054 | Strap |  | WIP
[5 empty] | 460 | 1380 | 207 | 1587 | SE123-053 | Conductor gasket |  | WIP
[5 empty] | 460 | 1380 | 207 | 1587 | SE123-052 | Conductor gasket |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-14 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-13 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-12 | Heating/Cooling tube Weldment |  | WIP
| Flexible cooling tube lengths |  |  |  | 4 | 12 | 2 | 14 | SE123-145-11 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 8 | 24 | 4 | 28 | SE123-145-10 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-9 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-8 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-7 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-6 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 8 | 24 | 4 | 28 | SE123-145-5 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-4 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-3 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-2 | Heating/Cooling tube Weldment |  | WIP
[5 empty] | 4 | 12 | 2 | 14 | SE123-145-1 | Heating/Cooling tube Weldment |  | WIP