March 29, 2006

To: Distribution

From: Wayne Reiersen

Subject: Agenda for April 03 telecon

I am putting out a more detailed agenda so folks [1] can plan to attend only that portion of the Monday telecon that pertains to them and [2] will know what they are expected to report on.  This will minimize the burden on people’s time and sharpen the focus of the meeting while still providing a forum to discuss emerging issues.  Notice that whereas we previously had two telecons which tended to blend into one, we now just have one.

9:30	Coil procurements and fabrication

- Report on notable developments and urgent needs, especially re new clamp hardware to correct problems reported on March 27. (Dudek)

- Report on any assembly issues with the expanded clamp envelope (Brown)

- Report on progress re modular coil drawings being released for fabrication.  (Williamson)

9:40	Electrical joint performance and design

- Report on final configuration for providing contact pressure across conical seat and measured contact resistances.  Compare with TRC results. (Chrzanowski)

- Discuss changes (if any) appropriate for C2. (All)

9:55	Coil testing preparations

- Report on plans, progress, and issues related to coil testing.  Address grounding, support of hard tubing, instrumentation, current feeds, and lug cooling.  Identify information needed from ORNL to initiate coil testing. (Gettelfinger)

- Report on predictive analysis results, recommended current level, pulse length, TC location, and protection settings. (Nelson)

- 10:10	Heating/cooling tube design

- Report on progress finalizing the layout of tubes on the vessel and their integration with the magnetic diagnostics design (Cole)

- Report on resolution of issues from clamp FDR and readiness for hose and thermohydraulic FDR on April 4. (Goranson)

- 10:20	Magnetic diagnostics

- Report on plans, progress, and issues related to magnetic diagnostics.  (Labik)

- 10:30	VVSA work

- Report on disposition of NCRs and MTM response.  Provide assessment of potential schedule impact. (Viola)

- 10:45	Station 1 documentation, plan, and procedure development

- Report on status of documentation required to be in place for Station 1 operation (Viola)

- Report on schedule for ACC review (Viola)

- Cc: Dudek, Chrzanowski, Williamson, Nelson, Brown, Cole, Neilson, Fogarty, Gettelfinger, Strykowsky, Goranson, Labik, Stratton, Zarnstorff, Raftopoulos, Viola, Simmons, Edwards, Williams