04 March 2006

To: Distribution

From: Wayne Reiersen

Subject: Notes from the February 27 telecon on preparations for MC fabrication

Our weekly telecon to track plans, progress and issues regarding preparations for MC fabrication was held on February 27.  The next telecon is TBD.  I will be unavailable the next two Mondays.  Jim Chrzanowski who will be coordinating these telecons in my absence is also unavailable during our regular 9:30am time slot on Monday, March 6.  Please stay tuned…

- Needs for Type C coil assembly.

  - Routing of coolant tubes and co-wound loops.  Williamson requested that Chrzanowski provide the details of the routing so that ORNL could reflect those details in the design documentation.  Williamson indicated that the flux loop details are missing.  Later in the week, Chrzanowski expressed an interest in bring the coolant tubes out straighter through the bag mold on C2 and beyond to make sealing the penetration easier.

Post-VPI procedures and coil testing.  Issues associated with post-VPI procedures and coil testing were discussed.  Specific concerns include:

Design for connecting and feeding all of the cooling passages.  This is not only a cooling performance issue but a space issue for assembling coil-to-coil connections.  Gettelfinger to do flow calculations for lead block chill plates.

Design of the electrical breaks and high resistance grounds.  Gettelfinger agreed to take the lead here.  He will prototype Teflon tubing as the electrical break prior to testing the C1 coil using backing inserts as recommended by Irby (MIT).  Nelson and Cole to provide guidance.

Design of the instrumentation (flow, electrical, and temperature) and control for the modular coils, especially for the C1 coil which will undergo qualification testing

Coil protection requirements and settings.  Parameters needed to be provided by Gettelfinger to ORNL.

Placement of strain gages and resolution of issues with strain gage measurements on the TRC

Coil test procedures for qualifying the design of the Type C coil

Predictive analysis of coil performance that can be compared with measured values during qualification testing.  Freudenberg to provide predictive analysis.  Nelson requested that Fan provide independent calculation.

Qualification of the kickless cable design (or a suitable alternative) for use in the qualifying the C1 coil.  Gettelfinger and Ramakrishnan have inspected the kickless cable and suspect that it is not design for high voltage operation.  Gettelfinger will meggar it to the required 7.5kV manufacturing test voltage.  If it fails, then he will design solid bus to connect to the C1 coil for coil testing.

It is imperative that the hydraulic circuit design be completed so the electrical breaks can be installed and the C1 be declared finished before the end of March.  Coil testing will be confirmatory in nature.  The later we do it, the more re-work we will have to do in the event of a problem so we do not want that to languish either.  Details required to complete the C1 coil should be discussed at the next meeting (Nelson).

- Needs for Type A procurements and assembly

  - Lead blocks.  Lead block drawings for the Type A coil are now in checking and should be complete by March 3.

  - Cladding drawings.  Cladding drawings are improved and nearly complete.  Labels now reference the coil side and hole.  Williamson reported that the cladding drawings for the Type A coil should be in checking by March 3.

  - Prosthetic piece.  There is one region on the Type A coil that will require a prosthetic piece for coil assembly.  The model was sent up to Dudek and Chrzanowski for review and comment.  Upon review, Dudek indicated that this part could not be fabricated at PPPL and would have to be sent out for fabrication.  It would likely have to be hogged out of a solid piece of SS.  This part too should be ready to be released for fabrication very shortly.

The next telecon will be the announced shortly.  Please be prepared to discuss the needs and status of time critical items.

Distribution: Dudek, Chrzanowski, Williamson, Nelson, Brown, Cole, Neilson, Fogarty, Gettelfinger, Williams, Strykowsky