10 January 2006

To: Distribution

From: Wayne Reiersen

Subject: Notes from yesterday’s meeting on Station 1 preparations

Our weekly telecon to track progress and issues regarding Station 1 preparation activities was held yesterday.  Dudek, Viola, Labik, Brown, and Reiersen participated from PPPL.  Goranson participated from ORNL.  The most alarming developments were that the procurement of the flux loop templates, heater tape, and H/C tubes are all slipping out to where the components may not be on hand when needed.  Every effort should be made to complete the design work expeditiously and initiate these procurements ASAP.

- Procurements (Dudek).  Dudek reported that the procurements of the cryostat interface flange and H/C manifolds were going well.  He expressed concern that other procurements such as the flux loop templates, heater tape, and H/C tubes were late and could impact work on Station 1.  (Responsible parties [Brown and Goranson] need to expedite these procurements.)  An updated BOM was provided to Dudek by Nelson before the holidays.  This BOM came off the -049 assembly drawing which is not the top level assembly drawing for the Station 1 assembly.  The only parts in the Station 1 assembly that are not called out on the -049 drawing are the magnetic loops according to Tom Brown.  (Dudek should verify that the BOM he has is complete.)

- Station 1 fabrication and installation (Dudek). Fabrication is proceeding well and should be finished next week.  Higher priority is given to other NCSX jobs in the queue as this one is not schedule critical.

- Magnetic diagnostics (Labik).  Labik reported that the fabrication drawings for the template procurement are lagging.  The earliest we now expect the drawings to be completed is next week (January 20).  (Brown to expedite completion of the template fabrication drawings.)  The risk that the templates will not be available when needed is a real concern.  Options for expediting the procurement of fabricating at least some of the templates in-house should be explored.  (Labik is requested to recommend a procurement plan at the next meeting.)  Labik reported that the layout of the loops has been changing but has finally settled down (we think).  Tom Brown needs to communicate to Martin Brown the final loop layout so the loops can be incorporated into the model and installation drawings.  Labik reported that it has been decided to not route the leads from the co-wound loops on the modular coils up Port 12, but rather out through the cryostat via a different route.

- H/C tube final design (Goranson).  Tests are required to confirm acceptable heat transfer characteristics.  Plans are to use the NSTX centerstack prototype as a testbed for determining the heat transfer characteristics of the H/C tube options and confirm that at least one of the candidates provides acceptable performance.  Candidates presently include the baseline - flexible tubing with a braid (perhaps augmented with copper straps) and alternates - flexible tubing sans braid and flexible tubing joined by short lengths of rigid tubing.  The baseline will be tested first.  Completion of the tests for the baseline has slipped to January 31.  (Goranson to expedite testing the baseline H/C tube design.)  If successful, we will proceed with an FDR in early February.  If the tests arte not successful, we will proceed to test the alternates, pushing the FDR even further back.  PPPL [Viola and Dudek] volunteered to procure some ¼” SS tubing to see if the “heat and bend in situ” option is feasible.  These tests should also be concluded before the end of the month.  (Dudek to expedite testing the in situ option.)

- Heater tape design (Goranson).  A non-magnetic heater tape is on order.  ORNL will test it as part of an integrated test (prototype) of the H/C tubes, heater tape, thermal insulation system, and magnetic loops.  However, this integrated test would likely occur after we need to order the heater tape for Port 12.  The plan is for ORNL to do some basic tests with the non-magnetic heater tape – make sure it can operate at 350C and verify that it is non-magnetic.  If successful, ORNL will schedule an FDR to review the results and we will go forward with the procurement for Port 12.  The integrated test, which will address whether we can really control the temperature profile adequately, should be completed before we install the heater tape on Port 12.  Upon completion of the integrated test, there will be a follow-up FDR that will be used as the basis for authorizing installation of the heater tape on Port 12 and procurement of the heater tape for the other port extensions.  (Goranson to expedite basic testing of the heater tape and conduct of the integrated test.  Target should be to complete basic testing by January 27 with the FDR completed by February 3.)

- Station 1 plan and procedure development (Viola).  There are a number of plans and procedures required for Station 1 activities.  The Station 1 Dimensional Control Plan (Stratton) is complete and in the signature loop.  The Station 1 FPA Sequence Plan (Brown) is in the review cycle.  These two documents along with the Station 1 assembly drawings are foundational for developing the Station 1 MIT/QA Plan and implementing procedures.  The project has been developing guidelines for what should be in a facility operations plan and what should be in an MIT/QA plan.  Bob Simmons is updating the Manufacturing Facility Operations Plan and the draft Station 1 MIT/QA Plan consistent with these guidelines.  These updates should be complete by January 20.  (Viola to provide a plan for procedure development including [1] what specific procedures are planned to be developed [2] who is responsible for drafting the procedure and [3] what is the schedule for preparing each procedure at the next meeting.)  In addition to the -049 assembly drawing and the assembly drawing for the magnetic loops, installation drawings have been generated to define the Station 1 assembly.  These drawings include SE121-004, -005, -008, and -009; and SE310-030-1, -2, and -3.  Brown stated that the drawings are complete but that the loop geometry needs to be updated.  Viola contends that the present suite of drawings is inadequate to even begin writing procedures.  (Viola to resolve with Brown by the next meeting the additional information required on the drawings to support writing the procedures and performing Station 1 assembly activities.)

- Station 1 metrology (Raftopoulos). The Leica laser tracker and a refurbished Romer arm will reportedly be used for assembly operations on Station 1.  The Leica has not been used before on the NCSX project.  New software has been bought or is planned to be bought.  Nobody is expert in the use of this equipment.  Training options have been explored but not exercised.  The Romer arm requisition which was submitted prior to the holidays was rejected because there was no JCNP provided.  Raftopoulos is asked to discuss at the next meeting his plan for ensuring that all of the required hardware and software for metrology activities on Station 1 is operational and personnel have been trained before Station 1 activities are scheduled to begin.

The next meeting will be the next Monday, January 16, at our regular 10am time slot.  Please be prepared to respond to the assigned action items.

Distribution: Dudek, Nelson, Goranson, Labik, Brown, Cole, Neilson, Stratton, Zarnstorff, Raftopoulos, Viola, Simmons, Edwards