23 January 2006

To: Distribution

From: Wayne Reiersen

Subject: Notes from yesterday’s meeting on Station 1 preparations

Our weekly telecon to track progress and issues regarding Station 1 preparation activities was held yesterday.  Dudek, Brown, Raftopoulos, Edwards, Stratton, and Reiersen participated from PPPL.  Goranson and Cole participated from ORNL.  Viola was away at MTM assisting in leak checking so there was no report on Station 1 plan and procedure development.  Some procurements needed for Station 1 including the flux loop templates, heater tape, and H/C tubes still have not been placed but progress was reported.

- Procurements (Dudek).  Dudek has continuing concern that procurements such as the flux loop templates, heater tape, and H/C tubes are late and could impact work on Station 1.  He reported that the cryostat interface flange should be here by next week.

- Station 1 fabrication and installation (Dudek). No change was reported.  Fabrication should be finished soon.  Higher priority is given to other NCSX jobs in the queue as this one is not schedule critical.

- Magnetic diagnostics (Labik).

  - Tom Brown reported that the template drawings should be released for fabrication today.  (Brown to continue to expedite completion of the template fabrication drawings.)

  - The risk that the templates will not be available when needed is still a real concern.  Options for expediting the procurement of fabricating at least some of the templates in-house should be explored.  (Labik is requested to recommend a procurement plan at the next meeting.)

  - Tom Brown reported that the loop positions have been sent to Cole who will be updating the Martin Brown drawings.  Cole will coordinate the stud locations with Goranson.  Tom Brown indicated that the routing of the leads for the flux loops should be straightforward except near the vertical port where they all come together.

  - Tom Brown reported that the loop locations were sent to Neil Pomphrey.  Brown is waiting for a response from Pomphrey re the changes that were implemented.

- H/C tube final design (Goranson).

  - Goranson reported that the first tests of the H/C tube were performed.  Another run will be made this week to correlate with ANSYS on the proper heat transfer coefficient to use.  Goranson thought we should know by the end of the week whether the baseline tube design would be acceptable.  Reiersen requested that the performance for heating and cooling be separately reported.  If successful, we will proceed with an FDR in early February.  If the tests are not successful, we will proceed to test the alternates, pushing the FDR even further back.  (Goranson to expedite completion of tests and, if successful, conduct of the FDR.)

  - PPPL [Viola and Dudek] volunteered to procure some ¼” SS tubing to see if the “heat and bend in situ” option is feasible.  These tests should also be concluded before the end of the month.  No report given on progress this week.

- Heater tape design (Goranson).

  - A non-magnetic heater tape is on order but has not arrived yet.  Dudek reported that it is due at ORNL this week.  The plan is for ORNL to do some basic tests with the non-magnetic heater tape – make sure it can operate at 350C and verify that it is non-magnetic.  If successful, ORNL will schedule an FDR to review the results and we will go forward with the procurement for Port 12.  (Goranson to expedite basic testing of non-magnetic heater tape.)

  - ORNL will also test the heater tape as part of an integrated test (prototype) of the H/C tubes, heater tape, thermal insulation system, and magnetic loops.  The integrated test, which will address whether we can really control the temperature profile adequately, should be completed before we install the heater tape on Port 12.  Upon completion of the integrated test, there will be a follow-up FDR that will be used as the basis for authorizing installation of the heater tape on Port 12 and procurement of the heater tape for the other port extensions.  No progress was reported on setting up the integrated test, but it was noted that this work is not schedule critical for the heater tapes which can be installed after the flux loops and H/C tubes if necessary.  (Goranson to expedite conduct of the integrated test.)

- Station 1 plan and procedure development (Viola).

  - No report this week.  There are a number of plans and procedures required for Station 1 activities.  The Station 1 Dimensional Control Plan (Stratton) is complete and in the signature loop.  The Station 1 FPA Sequence Plan (Brown) is in the review cycle.  These two documents along with the Station 1 assembly drawings are foundational for developing the Station 1 MIT/QA Plan and implementing procedures.  The project has developed guidelines for what should be in a facility operations plan and what should be in an MIT/QA plan.  Bob Simmons has updated the Manufacturing Facility Operations Plan and the draft Station 1 MIT/QA Plan consistent with these guidelines.  The updated plans were sent out for review.  Viola discussed his vision of procedures required for Station 1.  The first Station 1 procedure will be a QA procedure which Viola and Edwards will write.  This procedure will include [1] a “gross damage and number count” receipt inspection of the VVSA [2] mounting the VV period assembly in the turning fixture [3] performing a metrology check of the VVSA dimensions and [4] performing receipt inspection of all components to be installed on Station 1 including H/C tubes and manifold assemblies and attaching hardware; heater tapes; cryostat interface flanges; flux loop templates and wire; and miscellaneous hardware.  Viola is planning to have supporting procedures written for the VV period assembly critical lift (Viola) and metrology check (Raftopoulos).  The QA procedure should be out fro review by February 7.  (Viola to develop a comprehensive list of procedures to execute all the work on Station 1 and to work with Dudek to have all activities associated with procedure development, review, and approval reflected in the schedule for Station 1 prep which Dudek is maintaining.)

  - There was discussion of what drawings would be available to support work on Station 1 and what additional drawings would be required.  (Viola to resolve with Brown the additional information required on the drawings to support writing the procedures and performing Station 1 assembly activities.  He should also explore the use of “eDrawings” to facilitate viewing of Pro/E models and assemblies during FPA.)

- Station 1 metrology (Raftopoulos).

  - The Leica laser tracker and a refurbished Romer arm will reportedly be used for assembly operations on Station 1.  The Leica has not been used before on the NCSX project.  New software has been bought or is planned to be bought.  Nobody is expert in the use of this equipment. (Raftopoulos to verify that the Leica is in proper working order.)

  - Raftopoulos indicated that if Duco was available the week of February 27 (Edwards to confirm), then training in the use of Verisoft software in conjunction with the Leica laser tracker and Romer arm could be done at that time.  (Raftopoulos to get PO issued for training that week.)

  - Raftopoulos would like for the training to be conducted on the VVSA and would like to trial the procedures for mounting the flux loops and studs for the H/C tube clamps as part of the training.  (Raftopoulos to make the necessary arrangements for all of the hardware required to support the training to be available on time.  Raftopoulos is also asked to update his plan for ensuring that all of the required hardware and software for metrology activities on Station 1 is operational and personnel have been trained before Station 1 activities are scheduled to begin consistent with this new training date.)

Please advise if any additions or corrections are in order.  There will be no meeting next week.  The next meeting will be the next Monday, February 6, at our regular 10am time slot.  Please be prepared to respond to the assigned action items.

Distribution: Dudek, Nelson, Goranson, Labik, Brown, Cole, Neilson, Stratton, Zarnstorff, Raftopoulos, Viola, Simmons, Edwards