27 March 2006

To: Distribution

From: Wayne Reiersen

Subject: Notes from 27 March meeting on Station 1 preparations

Our weekly telecon to track progress and issues regarding Station 1 preparation activities was held on March 27.  Notes from the meeting are provided below.

- Procurements (Dudek).

  - Heater tape, manifold, and stud requisitions placed.

  - US Hose indicated that they could provide a hose that has a permeability <1.02 along the hose and <1.05 at the ends.  The price quoted was $133 per 16 ft length for an order of 400 pieces. Requisition awaiting FDR now scheduled for April 4.

- Station 1 fabrication and installation (Dudek). Both fixtures have been completed but the brakes are still being installed in the shop.

- Magnetic diagnostics (Labik).

  - Labik will mark up Neil Pomphrey’s drawings of the loops in (u,v) space to define the lead routings.

  - Cole has updated the loop positions on the Martin Brown drawings.  Stud locations have been set.  Goranson is still finalizing the tube spacing.

  - Labik reported that the 2 Rogowski coils would be routed in the bag seal grooves on Type C coils.  Labik reported that the voltage loop design has not been done. The voltage loops go under cooling tubes.  Their installation needs to be incorporated in the FPA-001 procedure.  Tom Brown’s help is needed for routing the voltage loops.

  - George Labik indicates need for Larry Guttadora to prototype junction box tooling to cut sheath of cabling.  Guttadorea to be made available for 2 days this week.

- H/C tube final design (Goranson).

  - Braided hose has been adopted as our baseline.  The braided hose provides acceptable performance if grafoil is used under the clamps.  Clamp spacing and clamp design needs to be finalized.  Cole will integrate the modified clamp design (with appropriate clamp spacing) into the Station 1 assembly drawing.

  - Successful FDR conducted for the hose clamps.  Goranson to resolve chits submitted at the FDR.

  - FDR for the hoses, the routing of the hoses, and the thermohydraulics scheduled for April 4.

- Heater tape design (Goranson)

  - Heater tape ordered for Port 12.  Issues remain about the heater tape design for other ports.

  - ORNL is still planning on testing the heater tape as part of an integrated test (prototype) of the H/C tubes, heater tape, instrumentation (thermocouples), control system, thermal insulation system, and magnetic loops.  The integrated test, which will address whether we can really control the temperature profile adequately, should be completed before we install the heater tape on Port 12.  Upon completion of the integrated test, there will be a follow-up FDR that will be used as the basis for authorizing installation of the heater tape on Port 12 and procurement of the heater tape for the other VVSAs.  However, there was still no progress reported in even planning for this integrated test.

- VVSA-1 technical issues (Viola)

  - Out of tolerance condition.  The shell is seriously out of tolerance (by 0.3”) in several places.  Tom Brown has concluded that this does not present any assembly problems based on the data we currently have.  Art Brooks has concluded that the shell and flange encroach on the plasma, but where the shell encroaches, it is only out of tolerance by 0.1” (which is probably something we can give up on).  MTM was supposed to provide additional data by last Friday, but as of noon on Wednesday, it still had not arrived.  Nelson has established the flange tolerances required to assure that we can fit up the six pieces in final assembly but as of yet, this feedback has not been formally communicated to MTM.  We also have to provide a formal response to the NCRs that have been submitted on the VVSA which might be the best way of providing this feedback  Time is of the essence.  We need to get MTM back to work on the VVSAs or our Joule milestone to complete all three VVSAs by the end of September is at risk.

- Station 1 documentation, plan, and procedure development

  - Manufacturing Facility Operation Plan.  Revision 1 includes field period assembly operations and has been signed.

  - Preliminary Hazard Analysis of the Manufacturing Facility (NCSX-PHA-142-01).  Revision 1 which includes FPA is out for review (Dudek).

  - Station 1 Dimensional Control Plan (Stratton).  Signed.

  - Station 1 Assembly Sequence Plan (Brown).  Successful peer review of assembly sequence conducted 08 December 2005.  It defines the way the Station 1 period assembly was designed to be assembled and is foundational for developing the Station 1 Assembly Procedure.  Brown indicated that a revision would be sent around for review this week.

  - Station 1 Product Specification (Goranson).  This document defines the Station 1 period assembly and its requirements.  It will identify the installation drawings to be used in the assembly work on Station 1.  It will also identify the inspections and tests that should be conducted as part of the work on Station 1 to verify that the requirements have been met. This document is foundational for developing the Station 1 Assembly Procedure.  Guidance on content provided to Goranson on March 7.

  - Installation Drawings (Cole).  The installation drawings are being updated based on revised loop and stud locations.  Viola can use the current drawings for developing complete drafts of the procedures and update the procedures when the drawings are released for fabrication.  The drawings have been sent to Viola.  No feedback has been provided to Cole.  The installation drawings need to be finalized for the Station 1 assembly procedure.

  - Field Period Assembly MIT/QA Plan (Viola).  Draft sent out and comments received.  Sections dealing with work on Station 1 need to be finalized prior to the ACC review for Station 1.  Tom Brown to provide revised Station 1 information on March 7.

  - Station 1 QA Procedure (Viola).  This procedure will include [1] a “gross damage and number count” receipt inspection of the VVSA [2] mounting the VV period assembly in the turning fixture [3] performing a metrology check of the VVSA dimensions and [4] performing receipt inspection of all components to be installed on Station 1 including H/C tubes and manifold assemblies and attaching hardware; heater tapes; cryostat interface flanges; flux loop templates and wire; and miscellaneous hardware.  Viola is planning to have supporting procedures written for the VV period assembly critical lift (Viola) and metrology check (Raftopoulos).  The Station 1 QA Procedure should be finalized at the time of the ACC review for Station 1 (nominally in mid-March after the Station 1 turning fixture is installed and before we receive the first VVSA).  This QA procedure will be based on the VVSA spec. First draft sent out for additional information.

  - Station 1 Assembly Procedure (Edwards).  Edwards is working on the assembly procedure which will follow the QA procedure.  Supporting procedures (if any) should be identified.  For the ACC, a complete draft of the assembly procedure should be available.  This assembly procedure will be based on the product specification and associated drawings for the Station 1 period assembly. First draft out, needs updating based on input from MIT/QA plan meeting

- Station 1 metrology (Raftopoulos).

  - Raftopoulos to determine with Dudek whether factory servicing should be performed prior to being put in service for FPA.

  - Need to purchase screen and projector for test cell (Viola)

  - Raftopoulos to ensure that all of the required hardware and software for metrology activities on Station 1 is operational and personnel have been trained prior to the Station 1 ACC review (before Station 1 activities are scheduled to begin).

Ray Camp has been notified that we would like to conduct an ACC review of the readiness of Station 1 for operation around the third week in March.  He requested a one week notice prior to the review.  The tentative charge is as follows:

- Does Station 1 have adequate safeguards for completing the QA and assembly work planned for Station 1?

- Are the safety controls identified in the Manufacturing Facility Operations Plan adequate and appropriate for the work on Station 1?

- Have these safety controls been properly implemented?  Specifically, is the JHA adequate for the work to be performed?  Has appropriate training been planned and provided for the supervisors and technician staff?

The review will consist of a presentation by the ATI (Viola) on the purpose and design of Station 1 followed by a walk-through of the facility.  Documents which should be provided to the ACC prior to the review should include:

Manufacturing Facility Operations Plan (signed)

Manufacturing Facility Preliminary Hazards Analysis (signed)

Field Period Assembly MIT/QA Plan (signed, but TBDs, e.g. listings of implementing procedures, allowed for non-Station 1 work)

Station 1 QA Procedure and supporting procedures (signed)

Station 1 Assembly Procedure (complete draft available)

Station 1 Period Assembly Product Specification (signed)

Station 1 Installation Drawings (released for fabrication)

Station 1 Job Hazard Analysis (complete)

Training requirements and records for Station 1 personnel documented

Approved work planning form clearly identifying appropriate engineering and safety controls for work on Station1.

Please be sure that these deliverables are prepared in a timely manner.

Distribution: Dudek, Nelson, Goranson, Labik, Brown, Cole, Neilson, Stratton, Zarnstorff, Raftopoulos, Viola, Simmons, Edwards, Williams