May 22, 2006

To: Distribution

From: Wayne Reiersen

Subject: Notes from May 22 telecon

Plans, progress, and issues in Type A/B design and procurements

Drawings to support Type A procurements and assembly activities have all been received.

Type B lower lead block drawings have been released for fabrication.  Upper lead block drawings are in review.

Type B Side A cladding and chill plates were released but need to have a change made.  Side B is due out this week.

Type B prosthetic piece is not yet done but no problems are expected.  The drawing will have minimal dimensions as it will be built basically from the model.

Kudos to Williamson et al for getting ahead of the schedule wave and staying under budget in the process.

Fogarty is designing the attachments for finishing the plumbing.  This work should be completed this week.

Plans, progress, and issues in coil testing

Gettelfinger had no major issues to report.  Forecast finish dates are shown in the table below.  The coil should be ready for testing next week.

ORNL would like to add a displacement monitor which they are designing and bringing up for installation this week.

The Teflon tubing attachment scheme was unsuccessfully tested.  Gettelfinger is going forward with G10 insulting breaks for testing the C1 coil.

ORNL (Nelson) will verify the structural adequacy of the leads prior to testing.

An internal review of the installation and test plan will also be conducted prior to testing.

Plans, progress, and issues in coil-to-coil interface hardware

Work to date limited to modifications in the winding forms converting through holes to tapped holes where necessary.

Design work will begin in earnest once Type B drawings are complete.

Testing of the shear plate concept will be performed ASAP.  ORNL is awaiting receipt of the studs for the test.

Plans, progress, and issues in FPA

Dudek reported that all the parts were received or on order except for the flexible tubes and clamp assemblies.  ORNL indicated that the detailed drawings were complete but that the assembly drawing was still in process.  It was agreed that ORNL would release the detailed drawings so that the parts could be procured.

FPA assembly activities have focused on learning how to use the Leica laser tracker in conjunction with the VeriSurf software.  Raftopoulos, Edwards, and Duco have all been involved.  Dimensional verification is expected to continue for a couple of weeks.  Duco is slated to go to MTM June 14 to learn how they take their measurements.

Plans, progress, and issues in global modeling

Brooks reported that the global modeling effort is proceeding without any showstoppers close to the agreed upon schedule.  The global model captures all of the important modular coil features will minimizing nonlinear effects.

The geometry for the structures, PF, and TF has been modeled and is being debugged.

Fan will integrate those elements with the simplified modular coil model when he returns from vacation the second week in June.

The last step will be to run various load cases.

Cc: Dudek, Chrzanowski, Williamson, Nelson, Brown, Cole, Neilson, Fogarty, Gettelfinger, Strykowsky, Goranson, Labik, Stratton, Zarnstorff, Raftopoulos, Viola, Simmons, Edwards, Williams, Meighan