September 11, 2006

To: Distribution

From: Wayne Reiersen

Subject: Notes from the September 11 stellarator core telecon

A conference call was held with PPPL and ORNL to discuss stellarator core issues related to modular coil fabrication and field period assembly.

Testing C5

  - Reiersen reviewed the cost proposal from MIT for testing and providing a FBG setup for use on the C5 coil.  Sampling rates were raised as an issue at he telecon.  Reiersen to explore de-scoping options and alternative funds.

  - Gettelfinger will investigate the use of existing sensors and signal conditioning equipment here at PPPL to reduce the costs of testing.

  - Freudenberg reported that the FISO gages were ordered and were due this week.  Adhesion will be tested via a 3-point bend test.  Options include UV glue and Stycast.  The second phase will involve performance testing of the gages.

  - Reiersen drafted a position paper on our plans for future testing.  Thanks to all who provided input.  The paper will be provided to DOE once the FBG testing issue is resolved.

  - Reiersen will wrap up the C1 test report with the information in hand.

Finishing the modular coil assembly drawings (Williamson)

  - Williamson reported that work on the modular coil assembly drawings was proceeding.  The initial issue of the completed Type C assembly drawings for review should be this week.  A peer review will conducted shortly after the drawings are issued.  The Type A and B drawings will follow thereafter.

  - Design issues which should be addressed include:

    - TC and strain gage number and location

    - Boxes to protect the co-wound loops

    - Clamp hardware design (profile) issues

    - Coolant loop routing and termination

    - Bat insulation requirements and design.

    - Shear plate connections (may require longer timeframe)

Vacuum vessel thermal insulation.  Goranson reported on the initial results of the “ant farm” test which showed that the aerogel, while it flowed well, had a definite “slump angle” and did not fill all voids.  A summary was provided following the meeting. It was noted that special insulation may be required behind the port collars because of high temperatures associated with welding the port extensions.  Need a plan forward to resolve thermal insulation issues (Goranson).  There was some discussion of the bat insulation to be installed on the modular coils.  There was a sentiment that a modest prototyping activity to refine the concepts for the bat length and attachment scheme might be very useful (Viola). Zarnstorff thought the bat insulation might be overkill and that a simple piece of glass cloth draped over the winding might suffice to suppress convection between the winding and vacuum vessel.

Finish the coil-to-coil interface design.  An information meeting is scheduled for Wednesday September 30 at 2:30pm to review the concepts for coil-to-coil interface design.  The purpose of the meeting is to review the proposed design from an assembly standpoint and to assure that all structural requirements are recognized and are being addressed.  This meeting presents an opportunity for the folks responsible for assembly to provide feedback to the designers at a time when changes can still be readily made.  Mike Cole will structure the agenda.

Finalize design modifications to the VV vertical supports.  Goranson requested the radial locations of the bosses to confirm that the design modifications can indeed accommodate the as-built nonconformances (Viola)

Release drawings for modular coil fabrication.  Williamson reported that all of the Type B terminal assembly drawings and side and top plate drawings are ready for checking.  No schedule issues with procurement of components for fabrication of the remaining coils were identified.

Resolve VV clamp issues.  Edwards and Duco are concerned that the clamps will not hold on an outside radius.  Other clamp issues were raised previously.  Dudek and Goranson to resolve.  Goranson indicated that a single coolant loop on the spacers would alleviate concerns.  Brown noted that interferences with the flux loops on the spacers would have to be addressed.

Station 1 FPA.  It was noted that thermocouple locations are needed to avoid interferences.  Cole to send preliminary set to Brown.  There are reportedly 14-16 TCs per VVSA.

FY07 staffing plans.  These need to be finalized ASAP.  Cole to submit revised plans for ORNL scope.  Reiersen to review along with updated PPPL plans.

Metrology requirements.  In order to work on more than one FPA station at a time, it appears that more metrology equipment might be required.  Raftopoulos indicated that a metrology utilization study would be required to make this determination.  Viola to take the lead in establishing metrology requirements.

The following events are upcoming:

Tuesday	September 5	10am		Next telecon (Monday is Labor Day)

Wednesday	September 6	9:30am		Solenoid Assembly FDR

Wednesday	September 20	9:30am		Station 2 Tooling PDR/FDR

Wednesday	September 20	2:30pm		Coil-to-coil interface design information meeting

Wednesday	October 11	8:00am		Field Period Assembly External Peer Review

Reviewers to be invited include G. Johnson, T. McManamy,

S. Anderson, D. Anderson (HSX) and TBD from W7-X

Knowlton (Auburn) Action: Reiersen

Wednesday	October 18	9:30am		Station 3 Tooling PDR/FDR

The next meeting will be held on September 18 at 9:30am.  PPPL participants will be meeting in the Engineering Conference Room.  Remote participants can dial in on 866.718.9081 passcode 706670.

Please advise if any additions or corrections are in order.

Distribution: Nelson, Cole, Williamson, Goranson, Freudenberg, Dudek, Viola, Chrzanowski, Raftopoulos, Brown, Stratton, Brooks, Neilson, Zarnstorff, Strykowsky, Gettelfinger, Williams, Labik, Simmons, Gernhardt, Heitzenroeder, Sichta, Simmons