September 25, 2006

To: Distribution

From: Wayne Reiersen

Subject: Notes from the September 25 stellarator core telecon

A conference call was held with PPPL and ORNL.  The primary topic of discussion was modular coil clamp issues.  David Williamson provided an excellent summary of clamp issues.  The following issues were discussed.

Bushing height.  The reference dimensions on two drawings were incorrect.  This led to the bushing being the wrong height.  The longer bushing ordered for C1 coil should be used throughout (Dudek).

Top pusher assembly travel.  The top pusher assembly features a spherical washer and seat.  In regions of high torsion, the spherical washer does not have adequate travel.  The flat section of the washer that sits on the pusher pad appears to run into the spherical seat.  A number of solutions were discussed including using the existing clamp swivel (used for the side clamps) and a reduced profile clamp swivel.  The problem with these solutions is that they will protrude at least 0.25” above the top of the clamp yoke.  Dudek will investigate removing the flat section of the washer which is what runs into the spherical seat.  This should also eliminate the need for the additional 1/16” G11 pad which sits atop the embedded pad on some of the Type C coils.

Top pusher assembly retention and locking.  The design intent was to remove the set screw holding the assembly together after it is installed.  The concern is that particularly in regions of high torsion, the spherical washer will come free, followed by the rest of the pusher assembly.  The set screw cannot stay installed in these regions because the hole in the center of the spherical washer must be free to rotate during installation.  It was also noted that there needs to be some positive locking feature to keep the threaded bushing from backing out.  Plugging the hole with roving and epoxy after installation was suggested as a retention feature.  Spot welding all threaded connections was suggested as a locking mechanism.  Dudek and Williamson to resolve.

Clamp envelope.  It was noted that the width of the clamp is wider than the envelope assumed in the assembly simulations by 2 x 0.32.  Brown will repeat the assembly simulations and identify those areas where this 0.32” side excursion and a 0.25” top excursion would be problematic.  In those areas, alternate clamp configurations will be considered.  Possibilities include [1] a new clamp yoke with lower profile sides [2] a clamp yoke w/o sides [3] no clamp at all.

Clamp height.  The technicians have no way to set the height of the clamp yoke with respect to the tee.  Williamson agreed to provide the dimension from the top of the clamp to the top of the tee.  Dudek to investigate easy ways to set the clamp height in accordance with this dimension.

As-built clamp geometry.  The height of the winding packs deviate from nominal, in part due to our efforts to preserve the location of the current centroid.  This variation needs to be included in defining the coil envelope during assembly simulations.  Raftopoulos to review Brooks data an propose appropriate envelope to account for height variability.

Other issues being tracked from previous telecons were not discussed.  I updated the entries below where I had new information.

Coil testing

  - FY07 plans should NOT include coil testing.

  - Freudenberg reported that the FISO gages were ordered and were due this week.  Adhesion will be tested via a 3-point bend test.  Options include UV glue and Stycast.  The second phase will involve performance testing of the gages.

  - Reiersen is finalizing the C1 test report.

Finishing the modular coil assembly drawings (Williamson)

  - A peer review for the coil assemblies on September 27 at 1:30pm (note time change).

  - Design issues which should be addressed include:

    - TC and strain gage number and location

    - Boxes to protect the co-wound loops

    - Clamp hardware design (profile) issues

    - Coolant loop routing and termination

    - Bat insulation requirements and design.

    - Shear plate connections (may require longer timeframe)

Vacuum vessel thermal insulation.  Goranson reported on the initial results of the “ant farm” test which showed that the aerogel, while it flowed well, had a definite “slump angle” and did not fill all voids.  Two options for introducing the aerogel were discussed.  The first option is to pump it in many places using a commercial pump used for pumping powders that pumps mostly solids and little air.  A second option is to snake in tubes in many places and withdraw the tubes as the interspace between the VV and mod coils is filled.  (Goranson to resolve issues related to aerogel filling.)  It was previously noted that special insulation may be required behind the port collars because of high temperatures associated with welding the port extensions.  A modest prototyping activity to refine the concepts for the bat length and attachment scheme should be conducted to facilitate assembly (Viola).  Zarnstorff previously suggested the bat insulation might be overkill and that a simple piece of glass cloth draped over the winding might suffice to suppress convection between the winding and vacuum vessel.

Field period assembly peer review.  We would like to involve folks from HSX and W7-X remotely.  It appears difficult to fit this in one morning, so a consecutive morning agenda is proposed.

October 11

9:00	Reiersen	Introduction

9:10	Brooks		Dimensional control requirements for the mod coils and TF coils

9:30	Cole		Design overview and assembly features

10:30	Brown		FPA assembly sequence, tooling, measurements, and adjustments

NOON			ADJOURN

October 12

9:00	Brown		FPA assembly sequence, tooling, measurements, and adjustments (cont’d)

10:00	Viola		Cost and schedule, staffing, metrology utilization

11:00	Perry		Coordinate collection of comments from reviewers

NOON			ADJOURN

Reiersen to contact participants to see if this arrangement would be suitable.

Finalize design modifications to the VV vertical supports.  Goranson requested the radial locations of the bosses to confirm that the design modifications can indeed accommodate the as-built nonconformances (Brown)

Release drawings for modular coil fabrication.  Williamson reported that corrections were made on the Type B side and top plate drawings and that they are released for fabrication.  Type B base plate drawings to be released soon.

Resolve VV clamp issues.  VV clamp issues were discussed.  Dudek reported that the parts appeared to match the drawings except that the hose diameters appeared small, 0.44” in diameter instead of 0.46-0.48”.  Various modifications were discussed.  Dudek agreed to put a few studs on the PVVS and try them.  The torque on the clamp should be determined during prototyping.  The torque should be adequate to compress the grafoil while retaining some springiness.

Station 1 FPA.  It was noted that thermocouple locations are needed to avoid interferences.  Cole to send preliminary set to Brown.  There are reportedly 14-16 TCs per VVSA.  Simmons to expedite approval of the product specs for the Station1 FPA and magnetic loops mounted on the VV.

FY07 staffing plans.  These need to be finalized ASAP.  These will be reviewed at the status meeting on September 28.

Metrology requirements.  In order to work on more than one FPA station at a time, it appears that more metrology equipment might be required.  Raftopoulos indicated that a metrology utilization study would be required to make this determination.  Viola to take the lead in establishing metrology requirements.  Viola reported that the Verisurf software was down in the FPA area and the modular coil fabrication area this morning.  Metrology system availability should be factored into the assessment of what is required.

The following events are upcoming:

Wednesday	September 27	1:30pm		Coil Assembly Peer Review New time!

Monday		October 2	9:30am		Next telecon

Wednesday	October 11-12	9:00am		Field Period Assembly External Peer Review

Reviewers to be invited include G. Johnson, T. McManamy,

S. Anderson, D. Anderson (HSX) and TBD from W7-X

Knowlton (Auburn)

Wednesday	October 18-19	9:30am		Station 3 Tooling PDR/FDR

The next meeting will be held on October 2 at 9:30am.  PPPL participants will be meeting in the Engineering Conference Room.  Remote participants can dial in on 866.718.9081 passcode 706670.

Please advise if any additions or corrections are in order.

Distribution: Nelson, Cole, Williamson, Goranson, Freudenberg, Dudek, Viola, Chrzanowski, Raftopoulos, Brown, Stratton, Brooks, Neilson, Zarnstorff, Strykowsky, Gettelfinger, Williams, Labik, Simmons, Gernhardt, Heitzenroeder, Sichta, Simmons