Jim Anderson

- The budget within Washington regarding the Omnibus Bill, the budget has zero dollars for ITER, but 10 million for ITER research

- NCSX is was not mention in the budget

- NSTX can get a few million dollars for this year

- The OFES office can’t say if the project a go until further notice

- The critical points are when are we going to have the first four packs done?  This is critical that we meet this commitment and date.

Phil Heitzenroeder

- B1 and C1 interfaces are nearing resolution, the generic problem was with the B & C’s

- The NCR clarifying the fix to modify the

- The welded shims are coming

- Gary is fine tuning the stainless steel

- B & C are the lasts and are in good shape

- The C to C FDR is scheduled for the end of January

- Gary and Mike Cole are having a brief meeting to discuss the C to C shim design before they leave today.

Mike Viola

- ACC review was held Tuesday and was well received, confirmed by Ray Camp

- The assembly schedule was on track, but the MCHP B1 and C1 interference are losing time.  We lost a month of assembly time.  This needs to be solved immediately

- I am re-working  the schedule and will be completed today

- In order to get back on schedule will need overtime and shift work and maybe additional technicians

- We need stored calculations for the lift fixtures

Tom Brown

- The meeting for the trim coils was held on Tuesday Dec 18th.

- The PF support missed the port extension, the PF structure should be adjusted

- The leads need to be put on earlier otherwise they will be buried, it should take a couple of weeks to fix this problem

Hutch Neilson

- We need a plan on how to fix these designs problems.

Mike Kalish

- The PF PDR was held on last Friday, the resolution of the chits is in progress

- The Trim Coil meeting was to focus on a basic plan

- Mike Zarnstorff is working with Art Brooks with on the analysis

Jim Chrzanowski

- The Modular Coil in the process of installing the chill plates

- The B 5 and C6 coils are ready to be autoclaved

- In January I will release two technicians to help out Mike Viola’s team

- A blue slip will be processed into the system for one or two additional designers

- The winding data for C6 is completed

- C 6 impregnation will be the first week of February

Bob Simmons

- The comments for the Field Period Assembly procedure are still needed

Ron Strykowsky

- It was very productive visit with the ORNL boy Mike Cole and Gary McGinnis regarding the modular coil and shims

- Reminder that the bottoms up estimate is due by Friday December 21st, which is needed for the OECM review

- Heads up status meeting will be held January 4th

- The high visibility issues are the Modular Coil Set and the laboratory safety record and the upcoming crane lifts, DOE will be looking closely to the lifting procedures.

- Also the last thing that’s high visibility to DOE is the milestones

Raki Ramakrishnan

- The WBS 4 need additional fund to go forward

- Ron Strykowsky needs scope for the design review

- Where the power going to be delivered for the penetrations?

Tom Meighan

- My visit to Everson they high potted the TF 6 and shipping out TF 5 with TF 6

- The TF 7 is out of the mold and TF 8 is off the welding table and waiting for the wedge, also getting ready to wind TF 9

Judy Malsbury

- The field work audit project review will be held in mid-January

Gary McGinnis

- Gary is from Alexander Associates working as a subcontractor for ORNL on NCSX.

- B & C drawings will be out the first of next week

Mike Cole

- Raki need to know where to bring the power out of the Neutral beam lines

- The comments from Mike Zarnstorff are being reviewed

- The C to C design review will be held January 30th

- Paul Goranson is responsible to the lead and cryostat system

- Still need a hand shake on the thermal couples as where they exit the cryostat system

Larry Dudek

- The welding equipment arrived and on January 3rd the regional representative will work with the PPPL welders

- The shims first 100 batch is out for flame spraying

- The Station 3 fixture will be shipped Thursday, December 20th and due to arrive next week

- Frank Malinowski (QA) found a problem with the certifications for the washers for the super nut

- Steve Jurczynski is testing the oven cycle for the hardening and that should be on the drawings

- The requisition for the new machinist to help Mike is in the system

Jerry Levine

- The safety record is just as important as meeting the milestones

- Please be safe and do a job hazard analysis and use proper PPE

Mike Zarnstorff

- Trying to finish the physic analysis for the trim coils

Art Brooks

- The realignment of 16 and 18 as built

Steve Raftopoulos

- The requisition for the two new Romer arms is the system and we will swap out the old Romer arms for the two new ones

Jeff Makiel

- This year has been difficult for PPPL and ORNL, DOE measures project by money and finally the external people are learning how difficult NCSX is to build.

- The ITER project should be a research project, but it’s not!

- The NCSX project is 63% completed, we need to get the baseline and get it on the books.