## task list
Task | Who | when | comment
puck model | PJ | 2007-05-11
epoxy test at LN2 | KF | 2007-05-11 | if we have LN2, use pin test assy
lay out pucks on flanges | MJC |  | use KF as start
FEA model of pucks | KF |  | parametric: depth of cbore, dia, edge dist., epoxy stiffness, eccentricity, consider 1/2 model
lay out compression limiting shims | GM, MJC |  | all the same, act to support seal?, relief for epoxy fill tube(s)
run global bolt FEA case with mod coils only | LM
update global model with final design | LM
lead/crossover analysis | LM
shear testing | KF/RB
bore cbores in plexiglass | JC, JH | 2007-05-13 | put counterbores in existing plexiglass mockups
order sst round and plexiglass round | RB | done
get seal type 1
Decisions
steel or G10 bushing matl?
shear sleeve bushings inboard?
epoxy fill material
seal concept for puck
puck geometry

## matrix
OPTIONS
[11 empty] | 1.4726 | 20027.6532
| pin cushion | riveted waffle plate | Welded shim (to flange) | Welded shim-2 (to shim) | Bonded shim (pins into flng) | inflatable puck in counterbore | superbolt -adjustable wedge | shear thru-pin | serpentine tube | drilled holes in edge | 4-jaw chuck | putty puck | Friction Puck
Requirements
Loading
•Up to ~15 ksi compression | good - goes through flat shim, must be shimmed for thick | compression taken out on wedged features | yes | yes |  | yes, includes separate compression limiter shim |  |  |  | ok, but must be shimmed for thickness
•Up to ~ 4000 lbs per running inch shear | fair - goes through epoxy to pins | shear taken out on wedged features | ok from P/A, but may have slight "setting", high initial peak stresses | ok from P/A, but may have slight "setting", high initial peak stresses, hard to make tight shear connection |  | yes |  |  |  | requires cross pins for shear in any direction
•Shear stiffness of connection (must be adequate to avoid overloading of bolts- no slippage either) | ~ 100,000 psi effective shear modulus from test at twice load | potentially high | should be high | should be high |  | TBD, depends on load sharing |  |  |  | should be high
•Does not distort winding forms | ok | does not distort | may cause local distortion of flange | not expected |  | no |  |  |  | does not distort
•Does not connect winding forms electrically | ok, but needs bushing on each pin | requires electrical insulation on one of the loading faces | needs insulated pins, and insulation between shims, weld spatter could short out | weld spatter could short out |  | requires insulation between pucks |  |  |  | smearing of alumina during drilling could be an issue
•Does not exceed permeability limits | welds may exceed, pins ok? | rivets only potential issue | welds may be high | welds may be high |  | should not, no processing after manufacture |  |  |  | should be ok except for stud welding
flange to flange alignment requirement | max of .125 pin to hole | must be capable of returning coils to original fitup position, rivets must not interfere with mating part | very tolerant | relatively tolerant |  | arbitrary, probably 0.125 |  |  |  | accomodates large misalignment
•Can be installed reliably | no obvious way to check epoxy fill | inspection done with parts disassembled, gap can be measured to check fitup | yes, assuming welds are ok | yes, assuming welds are ok |  | requires testing, but no leaks means it works? |  |  |  | yes if you can drill deep 1/4-5/16 inch holes
Works on C-C connection |  | yes | no | no |  | yes |  |  |  | no, unless pins are trapped in one side?
•Retains function over life of machine w/o maintenance | no obvious issue other than epoxy failure? | yes | yes, assuming welds are ok | yes, assuming welds are ok |  | yes, but need fatique test |  |  |  | yes unless flange gap opens up and scrubbing starts
tolerant of loss of preload on inboard studs | moderately tolerant - no shear gap opens | yes, but joint surface insulation could fatigue due to repeated separations | yes | yes |  | yes |  |  |  | yes unless flange gap opens up and scrubbing starts
Ease of disassembly | bad, must re-do connection, probably does not damage casting | easy | must re-do all hardware after disassembly | must grind weld off, must re-do all hardware after disassembly |  | yes, but probably need all new hardware |  |  |  | good
•Finite cost and schedule
design cost | low | moderate | low | medium |  | moderate requires analysis |  |  |  | low
R&D cost | partially done, but potentially high to get reliability | moderate | depends on weld development | depends on weld development |  | need to develop standard puck, seal, fill tube, fatigue testing, fill testing |  |  |  | moderate? need to drill in place
machining of winding forms | none | drilling at assembly | no | no |  | yes, precision counterboring |  |  |  | none
machining of connection components | medium | components must fit very precisely together | match reamed plates | complicated insulation, shear bushings |  | yes, standard pucks |  |  |  | simple except for field drilling
welding | stud welding only, but cleanup may be expensive | none | field welding | stud welding and field welding |  | no |  |  |  | studs
riveting | n/a | many- need equivalent of 5% of flange area in shear e.g. 2 x 3/16 in dia rivets per square inch | no | no |  | no |  |  |  | none
epoxy injection | difficult | none | no | no |  | yes |  |  |  | none
inspection | stud welds "tap check", no way to inspect epoxy fill | pre-inspection of matched parts and gap measurement at fitup (except CC) | requires weld inspection | requires weld inspection |  | leak check? Can't check fill |  |  |  | possible
assembly cost |  | requires fitup and disassembly |  |  |  | epoxy fill |  |  |  | TBD, depends on deep drilling
Areas needing additional development | epoxy fill process |  | welding | welding |  | puck, seals
| epoxy fill inspection | geometry of components | pin insulation scheme | pin insulation scheme |  | filling of epoxy |  |  |  | accomodation of gaps that may open up
|  | drilling / fixtures |  |  |  | aspect ration of rings - start with acme thread form |  |  |  | deep drilling
|  | rivet choice |  |  |  | effect of cooldown
electrical coating choice
prototype manufacture, fitup and assembly
shear test at temperature
major advantages | ease of fit |  | simple | reduced/no distortion of shell flanges |  | relatively quick assembly |  |  |  | no epoxy, provides compression and shear
| stud welding is simplest shear connection | no epoxy |  |  |  | can be disassembled
|  | no welding |  |  |  | no shimming of puck needed
|  | no distortion of flanges |  |  |  | self aligning, both lateral and angular
prefit of parts possible
Major disadvantages | epoxy |  | does not work on CC | does not work on CC |  | seal development cost, winding form machining cost |  |  |  | accomodation of gaps that may open up
| epoxy | how to get the parts shimmed out between flanges within .001 or so | weld may be over-stressed | weld may be over-stressed |  | potential epoxy fatigue |  |  |  | electrical insulation may be an issue?
| clean up of stud |  | distortion of shell flanges | can't take apart |  | epoxy shrinkage could be an issue
| getting studs straight |  | can't take apart
may require pre-fit for thickness flanges
assume round pucks with tapered concentric rings
can be attached via rivets, stud welding, or counterbores

## Sheet2
| pin in plate, no bonding of epoxy | pin in plate, with bonding of epoxy | inflatable puck w/o shear bond | inflatable puck with shear bond
load | 16000 | 16000 | 18000 | 18000 | lbs
od | 2 | 2 | 2.5 | 2.5 | in
thickness | 0.25 | 0.25 | 0.25 | 0.25 | in
bearing area | 0.5 | 0.5 | 0.625 | 0.625 | in^2
bearing stress to winding form | 32000 | 32000 | 28800 | 28800 | psi
bearing area of epoxy | 0.5 | 0.5 | 1.375 | 1.375 | in^2 | assumes 1.75 and 1 inch rings
psi
bearing stress within puck |  |  | 13090.9091 | 13090.9091
shear area of epoxy | 10 | 10 | 2.4053 | 2.4053 | in^2
shear stress, if bonded | 0 | 1600 | 0 | 7483.5304
shear modulus of epoxy | 1 | 330000 | 1 | 330000 | psi | assumed
avg bond thickness | 0.025 | 0.025 | 0.125 | 0.125
shear stiffness, AG/t | 400 | 132000000 | 19.2423 | 6349944.1511 | lbs/in
epoxy compression modulus | 1100000 | 1100000 | 1100000 | 1100000 | psi | stycast at 77K
gap width, avg | 0.075 | 0.075 | 0.075 | 0.075
AE/L | 7333333.3333 | 7333333.3333 | 20166666.6667 | 20166666.6667 | lbs/in
total lateral stiffness | 7333733.3333 | 139333333.3333 | 20166685.9089 | 26516610.8177 | lbs/in
paths in series | 2 | 2 | 1 | 1
total stiffness | 3666866.6667 | 69666666.6667 | 20166685.9089 | 26516610.8177 | lbs/in
compressive stress in epoxy
shear stress in epoxy

## Sheet3
2.5 inch dia
| aa | 12 | 3 | 36
| ab | 14 | 6 | 84
| bc | 10 | 6 | 60
| cc | 14 | 3 | 42
|  | 50 |  | 222
| unique cases | 37
Lepoxy | 0.05
Lsst | 0.45
L total | 0.5
E epoxy | 100000 | psi
E sst | 28000000 | psi
E equiv | 968858.1315 | psi