Phil Heitzenroeder

- Constructability review will be on October 29, 2007

- Lining up reviewers for this review

- Weld Interface PDR will be October 18, 2007

- Two reviewers; one from J Lab and one from Brookhaven

- Question needs to be answered about engineering technical requirements, how stellarator error, factor cool down deflection, assembly to meet all of the goals

- Next month is critical!

Mike Viola

- During weld test we learned that distortion is consistent, shim wants to lift off

- Solution to shims lifting is to put in small tacks when assembling the machine, and to stagger welds

- Field Period pre-measurements coming along, all coil are racked

Jim Chrzanowski

- Making progress, mounted B-6

- October 13 the coils to have thermocouples

- Strain gauges only needed for 3rd Field Period

Red Delany

- Working on weld tests, C1-coil just started today and C-2 down at the shop

Mike Kalish

- TF-4 coil is crated and sealed

- TF-3 coil has dry spots, and was tested electrically

- Will ship TF 3 and 4 coils for December’s milestone

- TF-3 coil sealed with D40, painted on one side

- Working on Trim Coil estimate with Tom Brown and Art Brooks for upcoming review

Tom Brown

- Trimming of the seal plates to be done today

Steve Raftopoulos

- Mark Smith was put in charge of measuring the TF coils

- Going to Cern next week with Mike Viola and Bill Sands

Ron Strykowsky

- Status meeting today at 10:00 AM

- Need Trim Coil estimates for meeting next week

Paul Henderson

- Metrology computer now has network folders

- A Pentium 4 computer with a wireless card was installed, no updates were done

Mike Cole

- Comments for Station 3 drawing are due in two weeks

- Station 2, received Tom Brown comments and still need Mike Viola’s comments

- Trim coil estimate meeting with Mike Kalish today at 2:00 PM

- Bolt stud lengths working with limited data with Larry Dudek’s help

- Error with strain gauge lengths, due to a glitch in Pro-E, Tom Brown found error

Bob Simmons

- Metrology web is now posted on the NCSX website

- Weld distortion will be posted, waiting for Mike Viola input

- C-Spec needed from Phil and still needs ECP

Larry Dudek

- Erik Perry can’t find 316 LN for testing on inboard shims

- Shims first batch due October 23rd

- We still need a vendor for alumina shims, deadline November 23rd

- Cost of sheets are approximately 20,000 a sheet, 5/8 could be used instead

Jeff Makiel

- NCSX is still on probation, three things need to be answered; rebaselining, work scope needed for physics necessity, and can this machine be built?

- Constructability review will be on October 29, and answered by early Nov.

- Rebaselining and milestones are crucial, we are still under the microscope

Hutch Neilson

- We have to submit a year end report to DOE, draft in progress, input needed

- Trim coils are a priority