NCSX Project Plan

Current Project Approach

- Drive critical path schedule

- Maximize schedule float of highest risk activities

- Assess risks, and estimate required contingency

- Propose re-baseline now with 32% design to go

- Accept highest risks (Station 5 & 6 assembly)

Proposed New Approach

- Drive schedule that aggressively completes all core stellarator preliminary design reviews (PDRs) by Aug 2008

- Drive schedule that reduces assembly risks to improve ETC confidence

- Engage external experts to speed up design (as reviewers, consultants, and/or subcontractors)

- Demonstrate substantial measurable progress by Aug 2008

  - Submit BCP 8/30/08 consisting of current version, with new bottoms-up estimates for only work that has been changed as per items 1-3

Submit a Plan to DOE by 4/28/08 and to include a resource loaded schedule with identified resources that will:

- Optimize staffing resources (qualified & available people)

- Complete cryosystem PDRs by Aug 2008

- Complete coil services PDRs by Aug 2008

- Complete NB ducts PDR by Aug 2008

- Complete Station 5 & 6 tooling design PDRs by July 2008

- Consider trade-offs from accelerating low-risk ancillary system designs

- Complete the first modular coil half period (MCHP) assembly by Nov(?) 2008

- Demonstrate fit-up of MCHP over vacuum vessel system assembly by ??

- Include weekly calls between project with R. Fonck & D. Lehman (similar to what is done on BES projects) to report progress, resolve issues, agree upon expectations.