Background:  This is a report of the Project Meeting held Wednesday, April 30th.   The meeting was moved to Wednesday to permit all Job Managers to attend.

The focus of this meeting is to primarily look at the next three weeks and the actions needed to ensure that the scheduled items will be met. The RLMs conduct this meeting using the three month look-ahead schedule that is sent out prior to the meeting.  These minutes include:

- Summary of actions identified during the meeting;

- Safety minute briefing;

- Three week look ahead schedule; and

- Action items from previous and the current meeting

NOTE: Future meetings will be held on Wednesdays at 1:00 pm.

Meeting Minutes:

Safety Briefing – Mike Kalish spoke on “doing the right thing” when it relates to safety. Major messages:

- Be assertive when safety is involved – don’t be hesitant to stop work if you see a potential or real safety hazard

- Ensure that folks do the work right with proper regard for safety – no shortcuts!

Heitzenroeder (RLM)

  - Tom Brown (Jobs 8203/8205 Design Integration) – designer issues resolved.

    - Jim Chrzanowski – Mike Kalish reporting -  Jobs 1302/1352) – PF coil procurement ready to be awarded – hopefully next week after DOE review.

    - Mike Cole (Jobs 1353/1416/1421/1806/12xx?).

  - Job 1416-NEW – new work: thermal analysis of MC & LN2 colling. Related question – how do VV Title III jobs and unscheduled work get added and charged? => add to WAF, albeit with no budget and will accept variances.  Action: work out plan to collect charges for unplanned work that comes up and propose mechanism for collecting charges for such work to Project (Harris)

  - ORNL will assume responsibility for PF1a work. Cole will be job manager – updated schedules (Strykowsky)

  - Station. 3: Forecast models & drawings approved by May 6th – comments due and received by April 29th  - expect to issue for approval today or tomorrow to meet May 6th date =>should not impact Station 3 work.: (Harris/Cole)

  - Station 5 specs and drawings. Need to clarify when CSPEC and drawings actually needed (likely August vs. April time frame.  Ensure assembly specs put back into schedule (Strykowsky)

  - Increase granularity of schedules in Jobs 1355, WBS 16 jobs. Increased granularity provided for Jobs 1806 & 1901. (Cole)

  - WBS 16 jobs interfaces need to be defined –Stay on current course with LN2 manifolds design concept, including two-phase capability.  Expect PDR on June 3rd. Need to resolve Electrical leads routing with Tom Brown (Brwon/Cole/Goranson)

- Fred Dahlgren (Jobs 1353/1501/1702)

  - FDR for Coil Support Structure delayed until May 6th to update drawings and some analyses. (Dahlgren)

  - SRDs for both Base Support Structure and Coil Support Structure revised by Fred on April 23rd –now out for signature. Simmons to follow up on where these stand (Simmons)

- Bob Ellis (Job 8205) - Station. 3  Dimensional Control Plan draft to be issued tomorrow on Friday, May 2nd.  Has potential to impact Station 3 work, especially acceleration to mitigate risks.  Ellis

- Mike Kalish (Jobs 1361 & 1354):

  - No issues on TF coil schedules – previous concerns about delivery of wedges appears to now be resolved.

  - Trim coils.  On schedule for May 6th FDR. Jim Sims (LANL) has agreed to participate. Procurement award now forecast for June 27th – looking a feasibility of accelerating this procurement (Neilson/Kalish)

Larry Dudek (RLM)

- Tom Brown (Job 1803/05)

  - Station 2:  Wedges to ship May 3rd

  - Station 3 clearance studies moved to late May.

  - Station 5 6 tooling will be delayed until FY2009, but other Station 5 work will proceed to support assembly operations and planning.  New envelop study needed to follow up on the port alignment issues.  ORNL?  Cole and Brown resolve who will do this.

  - Diagnostic and thermocouple lead boxes on Type A coils have to be moved  - now planned for Station 5.

    - Mike Viola Jobs 1810/1815) .

        - Taking time for additional weld development and A2B2 shear plate design.  Impacts A1B1 and A2B2.  A1B1 and shear plate design on hold pending follow up on welding engineer advice.  Viola

        - Heating and cooling hoses.  We are replacing the damaged/leading hoses. However, reliability issue still a concern.  FMECA signed off. NCR to be prepared to document resolution of leaking hoses and larger reliability issues.

- Brent Stratton (Job 3101) – installation of Rogowski loops scheduled to be completed by end of May.  Need to develop work plan to complete checking of thermocouple leads and heater leads by end of May to support assembly operations.  (Stratton)

- Goranson (Job 1260) – need to define path forward for enclosing pyrogel in nomex bats.  Harris follow up with Benson to define what needs to be done (R&D & procedures.