## NCSX Shutdown Case Total
NCSX Cancellation Close-out & R&D Plan
| FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13
NCSX MIE Close-out (FY09=FY08 carryover) |  | #REF! | #REF!
PPPL |  | #REF! | #REF!
LANL |  | #REF! | #REF!
ORNL |  | #REF! | #REF!
PPPL Staffing Profile (FTE) (DIRECT)
RM (Expt) |  | 0.82 | 0.22
RM (Theorists)
RM (CPPG)
Engineers (Computer) |  | 0.19 | 0.01
Engineers (Mech) |  | 8.51 | 1.27
Engineers (Electrical) |  | 0.17 | 0.06
Engineers (FOM) |  | 6.96 | 0.64
Techs & SLS |  | 25 | 1.43
Designers |  | 3.53 | 0.75
Other |  | 3.23 | 0.61
PPPL Staffing Profile Total |  | 48.41 | 4.99
NCSX SEVERANCE (PPPL) |  |  | 1.75
NCSX Risk Reduction |  |  | #REF! | #REF! | #REF!
PPPL |  |  | #REF! | #REF! | #REF!
ORNL |  |  | #REF! | #REF! | #REF!
PPPL Staffing Profile (FTE) (DIRECT)
RM (Expt) |  |  | #REF! | #REF! | #REF!
RM (Theorists)
RM (CPPG)
Engineers (Computer)
Engineers (Mech) |  |  | #REF! | #REF! | #REF!
Engineers (Electrical) |  |  | #REF! | #REF! | #REF!
Engineers (FOM) |  |  | #REF! | #REF! | #REF!
Techs & SLS |  |  | #REF! | #REF! | #REF!
Designers |  |  | #REF! | #REF! | #REF!
Other |  |  | #REF! | #REF! | #REF!
PPPL Staffing Profile Total |  | 0 | #REF! | #REF! | #REF!
Post-NCSX R&D |  |  | 0.5 | 0.5 | 0.75
PPPL |  |  | 0.375 | 0.375 | 0.58
ORNL |  |  | 0.125 | 0.125 | 0.17
PPPL Staffing Profile (FTE) (DIRECT)
RM (Expt) |  |  | 0.4085 | 0.4085 | 0.63181
RM (Theorists)
RM (CPPG)
Engineers (Computer)
Engineers (Mech) |  |  | 0.75795 | 0.75795 | 1.1723
Engineers (Electrical)
Engineers (FOM)
Techs & SLS
Designers
Other
PPPL Staffing Profile Total |  | 0 | 1.1665 | 1.1665 | 1.8041
Research Prep
PPPL |  | 0.387
ORNL |  | 0.22
PPPL Staffing Profile (FTE) (DIRECT)
RM (Expt) |  | 1.056
RM (Theorists)
RM (CPPG)
Engineers (Computer)
Engineers (Mech) |  | 0.01
Engineers (Electrical) |  | 0.06
Engineers (FOM)
Techs & SLS
Designers
Other |  | 0.01
PPPL Staffing Profile Total |  | 1.136
| FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13
TOTAL NCSX Cancellation Plan(As-spent $M) |  | #REF! | #REF! | #REF! | #REF!
NCSX Shutdown - PPPL |  | #REF! | #REF! | #REF! | #REF!
NCSX Shutdown - LANL |  | #REF! | #REF! | 0 | 0
NCSX Shutdown - ORNL |  | #REF! | #REF! | #REF! | #REF!
PPPL Staffing Profile (FTE) (DIRECT)
RM (Expt) |  | 1.876 | #REF! | #REF! | #REF!
RM (Theorists) |  | 0 | 0 | 0 | 0
RM (CPPG) |  | 0 | 0 | 0 | 0
Engineers (Computer) |  | 0.19 | 0.01 | 0 | 0
Engineers (Mech) |  | 8.51 | #REF! | #REF! | #REF!
Engineers (Electrical) |  | 0.23 | #REF! | #REF! | #REF!
Engineers (FOM) |  | 6.96 | #REF! | #REF! | #REF!
Techs & SLS |  | 25 | #REF! | #REF! | #REF!
Designers |  | 3.53 | #REF! | #REF! | #REF!
Other |  | 3.24 | #REF! | #REF! | #REF!
PPPL Staffing Profile Total |  | 49.536 | #REF! | #REF! | #REF!
NCSX Program FWP |  |  | FY09 | FY10
TOTAL (As-spent $M) |  |  | 20.2 | 20.7
NCSX Shutdown - PPPL |  |  | 18.8 | 18.5
NCSX Shutdown - LANL |  |  | 0 | 0
NCSX Shutdown - ORNL |  |  | 1.4 | 2.2
PPPL Staffing Profile (FTE) (DIRECT)
RM (Expt) |  |  | 2.2 | 2.5
RM (Theorists) |  |  | 0 | 0
RM (CPPG) |  |  | 0 | 0
Engineers (Computer) |  |  | 0.7 | 2.7
Engineers (Mech) |  |  | 6.6 | 4.9
Engineers (Electrical) |  |  | 2 | 1.9
Engineers (FOM) |  |  | 7.4 | 5.3
Techs & SLS |  |  | 37.3 | 41.6
Designers |  |  | 3.6 | 2.7
Other |  |  | 4.4 | 5.4
PPPL Staffing Profile Total |  |  | 64.2 | 67
NSTX Program FWP |  | FY08 | FY09 | FY10
TOTAL (As-spent $M) |  | 32.9 | 29.7 | 30.3
PPPL Staffing Profile (FTE) (DIRECT)
RM (Expt) |  | 23.776 | 24.081 | 24.081
RM (Theorists) |  | 0 | 0 | 0
RM (CPPG) |  | 1.8 | 1.8 | 1.8
Engineers (Computer) |  | 5.8 | 5.9 | 5.9
Engineers (Mech) |  | 2.05 | 1.25 | 0.91
Engineers (Electrical) |  | 11.587 | 10.145 | 9.985
Engineers (FOM) |  | 5.206 | 3.9275 | 3.9275
Techs & SLS |  | 45.699 | 41.573 | 41.213
Designers |  | 3.575 | 1.7875 | 1.7475
Other |  | 7.25 | 7.25 | 7
PPPL Staffing Profile Total |  | 106.743 | 97.714 | 96.564
NCSX/NSTX Staffing impacts
|  | FY08 | FY09 | FY10
$M BA
| NSTX & NCSX FWP (PPPL) | #REF! | 48.5 | 48.8
| NSTX & NCSX Cancellation (PPPL) | #REF! | #REF! | #REF!
| TOTAL STAFF |  | FTE
| NSTX & NCSX FWP (PPPL) | 156.279 | 161.914 | 163.564
| NSTX & NCSX Cancellation (PPPL) | 156.279 | #REF! | #REF!
| Research |  | FTE
| NSTX & NCSX FWP (PPPL) | 27.452 | 28.081 | 28.381
| NSTX & NCSX Cancellation (PPPL) | 27.452 | #REF! | #REF!
| Engineers (Computer) |  | FTE
| NSTX & NCSX FWP (PPPL) | 5.99 | 6.6 | 8.6
| NSTX & NCSX Cancellation (PPPL) | 5.99 | 5.91 | 5.9
| Engineers (Mech) |  | FTE
| NSTX & NCSX FWP (PPPL) | 10.56 | 7.85 | 5.81
| NSTX & NCSX Cancellation (PPPL) | 10.56 | #REF! | #REF!
| Engineers (Electrical) |  | FTE
| NSTX & NCSX FWP (PPPL) | 11.817 | 12.145 | 11.885
| NSTX & NCSX Cancellation (PPPL) | 11.817 | #REF! | #REF!
| Engineers (FOM) |  | FTE
| NSTX & NCSX FWP (PPPL) | 12.166 | 11.3275 | 9.2275
| NSTX & NCSX Cancellation (PPPL) | 12.166 | #REF! | #REF!
| Techs & SLS |  | FTE
| NSTX & NCSX FWP (PPPL) | 70.699 | 78.873 | 82.813
| NSTX & NCSX Cancellation (PPPL) | 70.699 | #REF! | #REF!
| Designers |  | FTE
| NSTX & NCSX FWP (PPPL) | 7.105 | 5.3875 | 4.4475
| NSTX & NCSX Cancellation (PPPL) | 7.105 | #REF! | #REF!
| Other |  | FTE
| NSTX & NCSX FWP (PPPL) | 10.49 | 11.65 | 12.4
| NSTX & NCSX Cancellation (PPPL) | 10.49 | #REF! | #REF!
|  | 156.279 | 161.914 | 163.564
|  | 156.279 | #REF! | #REF!

## NCSX MIE Closeout
NCSX MIE Close-out
| 2008 cost through June 1st | 2008 ETC (June 1st to Sept 30) | 2008 Total | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
Budget ($k as spent) | 10232.046 | #REF! | #REF! | 2009: #REF!
PPPL | 8873.102 | #REF! | #REF! | 2009: #REF!
ORNL | 1191.944 | #REF! | #REF! | 2009: #REF!
LANL | 167 | #REF! | #REF! | 2009: #REF!
PPPL Resources FTE's ! (incl 20% cont)
Researchers | 0.54 | 0.28 | 0.82 | 2009: 0.22
Engineers (Computer) | 0.16 | 0.03 | 0.19 | 2009: 0.01
Engineers (Mech) | 5.85 | 2.66 | 8.51 | 2009: 1.27
Engineers (Elect) | 0.13 | 0.04 | 0.17 | 2009: 0.06
Engineers (FO&M) | 4.56 | 2.4 | 6.96 | 2009: 0.64
Technicians & SLS | 16.21 | 8.79 | 25 | 2009: 1.43
Designers | 2.14 | 1.39 | 3.53 | 2009: 0.75
Other | 2.47 | 0.76 | 3.23 | 2009: 0.61
total PPPL | 32.06 | 16.35 | 48.41 | 2009: 4.99
M&S, Travel, Allocations & Other (unloaded) | 1776 | 840 | 2616 | 2009: 96
ORNL Resources (incl 20% cont)
Researchers |  | 0.22 |  | 2009: 0.08
Engineers/Designers/other |  | 1.48 |  | 2009: 0.06
total ornl |  | 1.7 |  | 2009: 0.14
M&$, Travel, & Other |  | #REF! |  | 2009: #REF!
23.18

## NCSX Risk Reduction
NCSX Risk Reduction
| 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
Budget ($k as spent) |  | #REF! | #REF! | #REF!
PPPL |  | #REF! | #REF! | #REF!
ORNL |  | #REF! | #REF! | #REF!
PPPL Resources
Researchers |  | #REF! | #REF! | #REF!
Engineers (Computer)
Engineers (Mech) |  | #REF! | #REF! | #REF!
Engineers (Elect) |  | #REF! | #REF! | #REF!
Engineers (FO&M) |  | #REF! | #REF! | #REF!
Technicians & SLS |  | #REF! | #REF! | #REF!
Designers |  | #REF! | #REF! | #REF!
Other |  | #REF! | #REF! | #REF!
total PPPL |  | #REF! | #REF! | #REF!
M&S, Travel, & Other (unloaded) |  | #REF! | #REF! | #REF!
ORNL Resources
Researchers
Engineers |  | #REF! | #REF! | #REF!
M&$, Travel, & Other |  | #REF! | #REF! | #REF!

## Post NCSX R&D
Post-NCSX R&D
| 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
Budget ($k as spent) |  | 500 | 500 | 750
PPPL |  | 375 | 375 | 580
ORNL |  | 125 | 125 | 170
PPPL Resources
Researchers |  | 0.4085 | 0.4085 | 0.63181
Engineers (Computer)
Engineers (Mech) |  | 0.75795 | 0.75795 | 1.1723
Engineers (Elect)
Engineers (FO&M)
Technicians & SLS
Other
M&S, Travel, & Other (unloaded) |  | 20 | 20 | 20
ORNL Resources
Researchers |  | 0.2 | 0.2 | 0.3
Engineers |  | 0.2 | 0.2 | 0.3
M&$, Travel, & Other |  | 2 | 2 | 2

## NCSX As Planned Case Total
| FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 |  | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18
|  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
NCSX Facility Ops-PPPL (FY 09 M$) |  |  |  | 2 | 3 | 4 | 22 | 22 | 22 | 22 | 22 | 22 | NCSX Facility Ops-PPPL (FY 09 M$) |  |  |  | 2 | 3 | 4 | 22 | 22 | 22 | 22 | 22 | 22
Staffing Profile (FTE) (DIRECT) | [12 empty] | Staffing Profile (FTE) (DIRECT)
RM (Expt) |  |  |  | 0.2 | 0.3 | 0.25 | 0.97826 | 0.97826 | 0.97826 | 0.97826 | 0.97826 | 0.97826 | RM (Expt) |  |  |  | 0.2 | 0.3 | 0.25 | 0.97826 | 0.97826 | 0.97826 | 0.97826 | 0.97826 | 0.97826
RM (Theorists) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RM (Theorists)
RM (CPPG) |  |  |  | 0 | 0 | 0.2 | 2.1739 | 2.1739 | 2.1739 | 2.1739 | 2.1739 | 2.1739 | RM (CPPG) | [5 empty] | 0.2 | 2.1739 | 2.1739 | 2.1739 | 2.1739 | 2.1739 | 2.1739
Engineers (Computer) |  |  |  | 0.3 | 1 | 1 | 5.7826 | 5.7826 | 5.7826 | 5.7826 | 5.7826 | 5.7826 | Engineers (Computer) |  |  |  | 0.3 | 1 | 1 | 5.7826 | 5.7826 | 5.7826 | 5.7826 | 5.7826 | 5.7826
Engineers (Mech) |  |  |  | 0 | 0 | 0 | 1.0109 | 1.0109 | 1.0109 | 1.0109 | 1.0109 | 1.0109 | Engineers (Mech) | [6 empty] | 1.0109 | 1.0109 | 1.0109 | 1.0109 | 1.0109 | 1.0109
Engineers (Electrical) |  |  |  | 1.5 | 2.25 | 3 | 11.2174 | 11.2174 | 11.2174 | 11.2174 | 11.2174 | 11.2174 | Engineers (Electrical) |  |  |  | 1.5 | 2.25 | 3 | 11.2174 | 11.2174 | 11.2174 | 11.2174 | 11.2174 | 11.2174
Engineers (FOM) |  |  |  | 0.5 | 0.75 | 1 | 5.4565 | 5.4565 | 5.4565 | 5.4565 | 5.4565 | 5.4565 | Engineers (FOM) |  |  |  | 0.5 | 0.75 | 1 | 5.4565 | 5.4565 | 5.4565 | 5.4565 | 5.4565 | 5.4565
Techs & SLS |  |  |  | 3 | 5.5 | 6.5 | 40 | 40 | 40 | 40 | 40 | 40 | Techs & SLS |  |  |  | 3 | 5.5 | 6.5 | 40 | 40 | 40 | 40 | 40 | 40
Other |  |  |  | 0.5 | 0.5 | 0.75 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | Other |  |  |  | 0.5 | 0.5 | 0.75 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Staffing Profile Total |  |  |  | 6 | 10.3 | 12.7 | 69.1196 | 69.1196 | 69.1196 | 69.1196 | 69.1196 | 69.1196 | Staffing Profile Total |  |  |  | 6 | 10.3 | 12.7 | 69.1196 | 69.1196 | 69.1196 | 69.1196 | 69.1196 | 69.1196
| FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
NCSX RESEARCH-National (FY09 M$) |  | 0.7 | 0.7 | 0.7 | 3 | 8 | 12 | 15 | 18 | 18 | 18 | 18 | NCSX RESEARCH-National (FY09 M$) |  | 0.7 | 0.7 | 0.7 | 3 | 8 | 12 | 15 | 18 | 18 | 18 | 18
NCSX RESEARCH - PPPL (FY 09 M$) |  | 0.375 | 0.375 | 0.375 | 1.5 | 4 | 6 | 7.5 | 9 | 9 | 9 | 9 | NCSX RESEARCH - PPPL (FY 09 M$) |  | 0.375 | 0.375 | 0.375 | 1.5 | 4 | 6 | 7.5 | 9 | 9 | 9 | 9
NCSX RESEARCH-OTHERS (FY09 M$) |  | 0.325 | 0.325 | 0.325 | 1.5 | 4 | 6 | 7.5 | 9 | 9 | 9 | 9 | NCSX RESEARCH-OTHERS (FY09 M$) |  | 0.325 | 0.325 | 0.325 | 1.5 | 4 | 6 | 7.5 | 9 | 9 | 9 | 9
Staffing Profile (FTE) (DIRECT) | [12 empty] | Staffing Profile (FTE) (DIRECT)
RM (Expt) |  | 1 | 1 | 1 | 3.1167 | 8.3111 | 12.4667 | 15.5833 | 18.7 | 18.7 | 18.7 | 18.7 | RM (Expt) |  | 1 | 1 | 1 | 3.1167 | 8.3111 | 12.4667 | 15.5833 | 18.7 | 18.7 | 18.7 | 18.7
RM (Theorists) |  | 0 | 0 | 0 | 0.33333 | 0.88889 | 1.3333 | 1.6667 | 2 | 2 | 2 | 2 | RM (Theorists) |  |  |  |  | 0.33333 | 0.88889 | 1.3333 | 1.6667 | 2 | 2 | 2 | 2
RM (CPPG) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RM (CPPG)
Engineers (Computer) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Engineers (Computer)
Engineers (Mech) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Engineers (Mech)
Engineers (Electrical) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Engineers (Electrical)
Engineers (FOM) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Engineers (FOM)
Techs & SLS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Techs & SLS
Other |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other
Staffing Profile Total |  | 1 | 1 | 1 | 3.45 | 9.2 | 13.8 | 17.25 | 20.7 | 20.7 | 20.7 | 20.7 | Staffing Profile Total |  | 1 | 1 | 1 | 3.45 | 9.2 | 13.8 | 17.25 | 20.7 | 20.7 | 20.7 | 20.7
| FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18
[5 empty] | 1 | 1.25 | 0.9375 | 1.0714 | 1 | 1 | 1 | 1
NCSX UPGRADES-National (FY09 M$) |  |  |  |  | 10 | 24 | 9.5 | 7.4 | 6 | 6 | 6 | 6 | NCSX UPGRADES-National (FY09 M$) |  |  |  |  | 10 | 20 | 10 | 7 | 6 | 6 | 6 | 6
NCSX UPGRADES - PPPL (FY 09 M$) |  |  |  |  | 8 | 20 | 7.5 | 6 | 4.5 | 4.5 | 4.5 | 4.5 | NCSX UPGRADES - PPPL (FY 09 M$) |  |  |  |  | 8 | 16 | 8 | 5.6 | 4.5 | 4.5 | 4.5 | 4.5
NCSX UPGRADES - OTHERS(FY09 M$) |  |  |  |  | 2 | 4 | 2 | 1.4 | 1.5 | 1.5 | 1.5 | 1.5 | NCSX UPGRADES - OTHERS(FY09 M$) |  |  |  |  | 2 | 4 | 2 | 1.4 | 1.5 | 1.5 | 1.5 | 1.5
Staffing Profile (FTE) (DIRECT) | [12 empty] | Staffing Profile (FTE) (DIRECT)
RM (Expt) | [12 empty] | RM (Expt)
RM (Theorists) | [12 empty] | RM (Theorists)
RM (CPPG) | [12 empty] | RM (CPPG)
Engineers (Computer) |  |  |  |  | 0.236 | 1.575 | 0.22125 | 0.80357 | 0.4 | 0.4 | 0.4 | 0.4 | Engineers (Computer) |  |  |  |  | 0.236 | 1.26 | 0.236 | 0.75 | 0.4 | 0.4 | 0.4 | 0.4
Engineers (Mech) |  |  |  |  | 0.063 | 0.125 | 0.059063 | 0.6 | 0.4 | 0.4 | 0.4 | 0.4 | Engineers (Mech) |  |  |  |  | 0.063 | 0.1 | 0.063 | 0.56 | 0.4 | 0.4 | 0.4 | 0.4
Engineers (Electrical) |  |  |  |  | 0.783 | 6.1875 | 0.73406 | 1.6071 | 1.1 | 1.1 | 1.1 | 1.1 | Engineers (Electrical) |  |  |  |  | 0.783 | 4.95 | 0.783 | 1.5 | 1.1 | 1.1 | 1.1 | 1.1
Engineers (FOM) |  |  |  |  | 2.03 | 2.2375 | 1.9031 | 1.5 | 0.96 | 0.96 | 0.96 | 0.96 | Engineers (FOM) |  |  |  |  | 2.03 | 1.79 | 2.03 | 1.4 | 0.96 | 0.96 | 0.96 | 0.96
Techs & SLS |  |  |  |  | 13.93 | 24.125 | 13.0594 | 10.7143 | 8 | 8 | 8 | 8 | Techs & SLS |  |  |  |  | 13.93 | 19.3 | 13.93 | 10 | 8 | 8 | 8 | 8
Other | [12 empty] | Other
Staffing Profile Total |  |  |  |  | 17.042 | 34.25 | 15.9769 | 15.225 | 10.86 | 10.86 | 10.86 | 10.86 | Staffing Profile Total |  |  |  |  | 17.042 | 27.4 | 17.042 | 14.21 | 10.86 | 10.86 | 10.86 | 10.86
| FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 |  | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18
NCSX MIE Projected Costs (Year of Expenditure M$) | FY09: 21.5; FY10: 20.4; FY11: 21.3; FY12: 6.3 | NCSX MIE Projected Costs (Year of Expenditure M$) |  |  | 21.5 | 20.4 | 21.3 | 6.3
NCSX MIE (FY09 M$) | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF! | NCSX MIE (FY09 M$) |  | #REF! | #REF! | #REF! | #REF! | #REF!
PPPL | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF! | PPPL |  | #REF! | #REF! | #REF! | #REF! | #REF!
ORNL | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF! | ORNL |  | #REF! | #REF! | #REF! | #REF! | #REF!
NCSX National Total (FY09 M$) |  |  | #REF! | #REF! | #REF! | #REF! | 43.5 | 44.4 | 46 | 46 | 46 | 46
PPPL |  |  | #REF! | #REF! | #REF! | #REF! | 35.5 | 35.5 | 35.5 | 35.5 | 35.5 | 35.5
Rich PPPL |  | 14.8 | 18.8 | 17.8 | 30.7 | 32.3 | 31.4 | 31.4 | 31.4 | 31.4 | 31.4 | 31.4
NCSX MIE-National (FY09 M$) | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: 0
NCSX MIE - PPPL (FY 09 M$) | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: 0
NCSX MIE - OTHERS(FY09 M$) | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: 0
Staffing Profile (FTE) (DIRECT)
RM (Expt) | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: #REF!
RM (Theorists)
RM (CPPG)
Engineers (Computer) | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: #REF!
Engineers (Mech) | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: #REF!
Engineers (Electrical) | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: #REF!
Engineers (FOM) | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: #REF!
Techs & SLS | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: #REF!
Other | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: #REF!
Staffing Profile Total | FY08: #REF!; FY09: #REF!; FY10: #REF!; FY11: #REF!; FY12: #REF!; FY13: #REF!
| FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18
NCSX Program-National (FY09 M$) |  | #REF! | #REF! | #REF! | #REF! | #REF! | 43.5 | 44.4 | 46 | 46 | 46 | 46
NCSX Progra - PPPL (FY 09 M$) |  | #REF! | #REF! | #REF! | #REF! | #REF! | 35.5 | 35.5 | 35.5 | 35.5 | 35.5 | 35.5
NCSX Program - OTHERS(FY09 M$) |  | #REF! | #REF! | #REF! | #REF! | #REF! | 8 | 8.9 | 10.5 | 10.5 | 10.5 | 10.5
Staffing Profile (FTE) (DIRECT)
RM (Expt) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 16.5616 | 19.6783 | 19.6783 | 19.6783 | 19.6783
RM (Theorists) |  | 0 | 0 | 0 | 0.33333 | 0.88889 | 1.3333 | 1.6667 | 2 | 2 | 2 | 2
RM (CPPG) |  | 0 | 0 | 0 | 0 | 0.2 | 2.1739 | 2.1739 | 2.1739 | 2.1739 | 2.1739 | 2.1739
Engineers (Computer) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6.5862 | 6.1826 | 6.1826 | 6.1826 | 6.1826
Engineers (Mech) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.6109 | 1.4109 | 1.4109 | 1.4109 | 1.4109
Engineers (Electrical) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12.8245 | 12.3174 | 12.3174 | 12.3174 | 12.3174
Engineers (FOM) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6.9565 | 6.4165 | 6.4165 | 6.4165 | 6.4165
Techs & SLS incl designers |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 50.7143 | 48 | 48 | 48 | 48
Other |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Staffing Profile Total |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 101.5946 | 100.6796 | 100.6796 | 100.6796 | 100.6796

## MIE closeout staff detail
NCSX CLOSEOUT PLAN STAFFING REQUIREMENTS (hours/160)
Dept | Name | Job |  | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09
ORNL | COLE | Job: 1421 -Mod Coil Interface Design-COLE | [6 empty] | 0.8
ORNL | COLE | Job: 1806 -FP Assembly specs and drawings-COLE | [6 empty] | 0.3
ORNL | COLE | Job: 1901 -Stellarator Core Mngtt&Integr-COLE | [6 empty] | 0.4 | 0.4 | 0.4 | 0.4
ORNL | COLE | Job: 8221 -Documentation Closeout- | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | COLE subtotal = | [6 empty] | 1.5 | 0.5 | 0.5 | 0.5 | 0.1
[8 empty] | Actual = | 0.63 | 0
ORNL | FOGARTY | Job: 1901 -Stellarator Core Mngtt&Integr-COLE | [6 empty] | 0.1 | 0.1 | 0.1
ORNL | FOGARTY | Job: 8221 -Documentation Closeout- | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | FOGARTY subtotal = | [6 empty] | 0.1 | 0.2 | 0.2 | 0.1 | 0.1
[8 empty] | Actual = | 0.51 | 0
ORNL | FREUDENBERG | Job: 1416 -Mod Coil Type AB Fnl Dsn-COLE | [6 empty] | 0.6
ORNL | FREUDENBERG | Job: 1421 -Mod Coil Interface Design-COLE | [6 empty] | 0.2 | 0.1
ORNL | FREUDENBERG | Job: 8221 -Documentation Closeout-HEITZENROEDER | [6 empty] | 0.3 | 0.5 | 0.4 | 0.4 | 0.2
|  | FREUDENBERG subtotal = | [6 empty] | 1.1 | 0.6 | 0.4 | 0.4 | 0.2
[8 empty] | Actual = | 0.13 | 0
ORNL | GORANSON | Job: 1601 -Coil Services Design-GORANSON | [6 empty] | 0.3
ORNL | GORANSON | Job: 8221 -Documentation Closeout | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | GORANSON subtotal = | [6 empty] | 0.3 | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual = | 0.6 | 0
ORNL | HARRIS | Job: 8102 -NCSX MIE Management ORNL | [6 empty] | 0.4 | 0.5 | 0.4 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual = | 0.1 | 0
ORNL | HILLIS | Job: 8102 -NCSX MIE Management ORNL | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0.1
[8 empty] | Actual = | 0.14 | 0
ORNL | HOMESCU | Job: 1601 -Coil Services Design-GORANSON | [6 empty] | 0.3
[8 empty] | Actual = | 0.53 | 0
ORNL | LOVETT | Job: 1416 -Mod Coil Type AB Fnl Dsn-COLE | [6 empty] | 0.5
ORNL | LOVETT | Job: 1901 -Stellarator Core Mngtt&Integr-COLE | [6 empty] | 0.3 | 0.3 | 0.3 | 0.2
|  | LOVETT subtotal = | [6 empty] | 0.8 | 0.3 | 0.3 | 0.2
[8 empty] | Actual = | 0.72 | 0
ORNL | MCGINNIS | Job: 1601 -Coil Services Design-GORANSON | [6 empty] | 0.8
ORNL | MCGINNIS | Job: 1802 -FP Assy Oversight&Support-VIOLA | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2
ORNL | MCGINNIS | Job: 1901 -Stellarator Core Mngtt&Integr-COLE | [6 empty] | 0.3 | 0.3 | 0.3 | 0.3
|  | MCGINNIS subtotal = | [6 empty] | 1.3 | 0.5 | 0.5 | 0.5
[8 empty] | Actual = | 1 | 0
ORNL | MMORRIS | Job: 8102 -NCSX MIE Management ORNL-HARRIS | [6 empty] | 0.3 | 0.3 | 0.3 | 0.3
[8 empty] | Actual = | 0.23 | 0
ORNL | MOON | Job: 1421 -Mod Coil Interface Design-COLE | [6 empty] | 0.5 | 0.3
[8 empty] | Actual = | 0.54 | 0
ORNL | NELSON | Job: 1901 -Stellarator Core Mngtt&Integr-COLE | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual = | 0.01 | 0
ORNL | ORNL unassigned | Job: 1421 -Mod Coil Interface Design-COLE | [6 empty] | 0.2 | 0.1
[8 empty] | Actual = | 1.3 | 0
ORNL | WILLIAMSON | Job: 1416 -Mod Coil Type AB Fnl Dsn-COLE | [6 empty] | 0.4
ORNL | WILLIAMSON | Job: 8221 -Documentation Closeout- | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | WILLIAMSON subtotal = | [6 empty] | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | [5 empty] | 4.225
[8 empty] | Actual = | 0.35 | 0
|  | ORNL TOTAL = |  | 7.6 | 8.1 | 7.8 | 11.1 | 8.44 | 7.4 | 3.7 | 3 | 2.8 | 0.8 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2
[8 empty] | Actual = | 6.79 | 0
[9 empty] | 6.9 | 3.1 | 2.5 | 2.3 | 0.6 | 0 | 0 | 0 | 0 | 0
PPPL Computing | SICHTA et al | Job: 8221 -Documentation Closeout | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual = | 0.54 | 0
PPPL DESIGN | CRUIKSHANK | Job: 1354 -Trim Coil Design &Procurement-KALISH | [6 empty] | 1
PPPL DESIGN | CRUIKSHANK | Job: 1501 -Coil Structures Design-DAHLGREN | [6 empty] | 0.6
PPPL DESIGN | CRUIKSHANK | Job: 1702 -Base Support Struct Design-DAHLGREN | [6 empty] | 0.3
|  | CRUIKSHANK subtotal = | [5 empty] | Planned = | 1.9
[8 empty] | Actual = | 0 | 0
PPPL DESIGN | unassigned | Job: 8203 -Design Integration-BROWN | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1
PPPL DESIGN | unassigned | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 2.2 | 2.1 | 2.1 | 2.4 | 1.8 | 1.7
|  | unassigned subtotal = | [5 empty] | Planned = | 0.1 | 2.3 | 2.2 | 2.2 | 2.4 | 1.8 | 1.7
[8 empty] | Actual = | 0.96 | 0.13
PPPL DESIGN | MORRIS | Job: 1803/1805-FPA Tooling/Constr-BROWN | [8 empty] | 0.2 | 0.1
PPPL DESIGN | MORRIS | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.5 | 0.5 | 0.5 | 0.6
|  | MORRIS subtotal = | [5 empty] | Planned = | 0 | 0.5 | 0.7 | 0.6 | 0.6
[8 empty] | Actual = | 0.55 | 0.6
PPPL DESIGN | RUSHINSKI | Job: 1354 -Trim Coil Design &Procurement-KALISH | [6 empty] | 0.1
PPPL DESIGN | RUSHINSKI | Job: 1501 -Coil Structures Design-DAHLGREN | [6 empty] | 0.9
PPPL DESIGN | RUSHINSKI | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.5 | 0.5 | 0.5 | 0.6
|  | RUSHINSKI subtotal = | [5 empty] | Planned = | 1 | 0.5 | 0.5 | 0.5 | 0.6
[8 empty] | Actual = | 0.94 | 0.86
PPPL DESIGN | UPCAVAGE | Job: 8221 -Documentation Closeout-HEITZENROEDER | [5 empty] | Planned = | 0 | 0.3 | 0.3 | 0.3 | 0.4
[8 empty] | Actual = | 0.95 | 0
|  | TOTAL DESIGNERS = |  | 1.6 | 5.5 | 2.4 | 2.1 | 5.4 | 3 | 3.6 | 3.7 | 3.6 | 4 | 1.8 | 1.7
[8 empty] | Actual = | 3.4 | 1.59
PPPL EA Engr | AVASARALA | Job: 8221 -Documentation Closeout-HEITZENROEDER | [6 empty] | 0.3 | 0.3 | 0.3 | 0.2
[8 empty] | Actual = | 0.97 | 1
PPPL EA Engr | BROOKS | Job: 8204 -Systems Analysis-BROOKS | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2
PPPL EA Engr | BROOKS | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.2 | 0.2 | 0.2 | 0.2
|  | BROOKS subtotal = | [6 empty] | 0.2 | 0.4 | 0.4 | 0.4 | 0.2
[8 empty] | Actual = | 0.21 | 0.78
PPPL EA Engr | BROWN | Job: 1803/1805-FPA Tooling/Constr-BROWN | [6 empty] | 0.2 | 0 | 0 | 0
PPPL EA Engr | BROWN | Job: 8203 -Design Integration-BROWN | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1
PPPL EA Engr | BROWN | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.6 | 0.6 | 0.6 | 0.6
|  | BROWN subtotal = | [6 empty] | 0.3 | 0.7 | 0.7 | 0.7 | 0.6
[8 empty] | Actual = | 1 | 0.61
PPPL EA Engr | CHRZANOWSKI | Job: 1451 -Mod Coil Winding-CHRZANOWSKI | [6 empty] | 0.5 | 0.5 | 0.5
PPPL EA Engr | CHRZANOWSKI | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.3 | 0.3 | 0.3 | 0.3
|  | CHRZANOWSKI subtotal = | [6 empty] | 0.5 | 0.8 | 0.8 | 0.3 | 0.3
[8 empty] | Actual = | 0.54 | 0.43
PPPL EA Engr | DAHLGREN | Job: 1501 -Coil Structures Design-DAHLGREN | [6 empty] | 1.4
PPPL EA Engr | DAHLGREN | Job: 1702 -Base Support Struct Design-DAHLGREN | [6 empty] | 0.3
PPPL EA Engr | DAHLGREN | Job: 8221 -Documentation Closeout-HEITZENROEDER | [6 empty] | 0.3 | 0.9 | 0.9 | 0.8 | 0.7
|  | DAHLGREN subtotal = | [6 empty] | 2 | 0.9 | 0.9 | 0.8 | 0.7
[8 empty] | Actual = | 0.94 | 0.94
PPPL EA Engr | unassigned | Job: 8222 -Manuscripts and Papers -NEILSON | [9 empty] | 0.7 | 0.8 | 0.6 | 0.6 | 0.7 | 0.7 | 0.8
PPPL EA Engr | unassigned | Job: 1354 -Trim Coil Design &Procurement-KALISH
[8 empty] | Actual = | 0 | 0.14
PPPL EA Engr | ELLIS | Job: 8205 -Dimensional Control Coordin-ELLIS | [6 empty] | 0.2 | 0.3 | 0.3 | 0.1
PPPL EA Engr | ELLIS | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | ELLIS subtotal = | [6 empty] | 0.2 | 0.4 | 0.4 | 0.2 | 0.1
[8 empty] | Actual = | 0.32 | 0.21
PPPL EA Engr | FAN | Job: 1501 -Coil Structures Design-DAHLGREN | [6 empty] | 0.3
PPPL EA Engr | FAN | Job: 8204 -Systems Analysis-BROOKS | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1
PPPL EA Engr | FAN | Job: 8221 -Documentation Closeout-HEITZENROEDER | [6 empty] | 0.3 | 0.3 | 0.3 | 0.2
|  | FAN subtotal = | [6 empty] | 0.7 | 0.4 | 0.4 | 0.3
[8 empty] | Actual = | 0.89 | 0.97
PPPL EA Engr | HEITZENROED | Job: 8202 -Engr Mgmt & Sys Eng Sprt-HEITZENROED | [6 empty] | 0.7 | 0.7 | 0.7 | 0.7 | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.4
PPPL EA Engr | HEITZENROED | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.3 | 0.2 | 0.2 | 0.3
|  | HEITZENROED subtotal = | [6 empty] | 0.7 | 1 | 0.9 | 0.9 | 0.7 | 0.3 | 0.3 | 0.3 | 0.3 | 0.4
[8 empty] | Actual = | 0.68 | 0.54
PPPL EA Engr | JUN | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.2 | 0.2 | 0.2 | 0.2
[8 empty] | Actual = | 0 | 0
PPPL EA Engr | KALISH | Job: 1354 -Trim Coil Design &Procurement-KALISH | [6 empty] | 0.1
PPPL EA Engr | KALISH | Job: 1361 -TF Fabrication-KALISH | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1
PPPL EA Engr | KALISH | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | KALISH subtotal = | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.1
[8 empty] | Actual = | 0.29 | 0.18
PPPL EA Engr | RAFTOPOULOS | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.3 | 0.3 | 0.3 | 0.4
[8 empty] | Actual = | 0.64 | 0.05
PPPL EA Engr | REIERSEN | Job: 8202 -Engr Mgmt & Sys Eng Sprt-HEITZENROED | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
PPPL EA Engr | REIERSEN | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.3 | 0.2 | 0.2 | 0.3
|  | REIERSEN subtotal = | [6 empty] | 0.1 | 0.4 | 0.3 | 0.3 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual = | 0.1 | 0
PPPL EA Engr | SIMMONS | Job: 8101 -Project Management &Control-REJ | [10 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
PPPL EA Engr | SIMMONS | Job: 8221 -Documentation Closeout-HEITZENROEDER | [6 empty] | 0.5 | 0.7 | 0.7 | 0.7 | 0.6 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
|  | SIMMONS subtotal = | [6 empty] | 0.5 | 0.7 | 0.7 | 0.7 | 0.7 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
[8 empty] | Actual = | 0.75 | 1
PPPL EA Engr | ZHANG | Job: 8204 -Systems Analysis-BROOKS | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1
PPPL EA Engr | ZHANG | Job: 8221 -Documentation Closeout-HEITZENROEDER | [6 empty] | 0.3 | 0.3 | 0.3 | 0.2
|  | ZHANG subtotal = | [6 empty] | 0.4 | 0.4 | 0.4 | 0.3
[8 empty] | Actual = | 0.81 | 0
|  | TOTAL EA ENGINEERS = |  | 5.2 | 8.3 | 8.4 | 10.8 | 10.3 | 6.1 | 7.1 | 6.9 | 6.5 | 5.2 | 1.4 | 1.4 | 1.5 | 1.5 | 1.7
[8 empty] | Actual = | 8.14 | 6.85
PPPL Electrical Admin | SUCH | Job: 8202 -Engr Mgmt & Sys Eng Sprt-HEITZENROED | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
PPPL Electrical Admin | SUCH | Job: 8221 -Documentation Closeout-HEITZENROEDER | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
|  | Such subtotal = | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
[8 empty] | Actual = | 0.21 | 0.16
PPPL Electrical Engr | VONHALLE/Raki | Job: 8202 -Engr Mgmt & Sys Eng Sprt-HEITZENROED | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual = | 0 | 0.34
PPPL FO&M Engr | BLANCHARD | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual = | 0.03 | 0.01
PPPL FO&M Engr | DODSON **TERM** | Job: 1810 -Field Period AssyStation 1 2 3 VIOLA METROLOGY | [6 empty] | 1 | 1 | 1 | 1
PPPL FO&M Engr | DODSON **TERM** | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | DODSON **TERM** subtotal = | [6 empty] | 1 | 1.1 | 1.1 | 1.1 | 0.1
[8 empty] | Actual = | 0.86 | 0.94
PPPL FO&M Engr | DUDEK | Job: 8202 -Engr Mgmt & Sys Eng Sprt-HEITZENROED | [6 empty] | 0.7 | 0.8 | 0.7 | 0.7 | 0.4 | 0.3 | 0.3 | 0.4 | 0.3 | 0.4
PPPL FO&M Engr | DUDEK | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.1 | 0 | 0 | 0.1
|  | DUDEK subtotal = | [6 empty] | 0.7 | 0.9 | 0.7 | 0.7 | 0.5 | 0.3 | 0.3 | 0.4 | 0.3 | 0.4
[8 empty] | Actual = | 0.36 | 0.43
PPPL FO&M Engr | unassigned | Job: 8222 -Manuscripts and Papers -NEILSON | [9 empty] | 0.4 | 0.4 | 0.3 | 0.3 | 0.4 | 0.4 | 0.4
PPPL FO&M Engr | unassigned | Job: 1810 -Field Period AssyStation 1 2 3 VIOLA METROLOGY
[8 empty] | Actual = | 0.85 | 1.58
PPPL FO&M Engr | LABIK | Job: 3101 -Magnetic Diagnostics-STRATTON | [6 empty] | 0.3
PPPL FO&M Engr | LABIK | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | LABIK subtotal = | [6 empty] | 0.3 | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual = | 0 | 0.16
PPPL FO&M Engr | LANGISH | Job: 1451 -Mod Coil Winding-CHRZANOWSKI | [6 empty] | 0.4 | 0.4 | 0.4 | 0.4
[8 empty] | Actual = | 0.32 | 0.29
PPPL FO&M Engr | PERRY | Job: 8220 -Equipt Save & Facility Restora-PERRY | [6 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.3
[8 empty] | Actual = | 0.21 | 0.16
PPPL FO&M Engr | PRINISKI | Job: 1810 -Field Period AssyStation 1 2 3 VIOLA METROLOGY | [6 empty] | 1 | 1 | 1 | 1 | 0.4
[8 empty] | Actual = | 0.48 | 0.54
PPPL FO&M Engr | SANDS **PU** | Job: 1802 -FP Assy Oversight&Support-VIOLA | [6 empty] | 0.6 | 0.7 | 0.6 | 0.6
[8 empty] | Actual = | 0.43 | 0
PPPL FO&M Engr | SMITH | Job: 1803/1805-FPA Tooling/Constr-BROWN | [6 empty] | 0.8 |  | 0.2 | 0.1
PPPL FO&M Engr | SMITH | Job: 8205 -Dimensional Control Coordin-ELLIS | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | SMITH subtotal = | [6 empty] | 0.9 | 0.1 | 0.3 | 0.2
[8 empty] | Actual = | 0.61 | 0.35
PPPL FO&M Engr | VIOLA | Job: 1802 -FP Assy Oversight&Support-VIOLA | [6 empty] | 0.9 | 0.9 | 0.9 | 0.9
PPPL FO&M Engr | VIOLA | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.2 | 0.2 | 0.2 | 0.3
|  | VIOLA subtotal = | [6 empty] | 0.9 | 1.1 | 1.1 | 1.1 | 0.3
[8 empty] | Actual = | 0.86 | 0.47
|  | TOTAL FO&M ENGINEERS = |  | 4.1 | 7.3 | 8.2 | 8.5 | 7.1 | 6.2 | 5.9 | 5.8 | 6.1 | 2.3 | 0.9 | 0.9 | 0.8 | 0.7 | 0.8
[8 empty] | Actual = | 5.01 | 4.93
PPPL FO&M TECH | DREXEL | Job: 1802 -FP Assy Oversight&Support-VIOLA | [6 empty] | 1.1
PPPL Electrical SL&S | EDWARDS | Job: 1810 -Field Period AssyStation 1 2 3 VIOLA | [6 empty] | 0.9 | 0.9 | 0.9 | 0.9
PPPL FO&M TECH | DUCCO | Job: 1810 -Field Period AssyStation 1 2 3 VIOLA METROLOGY | [6 empty] | 1 | 1 | 1 | 0.7
PPPL FO&M TECH | EM//TB | Job: 1408 -MC Winding Supplies-CHRZANOWSKI | [6 empty] | 0.4 | 0.4
PPPL FO&M TECH | EM//TB | Job: 1451 -Mod Coil Winding-CHRZANOWSKI | [6 empty] | 4.3 | 3.9 | 1.5
PPPL FO&M TECH | EM//TB | Job: 1451 -Mod Coil Winding-CHRZANOWSKI | [7 empty] | 1.7
PPPL FO&M TECH | EM//TB | Job: 1451 -Mod Coil Winding-CHRZANOWSKI | [7 empty] | 0.3 | 0.2
PPPL FO&M TECH | EM//TB | Job: 1459 -Mod Coil Fabr.Punch List-CHRZANOWSKI | [6 empty] | 1.8 | 1.8 | 1.8
PPPL FO&M TECH | EM//TB | Job: 1810 -Field Period AssyStation 1 2 3 VIOLA | [6 empty] | 9.1 | 9 | 6.7 | 6.7 | 1.2
PPPL FO&M TECH | EM//TB | Job: 3101 -Magnetic Diagnostics-STRATTON | [6 empty] | 0.1
PPPL FO&M TECH | EM//TB | Job: 8220 -Equipt Save & Facility Restora-PERRY | [7 empty] | 3.2 | 5.1 | 6.3 | 4.8 | 2.3 | 2.2
PPPL FO&M TECH | GUTTADORA | Job: 3101 -Magnetic Diagnostics-STRATTON | [6 empty] | 1
PPPL FO&M TECH | HAUSE | Job: 1810 -Field Period AssyStation 1 2 3 VIOLA METROLOGY | [6 empty] | 1 | 1 | 0.5
PPPL FO&M TECH | HUSH | Job: 1810 -Field Period AssyStation 1 2 3 VIOLA METROLOGY | [6 empty] | 1 | 0.6
PPPL FO&M TECH | LANGELLA | Job: 8220 -Equipt Save & Facility Restora-PERRY | [7 empty] | 0.5 | 0.3 | 1.5 | 1.5 | 1.2 | 1.1
PPPL FO&M TECH | MEIGHAN | Job: 1361 -TF Fabrication-KALISH | [6 empty] | 0.3 | 0.3 | 0.3 | 0.2
PPPL FO&M TECH | MEIGHAN | Job: 1451 -Mod Coil Winding-CHRZANOWSKI | [6 empty] | 0.7 | 0.7 | 0.7
PPPL FO&M TECH | STEVENS **TERM** | Job: 1810 -Field Period AssyStation 1 2 3 VIOLA METROLOGY | [6 empty] | 1
|  | TOTAL FO&M TECHS = |  | 15 | 39.2 | 26.4 | 25.4 | 27.6 | 23.7 | 25.3 | 19 | 16.3 | 7.5 | 3.5 | 3.3
[8 empty] | Actual = | 22.95 | 17.88
PPPL HP Techs | SH//TB | Job: 1802 -FP Assy Oversight&Support-VIOLA | [6 empty] | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.6 | 0.6
[8 empty] | Actual = | 1.02 | 0.94
PPPL Project Controls | STRYKOWSKY | Job: 8101 -Project Management &Control-REJ | [6 empty] | 0.8 | 0.9 | 0.8 | 0.8 | 0.5 | 0.4 | 0.4 | 0.5 | 0.4 | 0.5
PPPL Project Controls | STRYKOWSKY | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.3 | 0.2 | 0.2 | 0.3
|  | STRYKOWSKY subtotal = | [6 empty] | 0.8 | 1.2 | 1 | 1 | 0.8 | 0.4 | 0.4 | 0.5 | 0.4 | 0.5
[8 empty] | Actual = | 0.83 | 0.56
PPPL Research | NEILSON | Job: 8101 -Project Management &Control-REJ | [6 empty] | 0.6 | 0.7 | 0.6 | 0.6 | 0.4 | 0.3 | 0.3 | 0.4 | 0.3 | 0.4
PPPL Research | STRATTON | Job: 8221 -Documentation Closeout-HEITZENROEDER | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1
|  | TOTAL RESEARCH = | [6 empty] | 0.6 | 0.8 | 0.7 | 0.7 | 0.5 | 0.3 | 0.3 | 0.4 | 0.3 | 0.4
[8 empty] | Actual = | 0.66 | 1.34
|  |  |  | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09
|  |  | Planned DESIGNERS = | 1.6 | 5.5 | 2.4 | 2.1 | 5.4 | 3 | 3.6 | 3.7 | 3.6 | 4 | 1.8 | 1.7 | 0 | 0 | 0
|  |  | Actual DESIGNERS = | 1.6 | 5.5 | 2.4 | 2.1 | 5.4 | 3.4 | 1.59
|  |  | Planned EA ENGINEERS = | 5.2 | 8.3 | 8.4 | 10.8 | 10.3 | 6.1 | 7.1 | 6.9 | 6.5 | 5.2 | 1.4 | 1.4 | 1.5 | 1.5 | 1.7
|  |  | Actual EA ENGINEERS = | 5.2 | 8.3 | 8.4 | 10.8 | 10.3 | 8.14 | 6.85
|  |  | Planned FO&M ENGINEERS = | 4.1 | 7.3 | 8.2 | 8.5 | 7.1 | 6.2 | 5.9 | 5.8 | 6.1 | 2.3 | 0.9 | 0.9 | 0.8 | 0.7 | 0.8
|  |  | Actual FO&M ENGINEERS = | 4.1 | 7.3 | 8.2 | 8.5 | 7.1 | 5.01 | 4.93
| Plan |  | Planned TECHS = | 15 | 39.2 | 26.4 | 25.4 | 27.6 | 23.7 | 25.3 | 19 | 16.3 | 7.5 | 3.5 | 3.3 | 0 | 0 | 0
| Actual |  | Actual TECHS = | 15 | 39.2 | 26.4 | 25.4 | 27.6 | 22.95 | 17.88
|  |  | Planned ORNL= | 7.6 | 8.1 | 7.8 | 11.1 | 8.44 | 7.4 | 3.7 | 3 | 2.8 | 0.8 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2
|  |  | Actual ORNL= | 7.6 | 8.1 | 7.8 | 11.1 | 8.44 | 6.79 | 0
|  | other | [6 empty] | 31.03 | 29.66 | 18.8 | 19.3 | 8.2 | 3.9 | 3.9 | 3.4 | 2.9 | 3.4
[9 empty] | 123.72 | 106.51 | 57.2 | 54.6 | 28 | 11.6 | 11.3 | 5.8 | 5.2 | 6.1
NCSX Closeout Manpower