## Sheet1
Mothball NCSX Hardware
.
Item | Qty | Size | Storage | Perry | Viola | Langella | TB | HP | M&S
|  |  | Location | MH | MH | MH | MH | MH | $K
(Lift Mgr)
Items from TFTR Test Cell
Modular Coils | 18
3 pack on wedge | 4 | 8.5' x 9.5' | NCTC |  | 8 |  | 32 | 4
3 pack on pallet | 2 | 8' x 9.5' | NCTC |  | 4 |  | 16 | 2
fab pallet for 3 pack | 2 | [5 empty] | 16 |  | 0.2
Vacuum vessel segments | 3 | 11' x 15' | NCTC |  | 12 |  | 72 | 3 | 1.2
Port extension crates | 6 | 4' x 10' | NCTC |  |  |  | 8 | 6
MC Bolts | 2 | 4' x 4' | NCTCB |  |  |  | 4 | 2
Fab crate for MC bolts | 2 | [5 empty] | 16 |  | 0.4
Coil winding Station | 1 | 10' x 16' | NCTC |  |  |  | 64 | 8
Parts shelves with parts | 12 | 3' x 7' | NCTCB |  |  |  | 48 | 12
Cabinets | 24 |  | NCTCB |  |  |  | 48 | 24
Crates | 10 | 2' x 4' | NCTCB |  |  |  | 20 | 10
Crates | 4 | 3' x 4' | NCTCB |  |  |  | 8 | 4
Remove Autoclave
Safe all AC Power to autoclave | [5 empty] | 24 | 8
Electrical removals | [5 empty] | 400 | 616 | 77
Remove handrails and walkways |  |  | NCTCB |  |  |  | 96 | 2
Blower heater duct |  |  | NCTCB |  |  |  | 48 | 2
Ladder and stairways |  |  | NCTCB |  |  |  | 16 | 2
Remove tanks on platform | 3 |  | NCTCB |  |  |  | 8 | 1
Remove air lines |  |  | NCTCB |  |  |  | 8 | 1
Remove insulation |  |  | NCTCB |  |  |  | 96 | 4
Remove vent systems |  |  | NCTCB |  |  |  | 80 | 2
Remove autoclave pumps |  |  | NCTCB |  |  |  | 16 | 2
Remove pump line to pumps |  |  | NCTCB |  |  |  | 16 | 2
Remove injection platforms | 3 |  | NCTCB |  |  |  | 96 | 2
Remove N2 tanks / stands |  |  | NCTCB |  |  |  | 16 | 2
Move Autoclave to D-site Pad |  |  | D-site pad |  | 16 |  | 80 | 16 |  | load on low boy; re-survey; unload with mobile crane
Portable AC units | 3 |  | C-site crib |  |  |  | 8 | 3
Drawing closeouts and field follow-up | [5 empty] | 200
Small shield block | 4 |  | D-site pad |  |  |  | 16 | 4
Large shield block | 4 |  | D-site pad |  |  |  | 16 | 4
Machine mock-up |  |  | NCTC |  |  |  | 8 | 1
Welding machines | 4 |  | RESA |  |  |  | 8 | 4
Tools |  |  | C-site crib |  |  |  | 32 | 16
Measuring Equipment |  |  | S-109 |  |  |  | 16 | 4
Inventory parts, material and tools as to their new location | [6 empty] | 80
Items from TFTR Basement
Shelves | 1 |  | NCTCB |  |  |  | 4
Cabinets | 8 |  | NCTCB |  |  |  | 32
Pallets | 25 |  | NCTCB |  |  |  | 100
Fab two 10' pallets | 2 | 4' x 10' | NCTCB |  |  |  | 16 |  | 0.2
Spare coil conductor pallet | 5 | 4' x 4' | NCTCB |  |  |  | 20
Items from D-site yard
Cable tray stack | 10 | 4' x 15' | D-site pad |  |  |  | 10
Pallet of tray covers | 6 | 4' x 15' | D-site pad |  |  |  | 6
Fab pallets for tray covers | 6 | [5 empty] | 48 |  | 0.6
Pallet of brackets | 3 | 4' x 4' | D-site pad |  |  |  | 3
Pallet of gnd jumpers/hardware | 2 | 4' x 4' | D-site pad |  |  |  | 2
Items from NCTC/D-site MG
TF coil crates | 18 | 9'6" x 11'3" | NCTC |  |  |  | 36 |  |  | stack 6 high
Sta 3 (?) fixture crates | 2 | 7' x 7' | NCTC |  |  |  | 2 |  |  | combine crates
Items from CAS Bldg
Aluminum I-beams for platform |  | 6' x 4' x 24' | NCTC |  |  |  | 4
Aluminum tubes for platform |  | 2' x 3' x 24' | NCTC |  |  |  | 2
Finished beams and columns |  | 4' x 4' x 12' | NCTC |  |  |  | 2
Fab pallet for beams/colmns | 1 | 4' x 12' | NCTC |  |  |  | 8 |  | 0.1
Pallet of connector boxes | [6 empty] | 8
Fab crate for connector boxes | 1 | 4' x 4' | NCTC |  |  |  | 8 |  | 0.1
Column end plates | [6 empty] | 8
Fab crate for end plates | 1 | 4' x 4' | NCTC |  |  |  | 8 |  | 0.1
In NCTC
Remove PLT water headers from CS High Bay Area | [6 empty] | 24
Replace 50% of floor penetration covers in CS high bay | 14 | [5 empty] | 358 |  | 21 | Must complete before moving items into NCTC
Coordination and oversight |  |  |  | 244.5
TOTAL |  |  |  | 244.5 | 40 | 624 | 2445 | 226 | 23.9
EDP 6/4/08