## By Review or Audit
Review/QA Audit # | Date of Review or Audit | Chit/Audit Finding | CHIT Author | Person Responsible for Resolution | Chit/Audit Summary | Status | Due Date
Coil Tolerance, Trim Coil Peer Review Cognizant Engineer - Art Brooks | 2004-04-21 | 1 | Heitzenroeder, Phil | Kalish, Mike | Dynamic deflections - especially for modular coils - have to be taken into account in criteria. |  | Must be resolved prior to trim coil PDR
Coil Tolerance, Trim Coil Peer Review Cognizant Engineer - Art Brooks | 2004-04-21 | 2 | Kalish, Mike | Kalish, Mike | Tolerances of + 3.0mm for PF5, PF 6 and TF (and maybe trim coils) may require an "extra" effort. Will be helpful to define exceptions to the rule so that we meet tolerances as required but are allowed relief in less critical areas. |  | Must be resolved prior to trim coil PDR
Coil Tolerance, Trim Coil Peer Review Cognizant Engineer - Art Brooks | 2004-04-21 | 3 | Kalish, Mike | Kalish, Mike | Provide requirements for brining out trim coil leads. How many individual circuits penetrate the cryostat on day one? |  | Must be resolved prior to trim coil PDR
Coil Tolerance, Trim Coil Peer Review Cognizant Engineer - Art Brooks | 2004-04-21 | 4 | Zarnstorff, Mike | Kalish, Mike | Re: Building Steel: need to characterize residual error fields and island when (a) use PF coils to compensate steel fields, as best you can ; (b) same as (a) but allow upper/lower PF coil currents to differ; (c) same as (b) but include trim coils. |  | Must be resolved prior to trim coil PDR
Coil Tolerance, Trim Coil Peer Review Cognizant Engineer - Art Brooks | 2004-04-21 | 5 | Reiersen, Wayne | Kalish, Mike | Document current patterns in trim coils required to correct each mode and each phase. |  | Must be resolved prior to trim coil PDR
Coil Tolerance, Trim Coil Peer Review Cognizant Engineer - Art Brooks | 2004-04-21 | 6 | Reiersen, Wayne | Kalish, Mike | Consider a 2-step tolerance requirement for the modular coils based on separation from the plasma boundary. |  | Must be resolved prior to trim coil PDR
Coil Tolerance, Trim Coil Peer Review Cognizant Engineer - Art Brooks | 2004-04-21 | 7 | Reiersen, Wayne | Kalish, Mike | Tolerance requirements on trim coils need to be justified. |  | Must be resolved prior to trim coil PDR
Shield Wall Reconfiguration PDR Cognizant Engineer - Bob Parsells | 2004-03-09 | 1 | Gettelfinger, Geoff | Perry, Erik | New Scope? An interface control document must be generated for: (1) N2 emergency exhaust duct; and (2) tons of pipe and creeping add-ons. I can do #1. |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Cognizant Engineer - Bob Parsells | 2004-03-09 | 2 | Brown, Tom | Perry, Erik | If there is a plan at some future date to add another layer of shield block, wouldn't it not be prudent to make the larger base shield block large enough to support the future blocks? |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Cognizant Engineer - Bob Parsells | 2004-03-09 | 3 | Viola, Mike | Perry, Erik | Forklift handling has been mentioned for the blocks. If forklift is used then 4' clearance is needed from face of the block. Slots under block would be needed. Rigging from forklift must be avoided consider standard block handling design Richmond anchor, etc. |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Cognizant Engineer - Bob Parsells | 2004-03-09 | 4 | Levine, Jerry | Perry, Erik | An ALARA Cost/Benefit Analysis should be performed for the shielding design. Consult with George Ascione. |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Cognizant Engineer - Bob Parsells | 2004-03-09 | 5 | Reiersen, Wayne | Perry, Erik | Consider raising the shield wall to highest "Practical" Height. Avoid relying on later reconfigurations. |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Cognizant Engineer - Bob Parsells | 2004-03-09 | 6 | Kalish, Mike | Perry, Erik | GRD requirement for seismic references DOE-STD-1020 which calls out JBC-2000. Static site specific criteria lead to the required horizontal shear of: V=.15W for "detailed plain masonry shear wall" V=.20 for "ordinary plain masonry shear wall" verify design meets the IBC-2000 criteria. |  | Must be resolved prior to reconfiguration
Shield Wall Reconfiguration PDR Cognizant Engineer - Bob Parsells | 2004-03-09 | 7 | Levine, Jerry | Perry, Erik | Shielding design and extent must be verified by analysis to meet the NCSX radiation exposure requirements for occupants outside the NCSX Test Cell (e.g., control room operator, office occupants, etc.) include sky shine. |  | Must be resolved prior to reconfiguration
Twisted Racetrack Coil FDR cognizant Engineer - Dave Willimanson | 2004-10-15 | 1 | Reiersen, Wayne | Williamson, Dave | No details presented on how "real time" determination of surface error (+/-) provided. Readiness of metrology effort for TRC Winding needs to be established |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 2 | Brown, Tom | Williamson, Dave | The metrology measurement system needs to be demonstrated before the winding of the coil. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 3 | Reiersen, Wayne | Chrzanowski, Jim | Provide schedule for demonstrating measurement capability required for TRC winding. TRC not even measured yet. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 4 | Reiersen, Wayne | Williamson, Dave | The specification for electrical isolation needs to be clarified. Properties of adhesive tape needs to be determined. Electrical tests need to be in the procedures. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 5 | Reiersen, Wayne | Chrzanowski, Jim | Need to figure out how to dissect coil w/o losing registration of winding to tee. Consideration should be given to more exotic, non-destructive options. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 6 | Reiersen, Wayne | Chrzanowski, Jim | Consider winding a complete coil to establish shimming requirements. Then rewind the coil using differences in clamping pressure to control boundary. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 7 | Reiersen, Wayne | Chrzanowski, Jim | Resolve whether the relief gets filled with RTV or Roving. (Roving would mechanically lock the winding which may not be good). |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 8 | Levine, Jerry | Chrzanowski, Jim | Lead blocks - it was mentioned during the presentation that this would be made of G10 or G11. For production coil, since G10 tends to become neutron-activated cause "hot spots" (Doe commend use of G11, not G10. Similarly for any other proposed uses of G10 or G11. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 9 | Dudek, Larry | Chrzanowski, Jim | Need to qualify the sil-foil carbon tong Braze procedure or write an exception. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 10 | Stratton, Brent | Chrzanowski, Jim | Measure signal in diagnostic flux loops while coil is energized. Check conformity of flux loops after coil fabrication is complete. Verify that center conductors of loop cables will not shorted to ground or other coil structures. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 11 | Stratton, Brent | Chrzanowski, Jim | The diagnostic flux loops need to be accurate, located (~1/16") at the outer "corners" of the winding pads! A groove should be put it into the surface on which the loop should be used to accurately, measure the path of each loop as-built |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 12 | Gettelfinger, Geoff | Chrzanowski, Jim | Provide epoxy strainer on fluid line to coil distribution manifold. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 13 | Dudek, Larry | Chrzanowski, Jim | Additional potential issue: 1) cladding and chill plates too time consuming. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 14 | Brown, Tom | Chrzanowski, Jim | Add to the assembly procedure the electrical tests required to assure that no shorts are present in the copper coolant system. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 15 | Dudek, Larry | Chrzanowski, Jim | Use a conductivity meter or some other device to monitor the resistance to ground (MCWF) during chadding installation. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 15 | Nelson, Brad | Chrzanowski, Jim | Take lots of pictures. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 16 | Nelson, Brad | Chrzanowski, Jim | Consider using fiber optic strain gages. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 17 | Nelson, Brad | Chrzanowski, Jim | Consider renting another Romer arm for 3rd winding station. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 18 | Nelson, Brad | Chrzanowski, Jim | Develop an insulation schematic to show what is connected. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 19 | Nelson, Brad | Chrzanowski, Jim | Use a grounded paddle to check for wiskers. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 20 | Nelson, Brad | Chrzanowski, Jim | Electical insulation looks marginal. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 21 | Malsbury, Judy | Chrzanowski, Jim | Assure resistive brazing qualification (procedure and individual) are completed before brazing on TRC. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 22 | Gettelfinger, Geoff | Chrzanowski, Jim | Use of FM Lasoer Radar is at the conceptual planning level. This is not "In the Bag! |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 23 | Cole, Mike | Chrzanowski, Jim | Consider vacuum only impregnation. |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 24 | Heitzenroeder, Phil | Chrzanowski, Jim | Provide an in-line electrical test at the insulated cable to check for copper "wiskers". |  | By 1/15/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 25 | Heitzenroeder, Phil | Chrzanowski, Jim | Define all in process, pre-VPI, and post VPI electrical tests and Peer Review to beginning of work. |  | By 1/15/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 1 | Zarnstorff, Mike | Reiersen, Wayne | Section 3.3.2: A) requirement for ground-loop detections out of scope, should be deleted. B) 3rd line: isn't this redundant with req't for single PT ground? |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 2 | Malinowski, Frank | Reiersen, Wayne | Appendix A. Is there instrumentation that will show success for each demonstration: If not, then tests are needed per the definition in 4.2 |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 3 | Malinowski, Frank | Reiersen, Wayne | 4.2 examination excludes use of instruments. We need an inspection approach that allows for special equipment. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 4 | Malinowski, Frank | Reiersen, Wayne | Appendix A, general terms such as "minimize" "fast" and "C fall rating" need more specific definitions. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 5 | Chrzanowski, Jim | Reiersen, Wayne | Section 3.3.2: I question whether the NCSX Project could disassembly/reassembly the machine, if a modular coil need replacement. A more realistic schedule or plan should be generated. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 6 | Neilson, Hutch | Reiersen, Wayne | 3.2.3 1st paragraph: "e…. consistent with the facility achieving a high level….." |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 7 | Neilson, Hutch | Reiersen, Wayne | All requirements should be verified by some combination of the methods presented No "N/A's" |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 8 | Neilson, Hutch | Reiersen, Wayne | Are the ref's scenario waveforms under configure control? What about the 3-coil assembly trajectory over the VV? |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 9 | Reiersen, Wayne | Reiersen, Wayne | Electrical design criteria should be added here (and perhaps in the GRD) |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 10 | Zarnstorff, Mike | Reiersen, Wayne | Section 3.2.3, the 75% availability is for the whole device, not the coils alone. The requirement here should come form the RAM plan. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 11 | Zarnstorff, Mike | Reiersen, Wayne | Section 3.2.3, should include a requirement for design features to ensure that the coils can be accurately positioned and actual position measured during assembly and operation |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 12 | Reiersen, Wayne | Reiersen, Wayne | Make the TDS an appendix to the SRD so it is a stand-alone dor. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 13 | Reiersen, Wayne | Reiersen, Wayne | References GRD requirements to show traceability |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 14 | Reiersen, Wayne | Reiersen, Wayne | QCM needs to correspond to requirements in this documents. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 15 | Zarnstorff, Mike | Reiersen, Wayne | Section 3.2.2, should include to co-wound sense coils. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 16 | Zarnstorff, Mike | Reiersen, Wayne | Section 3.2.2, we should check with Raki on whether he wants two feeds per MC circuit. Note: This is required for the C-site power option. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 17 | Zarnstorff, Mike | Reiersen, Wayne | In section 3.2.1.2, 4th sentence: should state what vessel back out temperature this holds for (350ºC). |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 18 | Zarnstorff, Mike | Reiersen, Wayne | In section 3.2.1.2, the 1st sentence: should state that the coils should be held at 80ºK for the full range of vacuum vessel operating temperatures (˜20º - 250ºC). |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 19 | Zarnstorff, Mike | Reiersen, Wayne | Section 2.3 should include the NCSX GRD |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 20 | Reiersen, Wayne | Reiersen, Wayne | Remove autoclave (all tooling) requirements from SRD. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 21 | Chrzanowski, Jim | Reiersen, Wayne | 3.2.2 In revolving facility autoclave requirement modify statement - should read. Heat assemblies from RT to 50º C in 4 hrs, 50º C to 110º C in 5 hrs. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 22 | Reiersen, Wayne | Reiersen, Wayne | Consideration should be given to organizing the requirements around machine states i.e. (the functional flaw diagram) in Section 3. |  | By 1/31/2005
MC SRD Spec. Review Cognizant Engineer - Dave Williamanson | 2004-03-31 | 23 | Reiersen, Wayne | Reiersen, Wayne | Applicable documents (Section 2) should identify all and only those documents referenced in this SRD. |  | By 1/31/2005
MC Winding Pack Peer Review Cognizant Engineer - Dave Williamson | 2004-03-19 | 1 | Neilson, Hutch | Williamson, Dave | There is significant uncertainty in the achievable copper cross-section, due to : Keystoning, twist deformation, waviness of the chill plates, squishiness of the insulation Recommendation: go ahead with twisted racetrack based on current design. Do not make changes that would delay. |  | Resolve by PDR
MC Winding Pack Peer Review Cognizant Engineer - Dave Williamson | 2004-03-19 | 2 | Reiersen, Wayne | Williamson, Dave | Show the location of the magnetic loops in winding pack |  | Resolve by PDR
MC Winding Pack Peer Review Cognizant Engineer - Dave Williamson | 2004-03-19 | 3 | Reiersen, Wayne | Williamson, Dave | Why are the 14 mil. (lateral and 32 mil. (radial) shims adequate? The 14 mil. shim looks small just based on conductor tolerances. Consider re-optimizing conductor aspect ratio and shim thickness or even re-size the conductor. |  | Resolve by PDR
MC Winding Pack Peer Review Cognizant Engineer - Dave Williamson | 2004-03-19 | 4 | Reiersen, Wayne | Williamson, Dave | Mold release the tee before applying the chill plates. Move the kapton from the tee onto the back of the chill plate to isolate the chill plate from the tee. |  | Resolve by PDR
MC Winding Pack Peer Review Cognizant Engineer - Dave Williamson | 2004-03-19 | 5 | Reiersen, Wayne | Williamson, Dave | Fill in radius at the base of the tee prior to applying mold release to avoid locking the winding to the tee. |  | Resolve by PDR
MC Winding Pack Peer Review Cognizant Engineer - Dave Williamson | 2004-03-19 | 6 | Reiersen, Wayne | Williamson, Dave | Consider removing French toast after potting so the coil behaves as modeled (or show it is inconsequential) |  | Resolve by PDR
MC Winding Pack Peer Review Cognizant Engineer - Dave Williamson | 2004-03-19 | 7 | Dahlgren, Fred | Williamson, Dave | Verify that cu cooling tubes are electrically isolated from each other and ground (e.g. the tee) |  | Resolve by PDR
MC Winding Pack Peer Review Cognizant Engineer - Dave Williamson | 2004-03-19 | 8 | Raftopoulos, Steve | Williamson, Dave | Will not be able to maintain a 0.100 inch gap between chill plates unless they are custom wedge-shaped or tapered. If we have to do this custom shaping in the field it will be very time consuming. |  | Resolve by PDR
VV Structrual Analysis Peer Review Cognizant Engineer - Fred Dahlgren | 2004-04-22 | 1 | Neilson, Hutch | Goranson, Paul | How do we document what model was analyzed? Need to associate the model version with an identifier. |  | Resolve by PDR
VV Structrual Analysis Peer Review Cognizant Engineer - Fred Dahlgren | 2004-04-22 | 2 | Goranson, Paul | Goranson, Paul | Add a doublers or criss-cross rib to reduce the max deflection on the shell such that the deflections at the ends of the parts are ok (part 2 and 9) |  | Resolve by PDR
VV Structrual Analysis Peer Review Cognizant Engineer - Fred Dahlgren | 2004-04-22 | 3 | Reiersen, Wayne | Dahlgren, Fred | Build local model of port extension to get a better picture of the stresses where the port extensions attach to the shell. |  | Resolve by PDR
VV Structrual Analysis Peer Review Cognizant Engineer - Fred Dahlgren | 2004-04-22 | 4 | Reiersen, Wayne | Goranson, Paul | Consider thickening the thickness of the turret and port extensions to being peak stresses below allowable (375ºc) of 25ksi esp. around ports 15 and 18. |  | Resolve by PDR
VV Structrual Analysis Peer Review Cognizant Engineer - Fred Dahlgren | 2004-04-22 | 5 | Reiersen, Wayne | Goranson, Paul | Do our clearance calculations accommodate the max. deflections at the end of the port extensions? What allowance was made? |  | Resolve by PDR
VV Structrual Analysis Peer Review Cognizant Engineer - Fred Dahlgren | 2004-04-22 | 6 | Reiersen, Wayne | Goranson, Paul | Weld efficiency. Determine allowables based on non-radiographed welds. |  | Resolve by PDR
VV Structrual Analysis Peer Review Cognizant Engineer - Fred Dahlgren | 2004-04-22 | 7 | Reiersen, Wayne | Goranson, Paul | Unbalances pressure loads also need to be considered. |  | Resolve by PDR
Coil Test Facility Plumibing FDR Cognizant Engineer - Geoff Gettelfinger | 2004-11-10 | 1 | Perry, Erik | Gettelfinger, Geoff | Relief valves vent into the room, oxygen deficiency potential must thoroughly evaluated. |  | Resolve prior to final installation and commissioning
Coil Test Facility Plumibing FDR Cognizant Engineer - Geoff Gettelfinger | 2004-11-10 | 2 | Levine, Jerry | Gettelfinger, Geoff | IH needs at least 1 week notice before the foaming operation begins to complete preparations to support this activity. Note that the results of the surveys will take 1-2 weeks to complete. |  | Resolve prior to final installation and commissioning
Coil Test Facility Plumibing FDR Cognizant Engineer - Geoff Gettelfinger | 2004-11-10 | 3 | Levine, Jerry | Gettelfinger, Geoff | Comments on the CTF Hazards Analysis must be resolved, and the document must be approved by the Safety Review Committee (SRC) prior to commencing CTF operations. |  | Resolve prior to final installation and commissioning
Coil Test Facility Plumibing FDR Cognizant Engineer - Geoff Gettelfinger | 2004-11-10 | 4 | Kalish, Mike | Gettelfinger, Geoff | For upper pressure control use a pressure regulator/control valve (offers finer control and smaller control band than RV) |  | Resolve prior to final installation and commissioning
Coil Test Facility Plumibing FDR Cognizant Engineer - Geoff Gettelfinger | 2004-11-10 | 5 | Nelson, Brad | Gettelfinger, Geoff | Make adjustable relief valve visible/audible to tell when it is venting |  | Resolve prior to final installation and commissioning
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski | 2003-06-12 | 1 | Reiersen, Wayne | Williamson, Dave | Verify that existing NEPA and WP cover the handling of cryogens and powering of test coils.
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski | 2003-06-12 | 2 | Reiersen, Wayne | Williamson, Dave | Add engough instrumentation to verify our thermal and stress analysis-- looks tight now.
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski | 2003-06-12 | 3 | Kalish, Mike | Williamson, Dave | Determine forces on clamp bolts and verfiy factor of safety with respect to pull out strength
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski | 2003-06-12 | 4 | Reiersen, Wayne | Williamson, Dave | Need to finalize design of clamps -- not clear that we have a desggin that works.
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski | 2003-06-12 | 5 | Reiersen, Wayne | Williamson, Dave | Consider going back to the half-lapped insulation if that is likely to be the reference design.
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski | 2003-06-12 | 6 | Nelson, Brad | Williamson, Dave | Try winding inside / outside turn rather than layer by layer
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski | 2003-06-12 | 7 | Heitzenroeder, Phil | Williamson, Dave | Suggest investigatin < half-lapped insulation for R&D program to verify "armadillo- effect".
Racetrack Coil FDR Cognizant Engineer - Jim Chrzanowski | 2003-06-12 | 8 | Raftopoulos, Steve | Williamson, Dave | Consider thermocouple buried in the base of the tee. This would measure any heat going into the casting.
VV Weld Joint R&D Plan Peer Review Cognizant Engineer - Mike Viola | 2004-03-25 | 1 | Nelson, Brad | Viola, Mike | Add TC Instrumentation to the back side of the Spool Piece test to monitor the temperature during the weld.
VV Weld Joint R&D Plan Peer Review Cognizant Engineer - Mike Viola | 2004-03-25 | 2 | Goranson, Paul | Viola, Mike | Perform a visual inspection of the root pass of the welds
VV Weld Joint R&D Plan Peer Review Cognizant Engineer - Mike Viola | 2004-03-25 | 3 | Goranson, Paul | Viola, Mike | Insulate the backside of the weld with microtherm to determine if there are any burning issues with the insulation during the test
VV Weld Joint R&D Plan Peer Review Cognizant Engineer - Mike Viola | 2004-03-25 | 4 | Zarnstorf, Mike | Viola, Mike | Is there a flux that can be used to make Inconel weld flow better
VV Weld Joint R&D Plan Peer Review Cognizant Engineer - Mike Viola | 2004-03-25 | 5 | Heitzenroeder, Phil | Viola, Mike | Anneal pieces before welding to ensure it's in a similar condition to the
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 1 | Perry, Erik | Cole, Mike | Need to demonstrate that adequate clearance among and between all the components exists during final assembly. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 2 | Perry, Erik | Cole, Mike | Need to document the assembly tooling requirements and demonstrate that they are reasonable and achievable and that budget exists to pay for them. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 3 | Perry, Erik | Cole, Mike | Document locations for all tooling balls. Document need for in-process sensors (motion, proximity, etc.) |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 4 | Perry, Erik | Cole, Mike | Document assembly requirements for the base support structure. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 5 | Erik Perry | Cole, Mike | Document assembly plan in a signed-off final assembly document. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 6 | Brown, Tom | Cole, Mike | Cryostat base needs to be on the field period before they are put together. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 7 | Gettelfinger, Geoff | Cole, Mike | Explain risk management approach for the almost inevitable insulation pinches. Is this a minor issue? |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 8 | Dudek, Larry | Cole, Mike | Need to develop a method to localize a vacuum leak in the field joint so that it can be repaired. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 9 | Simmons, Bob | Cole, Mike | Per Peer Review, current weight of filed period is 78,000 lbs. Significantly greater than current crane capability. Upgrade to crane is not in scope at this time. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 10 | Heitzenroeder, Phil | Cole, Mike | Establish a "weight coordinator" to watch that field period lift weight stays within crane limits. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 11 | Heitzenroeder, Phil | Cole, Mike | Develop an electrical and coolant coil test plan integrated with machine assembly. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 12 | Heitzenroeder, Phil | Cole, Mike | Verify lift-over clearance for solenoid is adequate. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 13 | Perry, Erik | Cole, Mike | WBS 7 should be reviewed to assure that sufficient resources and schedule exist for the multiple levels (PFA joining, port extensions, NB duct, etc) of leak checking called out in plan. |  | Resolve prior to PDR
Final Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-04-15 | 14 | Perry, Erik | Cole, Mike | Tom Brown's presentation on spool piece to clamp minimum clearance indicated that the spool piece would need to be supported by a cantilevered arm to rotate it into position. Will the stress on the spool piece weld be acceptable? |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 1 | Dudek, Larry | Cole, Mike | Need to have Viola and Chrzanowski review schedule in detail for timing of fixture deliveries with mockups and training. |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 2 | Chrzanowski, Jim | Cole, Mike | Where are the TF Coils sub-assemblies going to be assembled? The west side of the Test Cell is available, but the overhead crane won't reach. |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 3 | Viola, Mike | Cole, Mike | Identify weights of each assembly component and completed assembly. |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 4 | Neilson, Hutch | Cole, Mike | Schedule for Jobs 1808/1810 -Where is the mag. Sensor installation in the schedule? -Where is fit-check of mod-coil subassemblies in the schedule? -bake out temperature: Job P1-201 says 150º C change to 350º C+ to account for heating and cooling costs. -The additional parts needs to be accounted for in the schedule and tooling design. (Also, applies to WBS7) -Where are mockups costs? Some of these were answered in the talks. | Resource-Loaded Schedules updated? | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 5 | Dudek, Larry | Cole, Mike | Should perform a tolerance analysis (vs. tolerance budget) to determine if the tolerances required are achievable with the manufacturing and assembly processes selected. Would also serve as a map to troubleshoot the assembly process if it is determined that it is not achievable |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 6 | Neilson, Hutch | Cole, Mike | 1) Identify lay down and storage area for all components and completed sub-assemblies 2) If schedule changes such that parts accumulate, is a problem? |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 7 | Neilson, Hutch | Cole, Mike | At some point, the field period assembly trajectory needs to be under configuration control. |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 8 | Viola, Mike | Cole, Mike | What is the flammability of Microtherm concern is sparks from welding. |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 9 | Viola, Mike | Cole, Mike | The platform needs to address the safety access to the 20' difference in elevation needed for access for insulation and welding. |  | Resolve prior to PDR
Field Period Assembly Plan Peer Review Cognizant Engineer - Mike Cole | 2004-03-30 | 10 | Dudek, Larry | Cole, Mike | Need to look at deflection of parts/as fixture during assembly. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 1 | Johnson, Dave | Goranson, Paul | Consider making an intermediate port connection on all circular ports, with the joint just outboard of the modular coil. Consider making the extension tubes out of stainless. Consider an assembly strategy which would permit removal and replacement of extension tube at future date. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 2 | Majeski, Rich | Goranson, Paul | Present run of RF parts does not enter the vessel near enough to the ends at the antenna to allow a connection. RF parts need to be revisited. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 3 | Brown, Tom | Goranson, Paul | Needs to reposition the PF 5 leads (or rotate coil) to eliminate lead interference with Port 16. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 4 | Brown, Tom | Goranson, Paul | Reposition port #13, its too close to the TF winding. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 5 | Zarnstorff, Mike | Goranson, Paul | Consider unifying ports 9 and 13 to avoid interference during bake, to reduce costs. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 6 | Zarnstorff, Mike | Goranson, Paul | Near port 9, does the TF support structure have to be this large and come this close to the port? Can the edge of the support structure be pulled back? |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 7 | Zarnstorff, Mike | Goranson, Paul | Consider stepping the diameter of port 3 to a larger diameter tube outside the modular coils. This would allow a larger angle of view of the oblate cross-section (a region that has limited access). |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 8 | Zarnstorff, Mike | Goranson, Paul | In the regions of very close proximity between vessel and coils, what instrumentation should be built into the structure to allow monitoring so that bake out does not endanger the coils. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 9 | Zarnstorff, Mike | Goranson, Paul | On the NB Port: the internally bolted joints must be (somehow) designed so that each bolt does not become a virtual leak. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 10 | Heitzenroeder, Phil | Goranson, Paul | Include (consider) the port tolerances in the minimum clearance study |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 11 | Gettelfinger, Geoff | Goranson, Paul | Port 16 vs. # small bolts issue (interference?) |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 12 | Gettelfinger, Geoff | Goranson, Paul | Resolve bake out clearances at Port 4. Can diag stand a lesser port size? |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 13 | Dudek, Larry | Goranson, Paul | Work out the assembly sequence of the NB transition duct internal seal. (Can a man make it up from the inside) |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 14 | Gettelfinger, Geoff | Goranson, Paul | Further consider port NB joint detail. Bolted joint with seal weld? |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 15 | Gettelfinger, Geoff | Goranson, Paul | Consider beam geometry with port NB, all OK? |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 16 | Viola, Mike | Goranson, Paul | Have all system interfaces been reviewed? Are services other than diagnostic e.q., (RF, NB) been consulted? |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 17 | Viola, Mike | Goranson, Paul | This design represents # port additions of about 30% to the previous design. Besides the obvious installation of the ports there is additional insulating cooling tubes, assembly alignment etc. Is this cost budgeted? |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 18 | Viola, Mike | Goranson, Paul | Consider joining adjacent circular ports into one oval shape if there is any advantage |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 19 | Gettelfinger, Geoff | Goranson, Paul | Be wary of conflate seal leaks due to thermal gradients across the copper. Sandia and PPPL have had failures. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 20 | Viola, Mike | Goranson, Paul | Check clearances between welds of adjacent tubes. You will get a significant amount of distortion. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 21 | Viola, Mike | Goranson, Paul | The additional ports virtually "use up" any spare locations where diamond wire cutting could occur. An alternative method of cutting the vessel is needed |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 22 | Gettelfinger, Geoff | Goranson, Paul | What is the project's position on Inconel vs. SS port extrusions? Pick one and document the decision. |  | Resolve prior to PDR
VV Ports Peer Review Cognizant Engineer - Mike Cole | 2004-01-29 | 23 | Heitzenroeder, Phil | Goranson, Paul | Re-orient rather than re-locate or re-sizing to address tight clearances. (This is ok with diagnostics) |  | Resolve prior to PDR
TF Coil Peer Review Cognizant Engineer - Mike Kalish | 1904-01-25 | 1 | Nelson, Brad | Kalish, Mike | Thermo-hydraulic analyses need to be documented. |  | Resolve prior to PDR
TF Coil Peer Review Cognizant Engineer - Mike Kalish | 1904-01-25 | 2 | Viola, Mike | Kalish, Mike | What is the risk during cool down due to different expansion coefficients |  | Resolve prior to PDR
TF Coil Peer Review Cognizant Engineer - Mike Kalish | 1904-01-25 | 3 | Viola, Mike | Kalish, Mike | Does this add additional weight? What is the new total weight of 120 º field period. |  | Resolve prior to PDR
TF Coil Peer Review Cognizant Engineer - Mike Kalish | 1904-01-25 | 4 | Reiersen, Wayne | Kalish, Mike | Check the impact of out-of -plane defamations on resonant field errors. |  | Resolve prior to PDR
TF Coil Peer Review Cognizant Engineer - Mike Kalish | 1904-01-25 | 5 | Gettelfinger, Geoff | Kalish, Mike | The insulate -after-shaving and after ground-wrapping must be demonstrated by development program due to high risk. |  | Resolve prior to PDR
TF Coil Peer Review Cognizant Engineer - Mike Kalish | 1904-01-25 | 6 | Reiersen, Wayne | Kalish, Mike | Consider ways of soliciting vendor input on how to fabricate the coil assembly and on the vendor scope. |  | Resolve prior to PDR
TF Coil Peer Review Cognizant Engineer - Mike Kalish | 1904-01-25 | 7 | Reiersen, Wayne | Kalish, Mike | Check structural calculations modeling of wedge region is not accurate and up-down asymmetries are suspicious. |  | Resolve prior to PDR
Conventional Coil TF Stress Analysis Cognizant Engineers - Mike Kalish & Len Myatt | 2004-04-01 | 1 | Reiersen, Wayne | Kalish, Mike | Quantify material properties for our specific epoxy- insulation systems. |  | Resolve prior to PDR
Conventional Coil TF Stress Analysis Cognizant Engineers - Mike Kalish & Len Myatt | 2004-04-01 | 2 | Reiersen, Wayne | Kalish, Mike | Review design criteria especially with respect to very local regions of high stress. |  | Resolve prior to PDR
Conventional Coil TF Stress Analysis Cognizant Engineers - Mike Kalish & Len Myatt | 2004-04-01 | 3 | Reiersen, Wayne | Kalish, Mike | Investigate the use of 3D glass to lower thermal cool down stresses. |  | Resolve prior to PDR
Conventional Coil TF Stress Analysis Cognizant Engineers - Mike Kalish & Len Myatt | 2004-04-01 | 4 | Reiersen, Wayne | Kalish, Mike | Add leads to analysis plan. |  | Resolve prior to PDR
Conventional Coil TF Stress Analysis Cognizant Engineers - Mike Kalish & Len Myatt | 2004-04-01 | 5 | Neilson, Hutch | Kalish, Mike | Are there any issues with leads and coolant feeds? Historically these are a common failure site. |  | Resolve prior to PDR
Conventional Coil TF Stress Analysis Cognizant Engineers - Mike Kalish & Len Myatt | 2004-04-01 | 6 | Kalish, Mike | Kalish, Mike | Look at test Data and determine if a lower modulus can be used as well as if there is an indication of a soft plastic region in the .02% strain range. |  | Resolve prior to PDR
Conventional Coil TF Stress Analysis Cognizant Engineers - Mike Kalish & Len Myatt | 2004-04-01 | 7 | Kalish, Mike | Kalish, Mike | Consider testing for thermal cycling with coil samples. |  | Resolve prior to PDR
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 1 | Neilson, Hutch | Reiersen, Wayne | Location of the inconel-to-stainless transition joint and requirements for diagnostic flexibility need to be captured somewhere. Is it an interface or flowed down from the GRD? |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 2 | Brown, Tom | Reiersen, Wayne | What sets the VV insulation thickness? Is there a reference in the interface section or do you state that the insulation is 1" thick. |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 3 | Zarnstorff, Mike | Reiersen, Wayne | Section 3.2.1.2.1.2 or section 3.2.1.3.2 needs to recognize the GRD requirement to operate with the 250ºC liner (for lithium OP), presumably by operating with the vessel at 250ºC |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 4 | Zarnstorff, Mike | Reiersen, Wayne | Need a metrology requirement requiring that design features be incorporated to enable accurate measurement of the vessel position during assembly and in the assembled state during operation. |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 5 | Reiersen, Wayne | Reiersen, Wayne | Need to look at consequences of loss of site power, loss of heating/cooling , etc., see any requirements derived from this? |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 6 | Reiersen, Wayne | Reiersen, Wayne | Resolve issue of "what is possible" i.e. horizontal and vertical design loads. |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 7 | Reiersen, Wayne | Reiersen, Wayne | Organize 3.13 as a stand-alone section, not along WBS lines. |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 8 | Malsbury, Judy | Reiersen, Wayne | Section 3.3.1.4: NCSX structural & cryogenic design criteria is a draft & almost 2 yrs. old. Valid reference? |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 9 | Malsbury, Judy | Reiersen, Wayne | Section 3.3.1.2 b) standards for degreases & cleaning. |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 10 | Malsbury, Judy | Reiersen, Wayne | ( paragraph 2) add all docs ref'd in body of spec. |  | By 1/31/2005
VV SRD Spec. Review Cognizant Engineer - Paul Goranson | 2004-04-01 | 11 | Simmons, Bob | Reiersen, Wayne | Revise GRD to clarify pre-pulse temp. 20-60 ºC following pulse. Uniformities of temp required on VV? |  | By 1/31/2005
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 1 | Raki Ramakrishnan | Ramakrishnan, Raki | 1)The distance between top of one tray to the top of another tray shall be 18". This leave a clearance of 12" between trays for trapping etc. 2) Distance between one horizontal tray to another. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 2 | Raki Ramakrishnan | Ramakrishnan, Raki | Verify whether the FCPC side wall can carry the load of 600#/ft. of the tray system. Also, determine the maximum side lad that can be imposed to see as to what factor of safety is provided. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 3 | Raki Ramakrishnan | Ramakrishnan, Raki | What is the cost impact if the number of support structures are reduced by increasing the span. Can we adopt a design with a span of minimum 50' so that the number of supports are reduced. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 4 | Zarnstorff, Mike | Ramakrishnan, Raki | Where is the detailed drawing for the structure bridging between towers of types 1 and 2? |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 5 | Zarnstorff, Mike | Ramakrishnan, Raki | On drawings S1/1 Bridge Elevation, the diagonal bracing shown for the bridges does not correspond with that shown on drawings S3 and S4 (the angles are clearly different) |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 6 | Zarnstorff, Mike | Ramakrishnan, Raki | On drawings S2/6 "Typical Bracing Detail", where does this detail apply? This does not correspond to the bracing for the Tray support towers shown on drawings S2. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 7 | Zarnstorff, Mike | Ramakrishnan, Raki | On drawings S3 and S4, no dimensions are specified for a) the vertical columns. b) the height of the concrete caissons above grade . c) the horizontal separation between the caissons . Drawings S4/2 "Bridge Section" does not show the horizontal bracing, |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 8 | Zarnstorff, Mike | Ramakrishnan, Raki | On drawings S6/1 "Building Section", it is not clear what is new and what is existing. Also, the method for attaching the new structure to the building is not specified or detailed. Also: How will the building penetration be sealed (needed to prevent) |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 9 | Zarnstorff, Mike | Ramakrishnan, Raki | Why must the large bridge (drawing S4) be so much broader (˜ 8 feet between pillars) that the small bridge ( ˜4 feet between pillars, drawings S3 ? |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 10 | Zarnstorff, Mike | Ramakrishnan, Raki | The present design uses 4 different types of cable support platforms (with different widths etc. ) and four different tower types (ignoring Support type 3) in the straight part of the run. Why such a complicated design? Why not do it all with 60' to 70' |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 11 | Zarnstorff, Mike | Ramakrishnan, Raki | Presently, the trays are supported on a raised beam, mounted above the bridging structures, as shown on drawings S4/2 and S3/2. Why not make these cross-pieces part of the bracing structure, set between the side beams, and lay the bottom trays directly . |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 12 | Jones, Frank | Ramakrishnan, Raki | Contractor to document underground discrepancies and feed back information to client |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 13 | Jones, Frank | Ramakrishnan, Raki | Note: that the existing bridge has a clearance of 19'3". Should new bridge equal this clearance? |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 14 | Jones, Frank | Ramakrishnan, Raki | Tube steel ex. 4x2x 1/4 for tray support is unorthodox. Revise design to incorporate a material compatible with tray manufactures mounting clamps. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 15 | Jones, Frank | Ramakrishnan, Raki | Tray support spacing appears to exceed NEMA 20C capacity Review/Revise as appropriate to comply snow/ice load in calculations. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 16 | Jones, Frank | Ramakrishnan, Raki | Tray support size is short. Ex. Provide 40" minimum for a 36' tray and support clamps. Note: that tray flange is out on "Cope" ladder tray. Provide addition support length for RUN variation. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 17 | Jones, Frank | Ramakrishnan, Raki | Support system has no provision for fittings and vertical riser support - see tray manufactures specification for fitting requirements. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 18 | Jones, Frank | Ramakrishnan, Raki | 4/0 bare at column bridge must be tied to building grid when in the proximity of building or fence (existing requirement) |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 19 | Jones, Frank | Ramakrishnan, Raki | 1-1/c 1000 mcm cables should have overall jacket to aid cable pull, provide added protection and maintain twist spacing. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 20 | Oliaro, Gary | Ramakrishnan, Raki | Please see attached requirements for fiber and copper cables required for WBS5. Three points: 1. Prevent droops and resolve bending -see attached. 2. Allow space for growth. 3. Follow all pull spec for fiber. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 21 | Ilic, Alic | Ramakrishnan, Raki | C-site underground infrastructure is old and not well documented, so location of tower is critical to be documented in details, long time before final drawings. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 22 | Malinowski, Frank | Ramakrishnan, Raki | Several calculations and analysis have been mentions. All should be complied and documented. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 23 | Neilson, Hutch | Ramakrishnan, Raki | Before contract is awarded, determine funding source for the extra tray being added to support control cables WBS 4 or 5? |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 24 | Neilson, Hutch | Ramakrishnan, Raki | *Ensure that Safety Management plans are documented in the contract SOW. * Ensure that adequate day-to-day oversight is provided by PPPL. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 25 | Potensky, Carl | Ramakrishnan, Raki | High strength bolts are specified. Suspect bolts controls are required & cost increase & controls must be budgeted. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 26 | Potensky, Carl | Ramakrishnan, Raki | Do the support braces have the proper clearances from the road etc. example S-3 Bridge Section |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 27 | Potensky, Carl | Ramakrishnan, Raki | Any digging greater than 12" requires PPPL digging permit/hole. The digging permit will govern how the hole will be dug. Manholes will have to be hand dug & GPR required, etc. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 28 | Levine, Jerry | Ramakrishnan, Raki | Need to incorporate site seismic and wind loads into the design of the structure. Also snow and ice loads should be considers. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 29 | Levine, Jerry | Ramakrishnan, Raki | Burns should provide calculations of the loadings of this new structure on existing buildings (FCPC and Power Building). In general, all load calculations should be review by PPPL. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 30 | Van Kirk, Rick | Ramakrishnan, Raki | Trays mounted on square tubing is unconventional for standard hold-down clamps. How are trays going to be held down. Will this be acceptable for expansion hold down clamps also? |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 31 | Van Kirk, Rick | Ramakrishnan, Raki | 1.Trays shall be supported per manufacturer's specs. This does not appear to be the case. Radius tray @ 1/20. 2. Manufacturer recommended support at 2; both sides of thermal contractions of expansion joints. Where do these take place? Show on drawing prop. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 32 | Van Kirk, Rick | Ramakrishnan, Raki | Width of all supports need to be increased to accommodate hold-down clamps. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 33 | Van Kirk, Rick | Ramakrishnan, Raki | Distance between tray elevation needs to increase to 18" from bottom of one tray to bottom of another tray. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 34 | Van Kirk, Rick | Ramakrishnan, Raki | Liner support dimensions for tray inadequate - spacing too long. Manufactures' recommended spacing for said load plus snow and ice load should be followed. Nema 20C = 20' spacing at 100#/ft. We are more near? Lbs../ft. see chit #15 |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 35 | Jones, Frank | Ramakrishnan, Raki | Electrical notes and details are inadequate for tray installation. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 36 | Lacenere, John | Ramakrishnan, Raki | Maintenance access after bridge construction. Can all existing systems be accessed for repair/replacement? Especially neutral beam transformers at C-site and pump house? |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 37 | Lacenere, John | Ramakrishnan, Raki | Final design structure shall support (13) duplexed 1000 mcm cables total weight of cable per circuit is approximately 9#/ft. Therefore cable weight is 13*9 = 117#/ft. My concern is the structure for supporting the cable tray & cables alone FCPC Building. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 38 | Lacenere, John | Ramakrishnan, Raki | Too many elevation changes of cable tray between FCPC building and C-site. The NEC allows for 360 degrees of total bends between pull points. PPPL allows for maximum of 270 degrees between pull points. Also the maximum bending radius for duplex 1000 mcm is approximately 28-30". Better details for tray supports per tray manufacture's need to be shown. Especially y on bends and turns. More supports are required at turns and bends. Details for fabrication of and/or fasteners for tray. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 39 | Wise, Art | Ramakrishnan, Raki | Clearance of north side of C-site pump house double doors for equipment removal with structure passing right above loading dock. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 40 | Ramakrishnan, Raki | Ramakrishnan, Raki | Caisson in MOAT will need to be increased 6' deeper because gravel in moat is 5' deep. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 41 | Ramakrishnan, Raki | Ramakrishnan, Raki | Caisson TS4 will have to be moved west so that it does not interfere with existing transformer footing and support base. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 42 | Ramakrishnan, Raki | Ramakrishnan, Raki | Caisson TS3 and TS6 are blocking access to Sub-18 (for vehicle etc.) |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 43 | Ramakrishnan, Raki | Ramakrishnan, Raki | Drawing S1 does not show location of 13.8 kV duct bank |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 44 | Ramakrishnan, Raki | Ramakrishnan, Raki | Drawing S1 does not show location of 5kV system that goes to C-site pump house. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 45 | Ramakrishnan, Raki | Ramakrishnan, Raki | Drawing S1 does not show 2, 400 V street lighting system at D-site and clearance. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 46 | Ramakrishnan, Raki | Ramakrishnan, Raki | Drawing S1 does not show 480 V and phone cable system above ground and it's clearance. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 47 | Ramakrishnan, Raki | Ramakrishnan, Raki | The spacing between trays needs to be increased to a minimum of 12" from top of rail of lower tray to bottom of upper tray. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 48 | Ramakrishnan, Raki | Ramakrishnan, Raki | Reduce the number of drops in the tray system to reduce cable side wall forces. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 49 | Wise, Art | Ramakrishnan, Raki | There is a possible code violation where tray system passes through Sub-18 since it has nothing to do with Sub-18. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 50 | Ramakrishnan, Raki | Ramakrishnan, Raki | Burns Group to insure that cable pulling (six duplexed cable 2-1/c-1000mcm) in each of the trays can be performed per Tray & Cable manufacture's recommendations and per standard industry practice. |  | Must be resolved prior to machine installation in test cell
RF Shielding Requirements Peer Review Cognizant Engineer - Raki Ramakrishnan | 2004-04-21 | 51 | Ramakrishnan, Raki | Ramakrishnan, Raki | Provide 1-C-500mcm bare copper cable in each tray. This cable shall be grounded at both ends. Each tray section shall also be attached to the ground cable. |  | Must be resolved prior to machine installation in test cell
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.1 | Malsbury, Judy | Reiersen, Wayne | Documents are in draft form that should have been finalized. | SEMP, SRDs are being finalized and will be signed by mid-January. Criteria docs already signed and posted. | By 1/31/2005 (Revised from 12/17/2004)
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.2 | Malsbury, Judy | Simmons, Bob | The Configuration Management Plan and supporting guides and procedures will be reviewed and revised to incorporate 3D models | The ProE/INTRALINK system has a very disciplined process of handling revisions to drawings and models and this is being followed EXACTLY since ProE/INTRALINK will not permit otherwise. What has not been adequately done is to fully document this in NCSX documentation. The current version of the CMP addresses this and PROC-007 and the ProE/INTRALINK Users Guide will be modified. However, any inference that there is no system is incorrect. | By 1/15/2005 (Revised from 12/17/2004)
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.3 | Malsbury, Judy | Simmons, Bob | NCSX-PROC-004 will be revised to eliminate configuration item identification. | The Project response made it very clear that “the formal practice of configuration identification has never been done and should not be required.” PROC-004 is in the process of being revise to clarify what is a Configuration Item and should be finalized in early January, but it will NOT include any attempt to define each and every CI. | By 1/31/2005 (Revised from 12/17/2004)
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.4 | Malsbury, Judy | Simmons, Bob | Concerns were expressed about the relationship between the Ops Center and the NCSX Records Mgmt System | Both the DMP and the SEMP have been revised to clarify the relationship between the Ops Center and the NCSX Records Management System. Both documents are in final review and will be posted for signature next week. | By 1/31/2005 (Revised from 12/17/2004)
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.5 | Malsbury, Judy | Tyrrell, Marriane | The status of all chits from the design reviews for the MCWF and VVSA FDR will be reviewed. | A consolidated tracking log for all CHITs has been developed and is in the process of being statused. A revised disposition status and copy of this CHIT Tracking Log will be available next week (e.g.,, completed, planned for next design review , expected completion date, etc.). | By 1/31/2005 (Revised from 12/17/2004)
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.6 | Malsbury, Judy | Tyrrell, Marriane | All open chits will have milestones associated with them by which the chit should be closed. NCSX plans and procedures will be appropriately modified to reflect this practice. | NCSX Procedure 004 ready for signature. NCSX Engineering Administrator will use newly developed CHIT/Audit Finding Tracking Log to follow-up with WBS Managers and responsible engineers. | By 1/31/2005 (Revised from 12/17/2004)
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.7 | Malsbury, Judy | Malsbury, Judy | Concern with timely statusing and closure of CHITs. | See response to finding 1.6. J. Malsbury to verify that corretive action is being accomplished. | By 5/31/2005
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.8 | Malsbury, Judy | Malsbury, Judy | Concern with timely statusing and closure of CHITs. | See response to finding 1.6. J. Malsbury to verify that corretive action is being accomplished. | By 5/31/2005
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.9 | Malsbury, Judy | Simmons, Bob | Concerns with NCSX Design Review processing of chits | Systems Engineering Support Manager will obtain Head Engineering and Technical Infrastructure concurrence on NCSX-PROC-004 | By 1/31/2005 (Revised from 12/17/2004)
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.11 | Malsbury, Judy | Reiersen, Wayne | Design basis calculations for the MCWF were not all finalized and approved. | All will be formally documented and checked in analysis reports by the Comprehensive Modular Coil FDR. | By 3/5/2005
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.12 | Malsbury, Judy | Reiersen, Wayne | Recommendation made that plans and procedures be streamlined. | All plans and procedures for design control will be reviewed and modified as appropriate (not finalized). | By 1/28/2005
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.13 | Malsbury, Judy | Simmons, Bob | Recommendation made that plans and procedures be streamlined. | A peer review of these plans and procedures will be held. | By 2/25/2005
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 1.14 | Malsbury, Judy | Simmons, Bob | Recommendation made that plans and procedures be streamlined. | The plans and procedures for design control will be finalized using the output of the peer review. | By 3/25/2005
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 2.1 | Malsbury, Judy | Simmons, Bob | Training on the NCSX systems for design control has not been defined or provided. | COMPLETED. REV 1 ISSUED IN EARLY DECEMBER. | COMPLETED
QA Audit # 0406 NCSX Design Control Lead Auditor: Judy Malsbury | 2004-11-17 | 2.2 | Malsbury, Judy | Simmons, Bob | Training on the NCSX systems for design control has not been defined or provided. | Training will be provided to all project personnel involved in design control activities. | By 5/19/2005
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 1 | Barmes, Dori | Chrzanowski, Jim | A joint Management/ACC final walkdown of the facility be conducted. | Agreed. The project will schedule a final walkdown as soon as the facility is ready.
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 2 | Barmes, Dori | Chrzanowski, Jim | The ACC believes it would be prudent to assure that the issues affecting each stage are addressed prior to commencing that stage. | Agreed. The ATI (Chrzanowski) will obtain formal concurrence from the RLM prior to each stage. The concurrence will be documented in the form of an e-mail or memo. The Project Manager (Neilson) and Engineering Manager (Reiersen) will be copied on the correspondence.
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 3 | Barmes, Dori | Chrzanowski, Jim | NCSX procedures are not necessarily in accordance with PPPL established methodologies. Specifically: (1) Change control is not addressed (2) No ATI is specifically identified (3) Existing PPPL Procedures currently exist do not address the TRC, but are generalized to the production facility (4) Facility specific procedures and plans are in draft form; they should be reviewed and signed off (5) Emergency response during operations does not appear to be addressed in the current documentation. | Agreed. NCSX will update the Configuration Management Plan to address change control for manufacturing procedures. NCSX will request that PPPL Engineering consider revising ENG-030 to address manufacturing procedures.NCSX will use signed procedure; the ATI will be identified; and procedures will be developed and controlled in the pattern of PPPL installation procedures which are governed by ENG-030. An emergency response procedure will be developed. Training in procedures (especially the emergency response procedure) will be addressed. Training needs will be identified. Training needs will be incorporated in the NCSX Training Plan. | By 1/31/2005
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 4 | Barmes, Dori | Chrzanowski, Jim | The Work Planning Form, identified on the JHA’s (#1138) does not address the TRC operation. Is there a WPF specifically for the TRC | WP 1188 is specifically designed for TRC fabrication. NO ACTION REQUIRED. | COMPLETED
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 5 | Barmes, Dori | Chrzanowski, Jim | The JHA’s are in draft and should be reviewed and signed off prior to operations. This includes signing by all people who will perform the work, per ESH-004. | JHAs will be initially approved by the ATI, RLM, and IH. Field changes will be made by the ATI or technicians and used as part of the pre-job briefings. Conformance of our intended practice will be checked with ESH-004.
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 6 | Barmes, Dori | Chrzanowski, Jim | Non-conformances should be addressed. Are there currently any outstanding NCR’s? The chain-of-command/disposition of NCR’s has not been established and documented. | One NCR for the TRC (3602) was generated and closed. NCR's will be processed in accordance with PPPL procedures. Supervisor approval will be by the RLM. The Engineering Department Head (Williams) will have the final approval authority. NO ACTION REQUIRED. | COMPLETED
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 7 | Barmes, Dori | Chrzanowski, Jim | Metrology requirements are not clarified in documentation, e.g., calibration requirements/traceability to NIST, Roamer arm capabilities, critical measurements, etc. | Metrology requirements will de defined in the manufacturing procedures and supporting documentation. Specific metrology procedures will be developed on an as required basis.
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 8 | Barmes, Dori | Dudek, Larry | Many of the chits generated at the FRD related to operational procedures and would need to be resolved before operational procedures could be finalized. | Operational procedures will require the concurrence of the RLM that relevant chits have been addressed to the degree required for that stage of operation.
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 9 | Barmes, Dori | Chrzanowski, Jim | Training Matrix is incomplete, e.g., The matrix is not approved and HR/Training Department is not on approval review/sign-off. Other training requirements to consider for inclusion are: Metrology, Procedures, Firewatch, etc. | Training requirements will be determined by the ATI. Training requirements will be documented in the TRC training matrix which will be separately approved (ATI, RLM, and HR) and incorporated in NCSX Training Plan.
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 10 | Barmes, Dori | Chrzanowski, Jim | None of the four technicians slated to perform this work have all of the listed required training. | None of the technicians need to have all of the listed required training. The ATI will ensure that the technicians performing the work will have the required training for the tasks they perform.
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 11 | Barmes, Dori | Chrzanowski, Jim | One of the training requirements is for a course that has not yet been developed (Coil Lead Brazing). | A braze qualification procedure will be developed and approved.
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 12 | Barmes, Dori | Chrzanowski, Jim | The requirement for Field Supervision during TRC manufacturing is identified but does it provide adequate coverage? For “initial” operations, more uncertainty exists, making it prudent to assure the strongest level of field supervision is available. Field Supervisors should also be available to focus their efforts on this task without the distraction of other concurrent assignments. | Adequate field supervision will be provided. Sufficient manpower has been allocated. NO ACTION REQUIRED. | COMPLETED
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 13 | Barmes, Dori | Chrzanowski, Jim | Fire Protection needs final review/approval of Jeanes. Determination of requirements for Fire Extinguishers to be established and Fire Extinguishers to be located as required. | Jeanes has already provided the required guidance which will be implemented. | COMPLETED
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 14 | Barmes, Dori | Chrzanowski, Jim | Flame permits are not yet issued for the TRC. | Flame permits are issued on a daily basis and will be obtained in a timely manner. NO ACTION REQUIRED. | COMPLETED
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 15 | Malsbury, Judy | Chrzanowski, Jim | The standing platforms at the winding station should be reviewed by IH for tripping hazard and remediated as appropriate. | A 3rd platform is being provided. Railings are not required. Management/ACC walkdown (See item #1) will verify this. NO ACTION REQUIRED. | COMPLETED
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 16 | Malsbury, Judy | Chrzanowski, Jim | The “clean room” for TRC operations is not complete. Is it complete enough for safe initial operations? | It is ready. Management/ACC walkdown (See item #1) will verify this. NO ACTION REQUIRED. | COMPLETED

## By Responsible Person
Review/QA Audit # | Date of Review or Audit | Chit/Audit Finding | CHIT Author | Person Responsible for Resolution | Chit/Audit Summary | Status | Due Date
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 3 | Reiersen, Wayne | Chrzanowski, Jim | Provide schedule for demonstrating measurement capability required for TRC winding. TRC not even measured yet. | During the real time measuring of a layer [that will be performed (3) times during winding], it adds an additional 3-4 hours to the winding time per measurement series. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 5 | Reiersen, Wayne | Chrzanowski, Jim | Need to figure out how to dissect coil w/o losing registration of winding to tee. Consideration should be given to more exotic, non-destructive options. | The winding clamps will remain on the coil/casting during the cutting operations. This should help to restrain the bundle to tee registration during dissection. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 6 | Reiersen, Wayne | Chrzanowski, Jim | Consider winding a complete coil to establish shimming requirements. Then rewind the coil using differences in clamping pressure to control boundary. | Agree. The TRC trial winding was completed. Evaluation of results will determine whether or not trial windings will be performed for types A, B and C. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 7 | Reiersen, Wayne | Chrzanowski, Jim | Resolve whether the relief gets filled with RTV or Roving. (Roving would mechanically lock the winding which may not be good). | The TRC grooves were sealed with "Thenoseal" caulking. This caulking will prevent the epoxy from locking the winding. The groove has been eliminated on Type A,B,C castings. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 8 | Levine, Jerry | Chrzanowski, Jim | Lead blocks - it was mentioned during the presentation that this would be made of G10 or G11. For production coil, since G10 tends to become neutron-activated cause "hot spots" (Doe commend use of G11, not G10. Similarly for any other proposed uses of G | All of the lead fillers for the production coils will be fabricated using G-11. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 9 | Dudek, Larry | Chrzanowski, Jim | Need to qualify the sil-foil carbon tong Braze procedure or write an exception. | Process has been qualified and is now a part of the PPPL welding/brazing procedure. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 10 | Stratton, Brent | Chrzanowski, Jim Re-assign to Geoff Gettlefinger/ Diagnostic Group | Measure signal in diagnostic flux loops while coil is energized. Check conformity of flux loops after coil fabrication is complete. Verify that center conductors of loop cables will not shorted to ground or other coil structures. | Flux loop leads are provided. Diagnostic group must provide/coordinate instrumentation required to perform such measurements. Diagnostic group should coordinate with Geoff Gettlefinger for possible incorporation in the test plans. | TBD
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 11 | Stratton, Brent | Chrzanowski, Jim | The diagnostic flux loops need to be accurate, located (~1/16") at the outer "corners" of the winding pads! A groove should be put it into the surface on which the loop should be used to accurately, measure the path of each loop as-built | Investigating the possibility of using simple inexpensive gauge pads to position the flux loops. Further work is required. | By 1/30/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 12 | Gettelfinger, Geoff | Chrzanowski, Jim | Provide epoxy strainer on fluid line to coil distribution manifold. | Epoxy filters have been aded to epoxy delivery system. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 13 | Dudek, Larry | Chrzanowski, Jim | Additional potential issue: 1) cladding and chill plates too time consuming. | The installation of the cladding appears workable, however additional hands-on work along with redesign efforts is required prior to determining the actual installation and fabrication cost & schedule. | By 1/30/2005
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 14 | Brown, Tom | Chrzanowski, Jim | Add to the assembly procedure the electrical tests required to assure that no shorts are present in the copper coolant system. | Test has been added. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 15 | Dudek, Larry | Chrzanowski, Jim | Use a conductivity meter or some other device to monitor the resistance to ground (MCWF) during chadding installation. | Agreed. This test is incorporated in the procedure during installation of cladding. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 15 | Nelson, Brad | Chrzanowski, Jim | Take lots of pictures. | Concur. New camera has been procured for the field. This camera will be used by all field crews during fabrication. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 16 | Nelson, Brad | Chrzanowski, Jim | Consider using fiber optic strain gages. | Agreed. These will be incorporated in the TRC per FDR recommedations. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 17 | Nelson, Brad | Chrzanowski, Jim | Consider renting another Romer arm for 3rd winding station. | Agree. The need for the 3rd. Romer will be evaluated once two winding lines are operational. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 18 | Nelson, Brad | Chrzanowski, Jim (should reassign to ORNL) | Develop an insulation schematic to show what is connected. |  | TBD
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 19 | Nelson, Brad | Chrzanowski, Jim | Use a grounded paddle to check for wiskers. | Device has been fabricated and will be tested on the TRC. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 20 | Nelson, Brad | Chrzanowski, Jim | Electical insulation looks marginal. | The turn to turn insulation plan has been reviewed and has deemed appropriate | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 21 | Malsbury, Judy | Chrzanowski, Jim | Assure resistive brazing qualification (procedure and individual) are completed before brazing on TRC. | See chit #9 | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 22 | Gettelfinger, Geoff | Chrzanowski, Jim | Use of FM Lasoer Radar is at the conceptual planning level. This is not "In the Bag! | This is not being planned. NO ACTION REQUIRED | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 23 | Cole, Mike | Chrzanowski, Jim | Consider vacuum only impregnation. | Disagree: The VPI procedures are based on R&D activities and will include a combination of both vacuum and pressure. These decisions will be made during the VPI operation at the discretion of the VPI Directror. | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 24 | Heitzenroeder, Phil | Chrzanowski, Jim | Provide an in-line electrical test at the insulated cable to check for copper "wiskers". | See chit #19 | COMPLETED Approved by Larry Dudek
Twisted Racetrack Coil FDR Cognizant Engineer - Dave Willimanson | 2004-10-15 | 25 | Heitzenroeder, Phil | Chrzanowski, Jim | Define all in process, pre-VPI, and post VPI electrical tests and Peer Review to beginning of work. | Agreed. This has been added in the manufacturing procedures. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 1 | Barmes, Dori | Chrzanowski, Jim | A joint Management/ACC final walkdown of the facility be conducted. | Agreed. The project will schedule a final walkdown as soon as the facility is ready. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 2 | Barmes, Dori | Chrzanowski, Jim | The ACC believes it would be prudent to assure that the issues affecting each stage are addressed prior to commencing that stage. | Agreed. The ATI (Chrzanowski) will obtain formal concurrence from the RLM prior to each stage. The concurrence will be documented in the form of an e-mail or memo. The Project Manager (Neilson) and Engineering Manager (Reiersen) will be copied on the approval. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 3 | Barmes, Dori | Chrzanowski, Jim | NCSX procedures are not necessarily in accordance with PPPL established methodologies. Specifically: (1) Change control is not addressed (2) No ATI is specifically identified (3) Existing PPPL Procedures currently exist do not address the TRC, but are g | Agreed. The modular coil manufacturing procedures have been updated in accordance with ENG-030. This includes procedure change control as outlined in the laboratory procedure. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 4 | Barmes, Dori | Chrzanowski, Jim | The Work Planning Form, identified on the JHA’s (#1138) does not address the TRC operation. Is there a WPF specifically for the TRC | WP 1188 is specifically designed for TRC fabrication. NO ACTION REQUIRED. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 5 | Barmes, Dori | Chrzanowski, Jim | The JHA’s are in draft and should be reviewed and signed off prior to operations. This includes signing by all people who will perform the work, per ESH-004. | JHAs will be initially approved by the ATI, RLM, and IH. Field changes will be made by the ATI or technicians and used as part of the pre-job briefings. Conformance of our intended practice will be checked with ESH-004. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 6 | Barmes, Dori | Chrzanowski, Jim | Non-conformances should be addressed. Are there currently any outstanding NCR’s? The chain-of-command/disposition of NCR’s has not been established and documented. | One NCR for the TRC (3602) was generated and closed. NCR's will be processed in accordance with PPPL procedures. Supervisor approval will be by the RLM. The Engineering Department Head (Williams) will have the final approval authority. NO ACTION REQUIRED | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 7 | Barmes, Dori | Chrzanowski, Jim | Metrology requirements are not clarified in documentation, e.g., calibration requirements/traceability to NIST, Roamer arm capabilities, critical measurements, etc. | Metrology requirements will be defined in the manufacturing procedures and supporting documentation. Specific metrology procedure (D-NCSX-MCF-005) addresses the metyrology (Romer arm) usage. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 9 | Barmes, Dori | Chrzanowski, Jim | Training Matrix is incomplete, e.g., The matrix is not approved and HR/Training Department is not on approval review/sign-off. Other training requirements to consider for inclusion are: Metrology, Procedures, Firewatch, etc. | Training requirements will be determined by the ATI. Training requirements will be documented in the TRC training matrix which will be separately approved (ATI, RLM, and HR) and incorporated in NCSX Training Plan. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 10 | Barmes, Dori | Chrzanowski, Jim | None of the four technicians slated to perform this work have all of the listed required training. | None of the technicians need to have all of the listed required training. The ATI will ensure that the technicians performing the work will have the required training for the tasks they perform. Marianne Tyrrell will coordinate the individuals required training with HR. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 11 | Barmes, Dori | Chrzanowski, Jim | One of the training requirements is for a course that has not yet been developed (Coil Lead Brazing). | See chit #9 | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 12 | Barmes, Dori | Chrzanowski, Jim | The requirement for Field Supervision during TRC manufacturing is identified but does it provide adequate coverage? For “initial” operations, more uncertainty exists, making it prudent to assure the strongest level of field supervision is available. Fiel | Adequate field supervision will be provided. Sufficient manpower has been allocated. NO ACTION REQUIRED. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 13 | Barmes, Dori | Chrzanowski, Jim | Fire Protection needs final review/approval of Jeanes. Determination of requirements for Fire Extinguishers to be established and Fire Extinguishers to be located as required. | R. Jeanes has already provided the required guidance which will be implemented. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 14 | Barmes, Dori | Chrzanowski, Jim | Flame permits are not yet issued for the TRC. | Flame permits are issued on a daily basis and will be obtained in a timely manner. NO ACTION REQUIRED. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 15 | Malsbury, Judy | Chrzanowski, Jim | The standing platforms at the winding station should be reviewed by IH for tripping hazard and remediated as appropriate. | A sheving unit placed at the edge of the platforms provides adequate protection for accidently stepping off platform. Barrier railings are not required. Management/ACC walkdown (See item #1) has verified this. NO ACTION REQUIRED. | COMPLETED Approved by Larry Dudek
ACC Review of Manufacturing Facility - Station #2 Cognizant Engineer Engineer - J. Chrzanowski | 2004-10-21 | 16 | Malsbury, Judy | Chrzanowski, Jim | The “clean room” for TRC operations is not complete. Is it complete enough for safe initial operations? | It is ready. Management/ACC walkdown (See item #1) will verify this. NO ACTION REQUIRED. | COMPLETED Approved by Larry Dudek