## Sheet1
| Rate | per Hr
| EM | 159
| SM | 101.5
| TB | 93
| DM | 98
TASK DESCRIPTION | Start | Completion | Working | EAEM | EAEM | EMSM
| Date | Date | Days | Chrz | Raft | meighan
|  |  |  | 70% | 50% | 100%
Engineering and Oversight | 2005-03-01 | 2005-05-16 | 54 | 302.4 | 216 | 432
|  |  |  | 48081.6 | 34344 | 43848 |  |  | 126273.6
Station No. 2- TRC Coil Winding |  |  |  | No. tech.s | No. of shifts | hours | Qty | Tot. hours
Complete winding and measuring | 2005-03-01 | 2005-03-15 | 11 | 2 | 2 | 352 | 1 | 352
Final coil winding activities | 2005-03-16 | 2005-03-19 | 4 | [5 empty] | 480
Complete groundwrap installation | 2005-03-07 | 2005-03-10 | 4 | 2 | 2 | 128 | 1 | 128 | 44640
Station No. 2- Final coil prep & Mold Application |  |  | 23 | Total working days per coil
Install outer Diagnostic loops | 2005-03-21 | 2005-03-21 | 1 | 2 | 2 | 32 | 1 | 32
Install chill plates | 2005-03-22 | 2005-03-31 | 9 | 2 | 2 | 288 | 1 | 288
Joule Milestone #2 | 2005-03-31
Perform pre-VPI elect. & pressure tests | 2005-04-01 | 2005-04-01 | 1 | 1 | 2 | 16 | 1 | 16
Pressure test cryo lines
Perform preliminary electrical tests | [8 empty] | 528
Install bag mold around modular coil | 2005-04-04 | 2005-04-19 | 12 | 1 | 2 | 192 | 1 | 192 | 49104
VPI Coil |  |  | 12 | Total working days per coil
Transfer TRC to Autoclave & prepare for VPI | 2005-04-20 | 2005-04-25 | 4 | 1 | 3 | 96 | 1 | 96
VPI modular coil | 2005-04-26 | 2005-05-03 | 8
Vacuum pumpdown mold and autoclave |  |  | 1 | 1 | 3 | 24 | 1 | 24
Epoxy fill coil |  |  | 1 | 3 | 3 | 72 | 1 | 72
Temperature rampup and Cure |  |  | 1 | 3 | 2 | 48 | 1 | 48
[parallel activity] Station cleanup during cure |  |  | 1 | 1 | 2 | 16 | 1 | 16
Temperature rampup and Post cure |  |  | 1 | 2 | 2 | 32 | 1 | 32
Temperature rampdown |  |  | 1 | 1 | 1 | 8 | 1 | 8 | 328
Cleanup & ready autoclave |  |  | 2 | 1 | 2 | 32 | 1 | 32 | 30504
Post VPI
Complete coil preps following VPI activities | 2005-05-04 | 2005-05-13
Cleanup & install final clamps |  |  | 8 | 1 | 2 | 128 | 1 | 128 | 128
11904
Warm Electrical Test |  |  | 1
Perform electrical & Pressure Tests | 2005-05-16 | 2005-05-16 | 1 | 1 | 2 | 16 | 1 | 16 | 16
Warm tests (room temperature) only | [8 empty] | 1488
| 44640 | Coil Wind
| 49104 | Pre VPI
| 30504 | VPI
| 11904 | Post VPI
| 45180 | M&S
| 126273.6 | Engr & Oversight
| 1488 | Warm test
| 309093.6 | Total
Material & Supplies | M&S |  |  | Machinist | Tech
| w/o G&A |  |  | SM | TB
Coil clamps (30) | 9000
Rework leak blocks |  |  |  | 200 | 120
Chill plates |  |  |  |  | 40
Miscellaneous | 1000
Totals | 10000 |  |  | 200 | 160 |  |  | Total | 45180
|  |  |  | 20300 | 14880