## Sheet1
NCSX Bill of Materials tracking list | [18 empty] | Assembly schedule/plan (Primavera Job number 9450-1***-1451)
Account | Description |  |  |  | Job Manager |  |  |  | Specification
9450-1***-1408 | Modular coil Type C winding components |  |  |  | J.Chrzanowski |  |  |  | NCSX-CSPEC-142-05-00 | [9 empty] | Assy Step | Primavera | Start Date | TASK DESCRIPTION | Work Shifts Req'd | Shifts | Shifts Planned | Working | No. of | Hours per | Cum working days
Item/Part info | [6 empty] | Status | [12 empty] | Task |  |  |  | per day | per day | Days | Tech. | Shift
Item | Assy Illustration page # (FDR-Fogarty) | Dwg/Document # | Part / Item # | Assy dwg # | Quantity per Coil | Units | Dwg Released for Fab | RESPONSIBLE | Purchase Status/Comments | Quantity Ordered | Req Number or PPPL woirk request | PO # | Vendor | Cost | Forecast delivery | Req'd delivery date | Receipt Inspection | Assy Step |  | #
Stud welding gun assy |  | n/a | [9 empty] | CC |  | 1650 |  | 2005-10-07
Temp winding clamp studs | 2 | ? | [5 empty] | Meighan | [9 empty] | 1-03 | 0-0 |  | 2005-09-23 | Receive C-1 Modular coil casting | [6 empty] | 0 |  | 2005-08-22 |  | holidays
Base plate support studs | 8 |  |  |  | 2 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-001 |  | Station No. 1- Casting Preparation | 19 | Total working days |  | 19 | [6 empty] | 2005-09-05
Base plate support stud nuts (0.375") | 9 |  |  |  | 2 |  |  | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 | 1-0 | P1-001 | 2005-09-27 | Drill 4 holes for cooling tubes @ poloidal break | 2 |  | 1 | 2 | 2 | 8 | 2 | 32 |  |  | 2005-11-24
Base plate insulator (0.0625") | 9 | SE-142C-211 |  |  | 1 |  |  | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 | 1-01 | P1-001 | 2005-09-30 | Mount casting in ring | 3 | 1 | 1 | 3 | 2 | 8 | 5 | 48 |  |  | 2005-11-25
G-11 for lead blocks for first coil only | [7 empty] | Chrzanowski |  |  |  | PE005914 | Total Plastics | 2995 | Delivered | Delivered |  | 1-05.1 |  | P1-001 |  | Position and mount casting to support ring | [7 empty] | 0 |  |  | 2005-12-23
G-11 for lead blocks for balance of coils | [7 empty] | Chrzanowski | [10 empty] | 1-02 | P1-001 | 2005-10-04 | Inspect casting | 2 | 1 | 1 | 2 | 2 | 8 | 7 | 32 |  |  | 2005-12-26
Lower winding blocks Side A | 3 | SE142C-134 |  |  | 1 |  | Yes | Dudek | Ordered for C-1 and C-2 only | 2 |  | PE005952 | JP Pattern | 3700 | Delivered | 2005-10-12 |  | 1-05.1 |  | P1-001 |  | Dimensional measure winding face | [7 empty] | 0 |  |  | 2005-12-27
" " " |  | " " |  |  |  |  | Yes | Dudek | For C-3 thru C-6 | 4 | R403063 | PE006055 | JP Pattern | 9220 | 2005-11-10 |  |  |  |  | P1-001 |  | Inspect surfaces for flaws, etc. | [7 empty] | 0 |  |  | 2005-12-28
Lower winding blocks Side B | 3 | SE142C-135 |  |  | 1 |  | Yes | Dudek | Ordered for C-1 and C-2 only | 2 |  | PE005952 | JP Pattern | 3700 | Delivered | 2005-10-12 |  | 1-05.1 |  | P1-001 |  | Electrically check poloidal break | [7 empty] | 0 |  |  | 2005-12-29
" " " |  | " " |  |  |  |  | Yes | Dudek | For C-3 thru C-6 | 4 | R403063 | PE006055 | JP Pattern | 9220 | 2005-11-10 |  |  |  | 1-03 | P1-001 | 2005-10-07 | Install studs for winding clamps | 3 | 1 | 1 | 3 | 2 | 8 | 10 | 48 |  |  | 2005-12-30
lower winding block positioning bushings | 3 | SE142C-192 |  |  | 4 |  |  |  | No longer required | [6 empty] | 2005-10-12 |  | 1-05.1 |  | P1-001 |  | Position and weld studs for winding and coil clamps | [7 empty] | 0 |  |  | 2006-01-02
lower winding block positioning threaded studs | Design change |  |  |  | 4 |  |  | Meighan | [10 empty] | 1-04 | P1-001 | 2005-10-10 | Clean casting | 1 | 1 | 1 | 1 | 2 | 8 | 11 | 16
lower winding block mounting bolts | 3 | ? |  |  | 4 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-001 |  | Clean casting using acceptable solvents | [7 empty] | 0
Upper winding block Side A | 4 | SE142C-136 |  |  | 1 |  | Yes | Dudek | Ordered for C-1 and C-2 only | 2 |  | PE005997 | JP Pattern | 4000 | 2005-09-09 | 2005-10-12 |  | 1-05.1 |  | P1-001 |  | Inspect and clean all threaded holes | [7 empty] | 0
" " " |  | " " |  |  |  |  | Yes | Dudek | for coils C-3 thru C-6 | 4 |  | PE006055 | JP Pattern | 9220 | 2005-11-10 |  |  |  | 1-05.1 | P1-001 | 2005-10-12 | Temp install upper/lower winding blocks and top plate & lead hardware | 2 |  | 1 | 2 | 2 |  | 13 | 32
Upper winding block Side B | 4 | SE142C-137 |  |  | 1 |  | Yes | Dudek | Ordered for C-1 and C-2 only | 2 |  | PE005997 | JP Pattern | 4000 | 2005-09-09 | 2005-10-12 |  | 1-05.1 | 1-05.2 | P1-001 | 2005-10-20 | Install inner cladding plates | 6 | 1 | 1 | 6 | 4 | 8 | 19 | 192 | 400
" " " |  | " " |  |  |  |  | Yes | Dudek | for coils C-3 thru C-6 | 4 |  | PE006055 | JP Pattern | 9220 | 2005-11-10 |  |  |  |  | P1-011 |  | Coil Winding Station 2 and 3 | 53 | Total working days per coil |  | 26.5
upper winding block bushing | 4 | SE142C-223 |  |  | 1 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 | 2-01 | P1-011 | 2005-10-20 | Prepare coil for winding | 12 |  |  | 6 |  |  |  | 0
upper winding block mounting bolts | 4 | ? |  |  | 4 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-011 |  | Install coil in turning fixture | 1 | 1 | 2 | 0.5 | 3 | 8 | 19.5 | 24
Top plate Tee bolt | 5 | ? |  |  | 1 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-011 |  | Install/set winding clamps sides A & B | 2 | 1 | 2 | 1 | 2.5 | 8 | 20.5 | 40
Top Plate mounting bolts | 5 | ? |  |  | 14 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-011 |  | Position inner groundwrap insulation onto winding form (sides A & B) | 9 | 1 | 2 | 4.5 | 2.5 | 10 | 25 | 180
Temporary jig blocks for winding block | 6 | ? |  |  | 8 |  |  |  | No longer required | [6 empty] | 2005-10-12 |  | 1-05.1 | 2-02 | P1-011 | 2005-10-31 | Wind Side "A" | 17 |  |  | 8.5 |  |  |  | 0
Base plate mounting bolts (0.375") | 10 | 150049 |  | SE-142C-050 | 6 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-011 |  | Position & secure 1st. coil lead set | 2 | 1 | 2 | 1 | 2.5 | 8 | 26 | 40
Terminal Lug bolts | 20 | 150050 |  | SE-142C-050 | 4 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-011 |  | Type C-Wind layer #1 - [10] turns of conductors onto casting (4-in-hand) (Lacing + 2shifts) | 13 | 1 | 2 | 6.5 | 2.5 | 10 | 32.5 | 260
Jumper mounting studs (0.375") | 11 | 150062 |  | SE-142C-050 | 3 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-011 |  | Position & secure 2nd. coil lead set | 2 | 1 | 2 | 1 | 2.5 | 8 | 33.5 | 40
Terminal lug nuts | 20 | 150260 |  | SE-142C-050 | 4 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 | 2-03 | P1-011 | 2005-11-10 | Prepare station for Side "B" | 1 |  |  | 0.5 |  |  |  | 0
Copper rod for connector cone fabrication 1" dia |  |  |  |  | 80 | ft |  | Chrzanowski | Out for quote. INSUFFICIENT quantity for all 18 coils. Need add'l 15 ft. |  | 403009 & 403098 | PE006033 | Capital Steel | 2725 | 2005-09-23 |  |  |  |  | P1-011 |  | Reposition coil | 1 | 1 | 2 | 0.5 | 3 | 8 | 34 | 24
Conductor connector cone bolts | 26 | 150262 |  | SE-142C-050 | 16 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 | 2-04 | P1-011 | 2005-11-11 | Wind Side "B" | 17 |  |  | 8.5 |  |  |  | 0
Conductor connector cone Bellville washers | 26 | NS151359 |  | SE-142C-050 | 32 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-011 |  | Position & secure 1st. coil lead set | 2 | 1 | 2 | 1 | 2.5 | 8 | 35 | 40
Jumper Lug Connector Side B |  | SE-142C- 057 |  | SE-142C-050 | 1 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-011 |  | Type C-Wind layer #1 - [10] turns of conductors onto casting (4-in-hand) (lacing +2shifts) | 13 | 1 | 2 | 6.5 | 2.5 | 10 | 41.5 | 260
Base plate (Temp stereolithograph piece) | 10 | SE-142C-047 |  | SE-142C-050 | 1 |  |  | Fogarty | for first coil only to size and position leads | [6 empty] | 2005-10-12 |  | 1-05.1 |  | P1-011 |  | Position & secure 2nd. coil lead | 2 | 1 | 2 | 1 | 2.5 | 8 | 42.5 | 40
Base plate | 10 | SE-142C-047 |  | SE-142C-050 | 1 |  |  | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 | 2-05 | P1-011 | 2005-11-29 | Final coil winding activities Complete groundwrap installation | 6 | 1 | 2 | 3 | 2.5 | 10 | 45.5 | 120 | 1068
Jumpers (Temp stereolithograph) | 13,15,16,17 | SE142C-054,053,052 & 051 |  | SE-142C-050 | 4 |  |  | Fogarty | for first coil only to size and position leads | [5 empty] | 2005-08-19 | 2005-10-12 |  | 1-05.1 |  | P1-020 |  | Final coil prep & Mold Application (Station 2 & 3) | 22 | Total working days per coil |  | 22
Jumpers | 13,15,16,17 | SE142C-054,053,052 & 051 |  | SE-142C-050 | 4 |  | Yes | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 | 2-06 | P1-020 | 2005-12-01 | Install outer Diagnostic loops | 2 | 1 | 1 | 2 | 2 | 8 | 47.5 | 32
Base plate threaded inserts (0.375") | 10 | SE-142C-047 |  | SE-142C-050 | 7 |  |  | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 | 2-07 | P1-020 | 2005-12-19 | Install chill plates & Tubing | 12 | 1 | 1 | 12 | 2.5 | 10 | 59.5 | 240
Jumper insulator (0.125") | 14,15,16, | SE-142C-049 |  | SE-142C-050 | 3 |  |  | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 | 2-08 | P1-020 | 2005-12-20 | Perform pre-VPI elect. & pressure tests | 1 | 1 | 1 | 1 | 2 | 8 | 60.5 | 16
Terminal Lug Side A | 20 | SE-142C-055 |  | SE-142C-050 | 1 |  |  | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-020 |  | Pressure test cryo lines | [7 empty] | 0
Terminal Lug Side B | 20 | SE-142C-056 |  | SE-142C-050 | 1 |  |  | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-020 |  | Perform preliminary electrical tests | [7 empty] | 0
Jumper Lug Connector Side A |  | SE-142C-058 |  | SE-142C-050 | 1 |  |  | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 | 2-09 | P1-020 | 2006-01-03 | Install bag mold around modular coil | [7 empty] | 0
Conductor connector cones | 25, 60 | SE-142C-059 |  | SE-142C-050 | 16 |  | Yes | Chrzanowski | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-020 |  | Install silicone bag & sprues | 3 | 1 | 1 | 3 | 2.5 | 8 | 63.5 | 60
Flat Washer |  | SE-142C-062 |  | SE-142C-050 | 7 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-020 |  | Vacuum pumpdown & leak repair | 2 | 1 | 1 | 2 | 2.5 | 8 | 65.5 | 40
Flat Washer |  | SE-142C-063 |  | SE-142C-050 | 14 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-020 |  | Install epoxy shell | 2 | 1 | 1 | 2 | 2.5 | 8 | 67.5 | 40 | 428
Hex Hd bolt |  | SE-142C-064 |  | SE-142C-050 | 4 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-021V |  | VPI Activities (Station 5) | 16 | Total working days per coil |  | 12
Conductor connector cone flat washers | 26 | SE-142C-065 |  | SE-142C-050 | 16 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 | 5-01 | P1-021V | 2006-01-10 | Transfer modular coil to Autoclave | 1 | 1 | 1 | 1 | 3 | 8 | 68.5 | 24
Cooling tube connectors | ? | SE-142C-066 |  | SE-142c-050 | 2 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-021V | [9 empty] | 0
Socket Hd Screw |  | SE-142C-067 |  | SE-142C-050 | 22 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 | 5-02 | P1-021V | 2006-01-13 | Prepare modular coil for VPI | 3 | 1 | 1 | 3 | 3 | 8 | 71.5 | 72
Insulating washer |  | SE-142C-068 |  | SE-142C-050 | 6 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 |  | P1-021V |  | (Connect fill lines, manifolds, hookup thermocouples & leak check) | [7 empty] | 0
Jumper mounting stud insulating sleeves | 12 | SE-142C-069 |  | SE-142C-050 | 3 |  |  | Meighan | [7 empty] | 2005-10-12 |  | 1-05.1 | 5-03 | P1-021V | 2006-01-17 | VPI modular coil | [7 empty] | 0
Side A Lower cladding | 22 | SE-142C-384-101-295 |  |  | 195 |  |  | Dudek | PPPL fabrication complete for C-1 | 195 | [5 empty] | 2005-10-20 |  | 1-05.2 |  | P1-021V |  | Vacuum pumpdown & preheat mold and autoclave | 2 | 1 | 1 | 2 | 3 | 8 | 73.5 | 48
Side A Upper cladding | 22 | SE-142C-382-101-295 |  |  | 195 |  |  | Dudek | PPPL fabrication complete for C-1 | 195 | [5 empty] | 2005-10-20 |  | 1-05.2 |  | P1-021V |  | Epoxy fill coil | 2 | 2 | 2 | 1 | 3 | 8 | 74.5 | 48
Side B Lower cladding | 22 | SE-142C-484-101-295 |  |  | 195 |  |  | Dudek | PPPL fabrication complete for C-1 | 195 | [5 empty] | 2005-10-20 |  | 1-05.2 |  | P1-021V |  | Temperature rampup and Cure | 3 | 3 | 3 | 1 | 2 | 8 | 75.5 | 48
Side B Upper cladding | 22 | SE-142C-482-101-292 |  |  | 195 |  |  | Dudek | PPPL fabrication complete for C-1 | 195 | [5 empty] | 2005-10-20 |  | 1-05.2 |  | P1-021V |  | Temperature rampup and Post cure | 2 | 2 | 2 | 1 | 2 | 8 | 76.5 | 32
Groundwrap | 23 | [6 empty] | Meighan | COMPLETE | [6 empty] | 2005-10-20 |  | 2-01 |  | P1-021V |  | Temperature rampdown | 1 | 1 | 1 | 1 | 1 | 8 | 77.5 | 8
Winding Clamps | [7 empty] | Meighan | COMPLETE | [6 empty] | 2005-10-20 |  | 2-01 |  | P1-021V |  | Cleanup & ready autoclave | 2 | 1 | 1 | 2 | 3 | 8 | 79.5 | 48 | 328
Winding clamp bolts | [7 empty] | Meighan | COMPLETE | [6 empty] | 2005-10-20 |  | 2-01 |  | P1-021C |  | Post VPI Activities (Station 1) | 7 |  |  | 7
Lead Block Chill Plate side A | 36 | SE142C-183 |  | SE-142C-233 | 1 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07 | 6-01 | P1-021C | 2006-01-26 | Transfer modular coil from Autoclave to Station #1 | 1 | 1 | 1 | 1 | 3 | 8 | 80.5 | 24
Lead Block Chill Plate side B | 36 | SE142C-241 |  | SE-142C-233 | 1 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07 | 6-02 | P1-021C | 2006-01-31 | Finalize coil & install final coil clamps (40 to 50 clamps/per coil) | 3 | 1 | 1 | 3 | 2 | 8 | 83.5 | 48
Winding Block Top Plate | 36 | SE142C-184 |  | SE-142C-233 | 1 |  | Yes | Chrzanowski | For coils C-1 thru C-6 | 6 | R403059 | PE006052 | Eptam Plastics | 4860 | 2005-10-20 | 2005-12-19 |  | 2-07 | 6-03 | P1-021C | 2006-02-01 | Perform (room temperature) electrical & Pressure Tests | 1 | 1 | 1 | 1 | 2 | 8 | 84.5 | 16
Winding block side plates A | 35 | SE142C-220 |  | SE-142C-233 | 1 |  | Yes | Chrzanowski | For coils C-1 thru C-6 | 6 | R403059 | PE006052 | Eptam Plastics | 4860 | 2005-10-20 | 2005-12-19 |  | 2-07 | 6-04 | P1-021C | 2006-02-03 | Remove coil from ring assembly | 2 | 1 | 1 | 2 | 2 | 8 | 86.5 | 32 | 120
Winding block side plates B | 35 | SE142C-221 |  | SE-142C-233 | 1 |  | Yes | Chrzanowski | For coils C-1 thru C-6 | 6 | R403059 | PE006052 | Eptam Plastics | 4860 | 2005-10-20 | 2005-12-19 |  | 2-07
Lead block Side A tubing | 29 | SE-142C-201 |  | SE-142C-233 | 1 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07 | [12 empty] | 2344 | 42192
Lead Block Side B tubing | 29 | SE-142C-202 |  | SE-142C-233 | 1 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07
Winding block filler wedges A | 34 | SE-142C-226 |  | SE-142C-233 | 4 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07 | [11 empty] | 50% | 1172 | 3516
Winding block filler wedges B | 34 | SE-142C-227 |  | SE-142C-233 | 4 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07 | [11 empty] | 25% | 586 | 1758
Side A Lower Chill plates | 29 | SE-142C-388-101-292 |  |  | 182 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07 | [11 empty] | 10% | 234.4 | 703.2
Side A Upper Chill Plates | 29 | SE-142C-386-101-292 |  |  | 182 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07
Side B Lower Chill plates | 29 | SE-142C-486-101-292 |  |  | 182 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07 | [13 empty] | 48169.2
Side B Upper Chill Plates | 29 | SE-142C-488-101-292 |  |  | 182 |  |  | Chrzanowski | [7 empty] | 2005-12-19 |  | 2-07 | [11 empty] | shift diff |  | 2408.46
Tubing |  | UNS C10200 |  |  | 8 @ 15 ft | ft |  | Meighan | (try to purcahse pre-tinned) | [6 empty] | 2005-12-19 |  | 2-07
Diagnostic Loops | ? | [6 empty] | Stratton | [7 empty] | 2005-12-19 |  | 2-07
Vulcanizing Tape | 38 |  |  |  | ? | ft2 |  | Meighan | [7 empty] | 2006-01-03 |  | 2-09
Chopped glass (for cotton candy cover) | 38 |  |  |  | ? | ft2 |  | Meighan |  |  | CC |  |  | 115 |  | 2006-01-03 |  | 2-09
RTV-11 | 38 |  |  |  | ? |  |  | Meighan | Credit Card as req'd (finite shelf life) | [6 empty] | 2006-01-03 |  | 2-09
HiSol | 38 |  |  |  | ? |  |  | Meighan | [7 empty] | 2006-01-03 |  | 2-09
Epoxy Sprues | [7 empty] | Chrzanowski |  |  | R4003011 | PE006048 | Bitec | 9779 | 2005-09-12 | 2006-01-10 |  | 5-01
Brass Ball Valves | [7 empty] | Chrzanowski |  |  | R403026 |  |  | 7310 |  | 2006-01-10 |  | 5-01
Brass fittings | [7 empty] | Chrzanowski |  |  | R403038 | PE006029 | Jade Int'l | 9343 | 2005-09-01 | 2006-01-10 |  | 5-01
Fittings | [7 empty] | Chrzanowski |  |  |  | PE006030 | Jade Int'l | 5760
PVC fittings for VPI | [7 empty] | Chrzanowski |  |  | R403113 |  |  | 1225 |  | 2006-01-10 |  | 5-01
Bar Clamp horizontal |  | SE1405-276 |  | SE-142C-275P | 48 |  | ? | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-Treaded screw |  | -14 |  | SE-142C-275P | 96 |  |  | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-Cap screw |  | -13 |  | SE-142C-275P | 96 |  |  | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-flat washer |  | SE1405-274 |  | SE-142C-275P | 96 |  | ? | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-Bushing-spacer |  | SE1405-278 |  | SE-142C-275P | 48 |  | ? | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-swivel pad cover |  | SE1405-273 |  | SE-142C-275P | 96 |  | ? | Meighan | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-swivel pad clamp |  | SE1405-272 |  | SE-142C-275P | 96 |  | ? | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-clamp pad |  | SE1405-267 |  | SE-142C-275P | 96 |  | ? | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp- screws |  | -7 |  | SE-142C-275P | 48 |  |  | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-spherical convex washer |  | SE1405-263P |  | SE-142C-275P | 96 |  | ? | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-piston spherical concave |  | SE1405-277 |  | SE-142C-275P | 96 |  | ? | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-screw set |  | SE1405-261P |  | SE-142C-275P | 192 |  | ? | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Final Clamp-washer Bellville |  | SE1405-258P |  | SE-142C-275P | 768 |  | ? | Meighan | [7 empty] | 2006-01-31 |  | 6-02
Terminal Splice Lugs | 55 | SE142C-263 & 264 |  |  | 2 |  | ? | Chrzanowski | [7 empty] | 2006-01-31 |  | 6-02
Formulas:
Start Date = WORKDAY(X7,[Cum working days],AJ8:AJ17)
Start Date = WORKDAY(X7,[Cum working days, row below],AJ8:AJ17)