NCSX

Modular Coil Manufacturing Facility

Operations Plan

NCSX-PLAN-MFOP-00-01

October 21, 2004

Author: _______________________________________

James H. Chrzanowski- Coil Facility Manager

Reviewed By: _________________________________

Steve Raftopoulos- Field Supervisor

Reviewed By: _________________________________

Tom Meighan- Field Supervisor

Reviewed By: _________________________________

Judy Malsbury- NCSX QA Representative

Reviewed By: _________________________________

Jerry Levine- PPPL Safety Representative

Reviewed By: _________________________________

Bill Slavin- PPPL IH Representative

Approved By: _________________________________

Larry Dudek- RLM for Coil Facility

RECORD OF CHANGE

| Revision | Date | Description of Change |
| --- | --- | --- |
| 00 | 4/1/04 | Initial release |
| 01 | 10/26/04 | Update document to include 3-winding stations and the fabrication of Twisted Racetrack Coil |

TABLE OF CONTENTS

1	Introduction and Scope	- 1 -

1.1	Introduction	- 1 -

1.2	Scope	- 1 -

2	Applicable Documents	- 1 -

3	General Description of Modular Coils	- 2 -

4	Facilities and Work Stations	- 3 -

4.1	Facilities Description	- 3 -

4.2	Work Station Descriptions	- 3 -

5	Manufacturing Inspection & Test Plan (MIT)	- 5 -

6	Flow Plan of the Manufacturing Operations	- 5 -

7	Responsibilities during Manufacturing	- 6 -

7.1	Manufacturing Facility Manager	- 6 -

7.2	Field Supervisors	- 7 -

7.3	Lift Engineer	- 7 -

7.4	Coil Test Director	- 7 -

7.5	Lead Technicians	- 7 -

7.6	Field Crews	- 7 -

7.7	Health Physics Representative	- 7 -

7.8	Industrial Hygiene Representative	- 7 -

7.9	Construction Safety Representative	- 8 -

7.10	Quality Control Representative	- 8 -

8	General Facility Operating Guidelines	- 9 -

8.1	Field Supervisors	- 9 -

8.2	House-Keeping Rules	- 9 -

8.3	Hard hats	- 9 -

8.4	Station Logbook	- 9 -

8.5	Daily Summary Report	- 9 -

9	Safety and Training Requirements	- 10 -

9.1	Integrated Safety Management (ISM)	- 10 -

9.2	Job Hazard Analysis Surveys and Safety Meetings	- 10 -

9.3	Safety Walk-Through’s	- 10 -

9.4	Training	- 10 -

9.5	Personal Protective Equipment [PPE’s]	- 10 -

9.6	Emergency Response Procedure	- 11 -

10	Meetings and Communication	- 11 -

10.1	Daily Startup Meetings	- 11 -

10.2	Safety Meetings	- 11 -

10.3	Pre-Job Briefings	- 12 -

10.4	Post-Job Briefings	- 12 -

11	Documentation	- 12 -

11.1	Document Control	- 12 -

11.2	Coil Document Books  R1	                                                                           - 12 -

11.3	Documents Retention and Storage	- 12 -

12	Quality Assurance/Quality Control Requirements	- 13 -

12.1	Quality Control during Manufacturing	- 13 -

12.2	Measurements	- 13 -

12.3	Other Quality Control Representative Responsibilities	- 13 -

LIST OF FIGURES

Figure 1-Modular Coil Types	- 2 -

Figure 2 -NCSX Coil Manufacturing Facility	- 4 -

Figure 3- Flow Plan for MC Fabrication  R1	- 5 -

Figure 4- Flow Plan for TRC Fabrication            R1	- 6 -

Figure 5-NCSX Coil Manufacturing Facility Organizational Chart    R1	- 8 -

# Introduction and Scope

## Introduction

The National Compact Stellerator Experiment (NCSX) Modular coils will be manufactured at the Princeton Plasma Physics Laboratory (PPPL) for the NCSX Project.  This document describes the general operating plan that will be used during the manufacturing of the Twisted Racetrack (TRC) and modular coils.   R1

## Scope

This document will describe how the NCSX coil facility will function during the coil-manufacturing phase. This document includes the following sections:

2	Applicable Documents

3	General Description of the Modular Coils

4	Facilities and Workstations

5	Manufacturing Inspection and Test Plan (MIT)

6	Flow Plan for Manufacturing Operations

7	Responsibilities during Manufacturing

8	General Facility Operating Guidelines

9	Safety Requirements

10	Meetings and Communication

11	Documentation

12	Quality Assurance/Quality Control

This “General Operating Plan” along with the Manufacturing, Inspection and Test (MIT) plan will govern the processes by which the modular coils will be fabricated.

# Applicable Documents

| Document Number | Title |
| --- | --- |
| ESH-004 | Job Hazard Analysis |
| ES&H 5008 | PPPL Environmental, Safety and Health Manual |
| NCSX-MIT/QA-142-01-00 | Mfg., Inspection, Test/QA Plan for Modular Coils |
| NCSX-CSPEC-140-03 | Modular Coil Specification |
| NCSX-CSPEC-142-04 | Twisted Racetrack Coil Product Specification R1 |
| WP-1188 | Work Planning Form for Twisted Racetrack Coil R1 |
| WP-1038 | Work Planning Form for Winding Production Mod Coil |
| ESH-008 | Access to Radiological Areas (RCA’s) |
| NEPA 1283 | Modular Coil Development and Production |
| D-NCSX-OP-EO-41 | NCSX Coil Manufacturing Facility Emergency Response R1 |

# General Description of Modular Coils

The Modular Coil Set consists of three field periods with 6 coils per period for a total of 18 coils.  Due to symmetry, only three different coil shapes are required to make up the complete coil set.  Each modular coil is constructed by winding pre-insulated rectangular compacted copper cable onto a stainless steel cast winding form. Each coil consists of two double pancake windings.  Once wound, the entire coil will be vacuum-pressure impregnated (VPI) with epoxy. The winding forms are bolted together to form a complete torus and are electrically insulated from each other at the bolted flange interfaces.  The coil set will be pre-cooled to cryogenic temperatures before each experimental pulse by helium or nitrogen gas.  Figure 1-Modular Coil Types shows the (3) different modular coil types.

Type B                                                                 Type A

Type C

Figure 1-Modular Coil Types

# Facilities and Work Stations

The Twisted Racetrack (TRC) and Modular Coils will be fabricated in the vacated TFTR Test Cell at D-site. The coil testing facility as well as the coil storage area will be located in the Test Cell basement. The NCSX Coil Manufacturing Facility (CMF) has adequate climate control needed for comfort and tolerance control and crane capabilities.  There are a total of six [6] workstations associated with the manufacturing of the modular and TRC coils.  The facility will from here on be identified as the “NCSX Coil Manufacturing Facility” (Figure 2 -NCSX Coil Manufacturing Facility). The basement area will be identified as the NCSX Coil Test Facility and the NCSX Coil Storage Area.

## Facilities Description

### Crane Capacity

The manufacturing facility has an overhead trolley crane with (2) hooks.

Load capacity: 	Large hook- 110 Ton

Small hook/ 25 Ton

### Climate Control

The coil manufacturing facility environment will be maintained at a constant 70 degrees F +/- 5 degrees with 50% relative humidity +/- 10%                            R1

### Work Space

Test Cell has over 14,000 square feet of floor space that will be shared between the coil manufacturing facility, field period assembly activities plus the remaining neutral beams from TFTR. The coil winding facility will need a minimum of 3500 square feet of floor space.

## Work Station Descriptions

There are a total of [6] workstations associated with the production of the Modular Coils.  Stations 1 thru 5 are located in the Coil Manufacturing Facility (CMF).  Station No. 6 is located in the basement.

Note:  All work associated with the TRC will be performed in only stations #2 and 5.                                                                                                                     R1

### Station No. 1- Winding Form Preparation and Post VPI

At this station the modular coil winding forms are inspected, measured and cleaned.  The coil clamp studs are welded in position, and the inner copper cladding is installed.

Once the coil has been epoxy impregnated (VPI) at station 5, it will return to station 1 for cleanup and installation of final coil clamps.                                  R1

Note: All winding form preparation and post VPI activities for the TRC will be performed at Station #2.

### Stations 2, 3 & 4- Coil Winding and Mold Preparation                                       R1

At these (3) stations the insulated cable conductors are wound onto the stainless steel winding forms.  Work at this station includes the installation of the Groundwrap insulation as well as completion of the coil leads.  Once the coil has been wound, the outer chill plates, outer diagnostics, coil clamps and “Bag Mold” are installed. These stations will be enclosed with a ceiling and walls to better control the cleanliness of the winding environment.  The rooms will be provided with positive pressure to reduce any outside contamination.

### Station No. 5- Autoclave/VPI

This station is comprised of the autoclave [vacuum/pressure oven], epoxy mixing station and epoxy control station for performing the epoxy vacuum-pressure-impregnation of the modular coils.

### Station No. 6- Modular Coil Test Facility

This station is located in the Test Cell basement.  Each of the modular coils will be electrically tested at liquid nitrogen temperatures to ensure the integrity of the coils.

Figure 2 -NCSX Coil Manufacturing Facility

# Manufacturing Inspection & Test/QA Plan (MIT)

The Manufacturing Inspection & Test/Quality Assurance Plan (MIT/QA) will govern all manufacturing activities.  This document will describe the steps required to successfully manufacture, inspect and test the Modular coils. The (MIT/QA) plan document number NCSX-MIT/QA-142-01-01 will identify procedures, test plans, Field Packages etc. necessary to complete the production of the modular coils.

# Flow Plan of the Manufacturing Operations

Figure 3- Flow Plan for MC Fabrication provides the general flow plan outlining the operation of this facility for the Modular Coils. Figure 4- Flow Plan for TRC Fabrication            R1 provides the general flow plan outlining the operation of this facility for the Twisted Racetrack Coil.

Figure 3- Flow Plan for MC Fabrication -R1

Figure 4- Flow Plan for TRC Fabrication            R1

# Responsibilities during Manufacturing

This section identifies by discipline, those individuals who will to staff the manufacturing facility.  Figure 5-NCSX Coil Manufacturing Facility Organizational Chart is an overall organization chart for the Modular Coil Manufacturing Facility.  The subsections, which follow, provide a brief description of each position on that organization chart.

## Manufacturing Facility Manager

The Manufacturing Facility Manager is responsible for the overall operation of the Modular Coil Manufacturing Facility and successful completion of the modular coils.  Duties include managing the Field Supervisors, heading daily startup meetings, and ensuring that both Integrated Safety Management (ISM) and risk management are incorporated in all aspects of the manufacturing activities.

## Field Supervisors

The Field Supervisors (FS) report to the Manufacturing Facility Manager and are responsible for managing the lead technicians and field crews.  Each FS will have a primary station responsibility as well as sharing the overall supervisory responsibilities. In addition they are responsible for ensuring that ISM and risk management are incorporated in all aspects of the manufacturing activities.

## Lift Engineer

The Lift Engineer shall monitor and retain overall responsibility for the hoisting and rigging of non-repetitive lifts.  (Modular Coils)

## Coil Test Director

This Coil Test Director is the engineer responsible for coordinating the testing of each coil in the Coil Test Station located in the Test Cell Basement.  He reports to the Manufacturing Facility Manager.

## Lead Technicians

The lead technicians are responsible for supervising the field crew activities at each workstation.  They are also responsible for communicating all questions and/or concerns to the Field Supervisor, filling the station log book on a daily basis, and for ensuring that ISM and risk management are incorporated in all aspects of the manufacturing activities.  The Lead Technician reports to the Field Supervisors.

## Field Crews

The field crews report to the Lead Technicians and are responsible for performing the manufacturing activities as identified in the MIT/QA Plan and procedures to successfully complete the fabrication of the Modular Coils.  They are also responsible for ensuring that ISM is incorporated in all aspects of the manufacturing activities

## Health Physics Representative

The Health Physics Representative is responsible for coordinating with the Field Supervisors all health physics issues associated with work being performed in the Coil Manufacturing Facility (Test Cell).

[Note:  The Manufacturing Facility is located in a Radiation Controlled Area (RCA) requiring HP coverage to ensure that activities conform to PPPL HP policy.]

## Industrial Hygiene Representative

The Industrial Hygiene (IH) Representative is responsible for reviewing and approving Job Hazard Analysis (JHA) surveys and issuing Confined Space Work Permits.  He/she provides IH technical support to the field supervisors, lead technicians and field crews.

## Construction Safety Representative

The Construction Safety Representative is responsible for reviewing and ensuring that all field activities are being performed safely and in accord with PPPL safety requirements.  Responsibilities include working with field supervisors, lead technicians and field crews, making recommendations for types of safety equipment to be used and how to perform work more safely.

## Quality Control Representative

QC shall work as an independent group, reviewing field activities to ensure that procedures are being followed and that necessary travelers and data sheets are completed in a timely fashion.  The QC representative shall apprise the Field Supervisors and Manufacturing Facility Manager of any concerns.

Figure 5-NCSX Coil Manufacturing Facility Organizational Chart    R1

# General Facility Operating Guidelines

The following sections provide a brief overview of the operating guidelines for the NCSX Coil Manufacturing Facility.

## Field Supervisors                                                                                               R1

### Shall be appointed by the Manufacturing Facility Manager and will supervise all field operations.  Additionally during Modular Coil production, a Field Supervisor will ALWAYS be on duty in the NCSX Coil Manufacturing Facility during working hours.

## House-Keeping/Cleanliness Rules

“Good House-Keeping” is an essential element to the success of the manufacturing of the modular coils.  The following steps will be taken to enforce this practice.

### No food, gum, smoking or beverage will be allowed in the NCSX Coil manufacturing facility. (Radiation Controlled Area “RCA”)                            R1

### The coil winding and molding stations [Work Stations #2-4] will be housed in a clean environment with walls, ceiling and filtered airflow.

### Only personnel associated with the coil manufacturing activities may enter Work Stations #2-4 unless approved by the Manufacturing Field Manager or Field Supervisors.  Approved names will be posted outside each station.

### Step-off pads will be used at the entrances of workstations 2-4, to minimize transport of foreign particulate and dirt into the work area.  In addition, some sort of approved protection must be worn over street shoes such as booties or other approved foot coverage while in these areas.

### Either latex, rubber or cotton lint-free gloves will be required to be worn during the handling of insulated conductor, insulation, fillers or other components used in the construction of the modular coils.

### It is recommended that lab coats or Tyvex suits be worn by the crew during the winding and molding operations.

### The manufacturing stations will be cleaned daily at the end of each shift.

### Markers and Pencils:

The use of lead pencils or non-approved markers is prohibited in the fabrication stations. “Sharpie” permanent markers are the only markers that may be used without prior approval by the Field Supervisor.

### Chips and Filings:

Extreme care must be taken when using files, grinders, etc. that could generate metal chips or filings.  Surrounding areas must be protected from these activities.

## Hard hats

Hard hats are not required in the NCSX Coil Manufacturing Facility unless the facility crane is in use directly overhead.

## Station Logbook

Each workstation will have a “Station Logbook” that will be filled in on a daily basis by the Lead Technician.  Entries will include technical data associated with that station, daily progress, as well as problems and solutions that may arise.

## Daily Summary Report

A daily summary report, outlining the day’s activities, will be issued by the Field Supervisor on duty at the end of the shift.  This report will briefly outline the day’s accomplishments as well as manufacturing issues he feels should be included.  This report will be e-mailed to a pre-approved list of NCSX project management. (During MC production)                                                                                                                     R1

# Safety and Training Requirements

## Integrated Safety Management (ISM)

ISM principles will be used throughout the coil manufacturing process. It is a “Common sense approach to Doing Work Safely”. There are seven guiding principles for safety management:

### Line management responsibility for safety

### Clear roles and responsibilities

### Competence commensurate with responsibilities

### Balanced priorities

### Identification of safety standards and requirements

### Hazard controls tailored to work being performed

### Operations authorization

## Job Hazard Analysis Surveys and Safety Meetings

### JHA’s will be generated to identify existing or potential workplace hazards and to evaluate the risk of worker injury or illness associated with job tasks. (Reference document ESH-004 “Job Hazard Analysis”)  The JHA’s will be reviewed by the IH representative for accuracy as well as completeness.  It will be reviewed with all activity participants at the Pre-Job briefings.

### Safety meetings will be conducted on a regular basis to ensure that the focus on safety is a foremost priority.

## Safety Walk-Through’s

Daily safety walk-throughs will be performed by Industrial Hygiene, by Construction Safety and by field supervisors with the intention of identifying and correcting unsafe conditions or activities in the manufacturing area.

## Training

Training of personnel is “Key” to completing the NCSX fieldwork safely.  Courses will be required for all personnel, instructing them in the proper use of tools and equipment; personal protective equipment (PPE’s); and general laboratory policy and safety requirements.  All personnel entering the Coil Manufacturing Facility must be Radiation Safety Qualified, must wear current radiation dosimetry, and must sign the Radiation Work Permit (RWP)/Access Log daily.  Visitors may only enter if escorted by an individual RAD Safety qualified with a visitors radiation badge.

## Personal Protective Equipment [PPE’s]

The PPPL Industrial Hygiene and Construction Safety representatives will work together with the Coil Facility Manager to identify the necessary and correct personal protective equipment needed to ensure a healthy and safe work environment for the work force.

## Radiation Controlled Area:

The modular coil manufacturing facility is located in a Radiation Controlled Area (RCA). As a result, all personnel entering or working in the area must be radiation qualified, or be escorted by a qualified escort.

R1

### Food and Beverage

No food, gum, or beverage will be allowed in the MC manufacturing facility because it is located in an RCA.

## Emergency Response Procedure

In the event of abnormal conditions in the NCSX Coil Manufacturing Facility, procedure “D-NCSX-OP-EO-41” identifies what actions should be taken. Abnormal conditions are identified as conditions which, if not corrected, could result in injury to personnel or damage to equipment.                                     R1

# Meetings and Communication

Communication between management and the field crews is essential to ensure a successful and cohesive working group.  In addition to the meetings described below, other meetings may be held “as required” to keep the work crew informed of laboratory or safety related items.

## Daily Startup Meetings

There will be a Daily Startup Meeting to review inter-actions, planning, scheduling and commitments for all activities associated with the Coil Manufacturing Facility.

### Time: The meetings will be held in the AM Monday thru Friday prior to the start of field activities and will address the day’s scheduled activities.

### Location:  The meetings will normally be held in the WCC trailer conference room at D-site.  Location of meeting may also be in the field.                          R1

### Chairman: The Manufacturing Facility Manager (MFM) or his designee (Field Supervisor) will chair this meeting.

### Attendees should include the MFM, Field Supervisors, Lead Technicians, Field Crews, Health Physics Representative, Industrial Hygiene Representative, Quality Control Representative and Construction Safety Representative.  This list may change depending upon the tasks being performed that day.

## Safety Meetings

There will be safety meetings typically every other week to discuss particular safety issues associated with the manufacturing of the modular coils and/or general safety related topics. (These meetings will commence once the manufacturing of the production coils has begun)                                          R1

### Time: The meetings will be held at 11:00 AM every other Tuesday and will address safety issues.

### Location:  The meetings will generally be held in the WCC trailer conference room at D-site.  However, they may be held in other areas as deemed appropriate for the topic being discussed.

### Chairman: Either a safety representative or a field supervisor will chair the meetings, as required.

### Attendees should include the Field Supervisors, Lead Technicians, Field Crews, Health Physics Representative, Industrial Hygiene Representative, Quality Control Representative and Construction Safety Representative.  This list may change depending upon the topic of the meeting that day.

## Pre-Job Briefings

Pre-job briefings are held prior to the start of any new work activity.  The purpose of the briefing is to discuss specific work activities, responsibilities of the participants, a review of the JHA/safety issues, and to respond to all questions and concerns.  The participants at these briefings should include all individuals who will be involved with the activity including lead technician, field crews, and supervisors.  Representatives from construction safety, Industrial Hygiene, Health Physics and Quality Control should be included as appropriate to the job.

## Post-Job Briefings

A post-job briefing is held at the conclusion of a work activity.  These briefings will be held at each station for every modular coil. The purpose of the briefing is to discuss the completed work activities.  It should include lessons learned including technique problems, improvements and safety related issues. The participants at these briefings should include all individuals involved with the completed activity or procedure. It should include the lead technician, field crews, and supervisors.  Representatives from construction safety, Industrial Hygiene, Health Physics and Quality Control will be included as appropriate to the job.

# Documentation

## Document Control

All NCSX associated documents used for manufacturing the modular coils will be under NCSX Project document control.  Any modifications to the procedures will be implemented via ENG-030.          R1

## Coil Field Package                                                                                        R1

### Each coil will have a separate “Coil Field Package” that will follow the coil from station to station.  It will include all of the process procedures, QC inspection reports, photographs, test results, and measurements used to document completion of major activities.  The Field Package will be further discussed in the MIT plan.

### The Lead Technician, Field Supervisor and or Quality Control representative will document all critical completions in the procedure.  This will be completed using the signer’s initials identifying the approver.

### The signoffs in the procedures will be filled out in a timely fashion once a particular activity has been completed.

## Documents Retention and Storage

All documents associated with the manufacturing of the NCSX coils will be stored in an appropriate location for an indefinite period of time or until the project authorizes their destruction.  Documents may be stored either electronic or hard copy.

# Quality Assurance/Quality Control Requirements

## Quality Control during Manufacturing

Quality control during the manufacturing process will be the responsibility of all parties involved in the manufacturing (Field supervisors, technicians, and Quality Control representative)

## Measurements

Measurements and tests will typically be performed by the work crews and engineering.  The QC representative should be made aware of planned tests and measurements, but unless required by the procedures, need not be present.

## Other Quality Control Representative Responsibilities

### The QC representative will review the field activities on a daily basis; checking for completion of documentation as well as compliance with the approved procedures.

### The QC representative will be a required signature on the procedure verifying that the station activities have been completed and that the coil may move to the next station.

### The QC representative will report to the laboratory appointed NCSX QA representative.  He/she will also inform the Coil Facility Manager of any issues or concerns that may be uncovered.

# Comments

It’s not clear what is considered to be repetitive vs. non-repetitive lifts. This should be defined in this document.

As a somewhat separate viewpoint, given the risks associated with this work, why not have a PPPL Lift Engineer monitor and retain overall responsibility for all hoisting and rigging?

If this cleaning will be done by the janitorial staff, they will need some training on what they can and cannot do.

Will the daily summary report also be generated during the TRC production?

Training specific to the work to be performed under this plan are identified in detail where?

Does this include the TRC?

Changes to the procedure may be of such a scope that an MPC is not appropriate and a revision may be required. I’m sure you hope this won’t happen, but it could.

The location needs to be established now. If paper documents, they should be stored in the Ops Center. If electronic documents, they should be stored on the NCSX web site. Per the NCSX Docs and Records Plan, they need to be retained until the machine is dismantled and disposed.

# Text boxes

# Station No.2

Winding/Molding Station A

# Station No.2

-Winding Form Prep.  -Coil Winding

- Install of Mold

# NCSX WBS 14 Manager

## Dave Williamson

Industrial Hygiene Representative

Three winding stations will be used.  Each station will include:

-Coil winding

-Ground wrapping

-Installation of chill plates

-Installation bag mold

-Vacuum leak checking of bag

Manpower:  2 technicians per station

Install TRC into autoclave; VPI and cleanup

Manpower:  4 technicians per station

# Station No.5

VPI/Autoclave Station

# Station No.1

Casting Preparation

# Station No.3

Winding/Molding Station B

# MC Manufacturing Facility Manager

Jim Chrzanowski

# Station No.5

VPI/Autoclave Station

Winding Form Preparation station:.  Activities include:

-Mount WF to support ring

-Measure/inspect WF surfaces

-Install clamp studs

-Clean & mold release WF

-Install winding clamps

-Install inner cladding

Manpower:  2 technicians per station

Station #2 activities include:

-Mount WF to support ring

-Measure/inspect WF surfaces

-Install clamp studs

-Clean & mold release WF

-Install winding clamps

-Install inner cladding

-Coil winding

-Ground wrapping

-Installation of chill plates

-Installation bag mold

-Vacuum leak checking of bag

Manpower:  2 technicians per station

# PPPL Responsible Line Manager

## Larry Dudek

Install MC into autoclave; VPI and cleanup

Manpower:  4 technicians per station

Station No. 6

Coil Testing

(1) Lead Tech. + [TBD] crew

Cold test the modular coil [TC Basement]

Station No. 5

VPI

(1) Lead Tech. + [3] crew

Stat. #5

# Field Supervisor *

# Tom Meighan

* Note:  Each Field Supervisor has a primary station responsibility as well as sharing overall field management responsibilities.

Quality Control Representative

Indicates a communication link, and not a management link between the participants

# Field Supervisor *

# Jim Chrzanowski

Station No. 2, 3 & 4

## Winding stations

(3) Lead Techs + [3] crew

# Field Supervisor *

# Steve Raftopoulos

(Metrology)

Station No. 1

Winding Form Preparation

(1) Lead Tech. + [1] crew

Construction Safety Representative

Health Physics (HP) Representative

Transport VPI’d coil back to Station #2 Turning fixture for installation of Final Coil Clamps

Manpower:  2 technicians per station

# Station No.2

Post VPI

# Station No.6

Coil Testing

# Coil Test Director

# Geoff Gettelfinger

Stat. #5

Future Field Period Assembly Area

Coil Exit

Transport VPI’d coil back to Station #1 Turning fixture for installation of Final Coil Clamps

Manpower:  2 technicians per station

# Station No.6

Coil Testing

Cold test the modular coil [TC Basement]

# Station No.1

Post VPI

# Station No.4

Winding/Molding Station C

Station #1

Station #4

Station #3

Station #2