## Sheet1
8 and 10 hour shifts |  | Estimate |  | C | 1 | C | 2 | C | 3 | C | 4 | C | 5 | C | 6
| Total | No. of | personhrs | personhrs | Total | personhrs | Total | personhrs | Total | personhrs | Total | personhrs | Total | personhrs | Total
TASK DESCRIPTION | Shifts | Tech./Shift | /coil | /coil | Shifts | /coil | Shifts | /coil | Shifts | /coil | Shifts | /coil | Shifts | /coil | Shifts
Station No. 1- Casting Preparation | 25 | Total Shifts per Coil |  | Delivery | 2005-10-03 | Delivery | 2005-12-15 | Delivery | 2006-02-27 | Delivery | 2006-03-29 | Delivery |  | Delivery
Winding form rework activities [Not planned]
Includes grinding, hole drilling, etc |  |  |  | 160 | 7 (*) | 32 | 2 |  | 4
Electrical test poloidal break
| 1 | 1 | 8 | 4 | 0.5 | 4 | 0.5
Position & mount casting to support ring
| 5 | 4 | 200 | 160 | 4 | 64 | 2 |  | 0.5
Install coil in station 1b turning fixture
| 1 | 3 | 24 | 32 | 1 | 32 | 1 |  | 0.5
Balance ring assembly
1
Weld monuments, stud adapters & lead nuts
TIG weld actvities | 2 | 2 | 32 | 32 | 2 | 24 | 1.5 |  | 2
Install studs for winding clamps
Position and weld studs for winding clamps | 3 | 3 | 72 | 90 | 3 | 60 | 2 |  | 2
Fitup Lead blocks and terminals [Remove lead blocks] | 2 | 2 | 32 | 16 | 1 | 8 | 0.5
1
Inspect casting
Label, Inspect surfaces, & magnetic permeability | 1 | 2 | 16 | 16 | 1 | 48 | 2
Measure casting using metrology equipment | 2 | 2 | 24 | 32 | 3
Clean casting
Clean casting using acceptable solvents | 1 | 2 | 16 | 16 | 1 | 16 | 1
and inspect/clean all threaded holes
Install edge Kapton and Mold release
| 1 | 2 | 16 | 32 | 2 | 24 | 1.5
Install inner cladding plates
Position and secure copper cladding plates | 6 | 4 | 192 | 480 | 12 | 126 | 6
Inc. rework
Coil Winding Station 2 and 4 | 57 | Total shifts per coil
Prepare coil for winding
Install coil in turning fixture | 1 | 3 | 24 | 32 | 1 | 24 | 1
Install/set winding clamps sides A & B | 3 | 2.5 | 60 | 96 | 4 | 132 | 7
Position Ground wrap sides A&B | 9 | 2.5 | 225 | 270 | 9 | 128 | 11
Position lacing strips sides A & B [Metrology require't] | 2 | 2.5 | 50 | 60 | 2 | 108 | 4
Dimensional measure surface [First coil] [Metrology require't] | 2 | 2 | 40 | 40 | 2
Wind Side "A"
Position & secure 1st. coil lead set [inc. brazing] | 2 | 2.5 | 50 | 90 | 3 | 35 | 1.5
Type C-Wind layer #1 - [10] turns of conductors (4-in-hand) | 11 | 2.5 | 275 | 360 | 12 | 148 | 7.5
Prepare station for Side "B" -Total Shifts (1)
Reposition coil from side A to side B | 1 | 3 | 24 | 32 | 1
Wind Side "B"
Position & secure 1st. coil lead set [inc. brazing] | 2 | 2.5 | 40 | 90 | 3
Type C-Wind layer #1 - [10] turns of conductors (4-in-hand) | 11 | 2.5 | 275 | 330 | 11
Final coil winding activities
Reposition coil bundle [sides A & B] [Metrology require't] | 4 | 2 | 80 | 270 | 9
Secure Lacing [Metrology require't] | 2 | 2 | 40 | 142 | 7.5
Remeasure after/during lacing is secured [Metrology require't] | 1 | 2 | 16 | 24 | 1
Complete groundwrap installation | 6 | 2.5 | 150 | 144 | 7
Numbers in blue are not completed activities
C1 | Line 69 | C1- Braze problems [ had to revise and requalify process]
(*) Includes fabrication and installation of new bearing plates
Through 1st. Shift Tuesday 2/21/06
|  | Estimate |  | C | 1 | C | 2 | C | 3 | C | 4 | C | 5 | C | 6
| Total | No. of | personhrs | personhrs | Total | personhrs | Total | personhrs | Total | personhrs | Total | personhrs | Total | personhrs | Total
TASK DESCRIPTION | Shifts | Tech./Shift | /coil | /coil | Shifts | /coil | Shifts | /coil | Shifts | /coil | Shifts | /coil | Shifts | /coil | Shifts
Final coil prep & Mold Application (Station 2 & 4) | 27
Install chill plates & Tubing
| 12 | 2.5 | 300 | 398 | 17
Install outer Diagnostic loops
| 2 | 2 | 32 | 48 | 2
Position & secure 2nd. coil lead set sides A&B [inc. brazing] | 4 | 2.5 | 50 | 76 | 6
Perform pre-VPI elect. & press. Tests
Pressure test cryo lines& perform prelim. [pre-vpi] electrical tests | 1 | 2 | 16 | 16 | 1
Install bag mold around modular coil
Install G-11 pads, glass, silicone bag & sprues | 4 | 2.5 | 80 | 176 | 6
Vacuum pumpdown & leak repair | 2 | 2.5 | 40
Install epoxy shell | 2 | 2.5 | 40
VPI Activities (Station 5) | 16 | Total Shifts per Coil
Transfer modular coil to Autoclave
| 1 | 3 | 24
Prepare modular coil for VPI |  |  |  | 190 | 13
(Connect fill lines, manifolds, hookup thermocouples & leak check) | 3 | 3 | 72
VPI modular coil | 12 |  | 232
Vacuum pumpdown & preheat mold and autoclave | 2 | 3 | 48
Epoxy fill coil | 2 | 3 | 48
Temperature rampup and Cure | 3 | 2 | 48
Temperature rampup and Post cure | 2 | 2 | 32
Temperature rampdown | 1 | 1 | 8
Cleanup & ready autoclave | 2 | 3 | 48
Post VPI Activities (Station 1) | 9 | Total Shifts per Coil
Transfer MC from Autoclave to Station #1
| 1 | 3 | 24
Remove sprues & structural shell & studs
| 2 | 2 | 32
Finalize coil & install final clamps (40-50 clamps/per coil)
| 3 | 2 | 48
Perform (RT) electrical & Pressure Tests
| 1 | 2 | 16
Remove coil from ring assembly
| 2 | 2 | 32
Total shifts to complete 1 coil | 134