## Sheet1
| Total | No. of | personhrs | %
TASK DESCRIPTION | Shifts | Tech./Shift | /coil | Complete
Station No. 1- Casting Preparation | 29 | Total Shifts per Coil
Winding Form rework activities[ TBD]
| 4 | 2 | 64 | 14%
Electrical test poloidal break-Total Shifts (1)
| 1 | 1 | 8 | 17%
Position & mount casting to support ring- Total Shifts (5)
| 5 | 4 | 200 | 34%
Install coil in station 1b turning fixture- Total Shifts (1)
| 1 | 3 | 8 | 38%
Weld monuments, stud adapters & lead nuts-Total Shifts (2) | 2 | 2 | 8 | 45%
Inspect casting -Total Shifts (3)
[Label, Inspect surfaces, & magnetic permeability]
Measure casting using metrology equipment | 3 | 2 | 48 | 55%
Install studs for winding clamps- Total Shifts (3)
Position and weld studs for winding clamps | 3 | 3 | 72 | 66%
Clean casting- Total Shifts (1)
Clean casting using acceptable solvents | 1 | 2 | 16 | 69%
Inspect and clean all threaded holes
Install edge Kapton and Mold release | 1 | 2 | 16 | 72
Fitup Lead blocks and terminals [Remove lead blocks]
| 2 | 2 | 32 | 79%
Install inner cladding plates- Total Shifts (6)
Position and secure copper cladding plates | 6 | 4 | 8 | 100%
| Total | No. of | Hrs per | %
TASK DESCRIPTION | Shifts | Tech./Shift | Shift | Complete
Coil Winding Station 2 and 4 | 61 | Total shifts per coil
Prepare coil for winding -Total Shifts (17)
Install coil in turning fixture | 1 | 3 | 24 | 2%
Install/set winding clamps sides A & B | 3 | 2.5 | 60 | 6%
Position inner groundwrap insulation onto winding form (sides A & B) | 9 | 2.5 | 225 | 21%
Position lacing strips sides A & B [Metrology require't] | 2 | 2.5 | 50 | 25%
Dimensional measure surface [First coil] [Metrology require't] | 2 | 2 | 40 | 28%
Wind Side "A" -Total Shifts (13)
Position & secure 1st. coil lead set [inc. brazing] | 2 | 2.5 | 50 | 31%
Type C-Wind layer #1 - [10] turns of conductors (4-in-hand) | 11 | 2.5 | 275 | 49%
Prepare station for Side "B" -Total Shifts (1)
Reposition coil from side A to side B | 1 | 3 | 24 | 51%
Wind Side "B" -Total Shifts (13)
Position & secure 1st. coil lead set [inc. brazing] | 2 | 2.5 | 40 | 54%
Type C-Wind layer #1 - [10] turns of conductors (4-in-hand) | 11 | 2.5 | 275 | 72%
Final coil winding activities -Total Shifts (17)
Reposition coil bundle [sides A & B] [Metrology require't] | 4 | 2 | 80 | 79%
Secure Lacing [Metrology require't] | 2 | 2 | 40 | 82%
Remeasure after lacing is secured [Metrology require't] | 1 | 2 | 16 | 84%
Position & secure 2nd. coil lead set sides A & B [inc. brazing] | 4 | 2.5 | 100 | 90%
Complete groundwrap installation | 6 | 2.5 | 150 | 100%
| Total | No. of | personhrs | %
TASK DESCRIPTION | Shifts | Tech./Shift | /coil | Complete
Final coil prep & Mold Application (Station 2 & 4) | 23 | Total Shifts per Coil
Install chill plates & Tubing -Total Shifts (12)
| 12 | 2.5 | 300 | 52%
Install outer Diagnostic loops -Total Shifts (2)
| 2 | 2 | 32 | 61%
Perform pre-VPI elect. & press. tests-Total Shifts (1)
Pressure test cryo lines& perform prelim. [pre-vpi] electrical tests | 1 | 2 | 16 | 65%
Install bag mold around modular coil- Total Shifts (8)
Install silicone bag & sprues | 4 | 2.5 | 80 | 83%
Vacuum pumpdown & leak repair | 2 | 2.5 | 40 | 91%
Install epoxy shell | 2 | 2.5 | 40 | 100%
| Total | No. of | personhrs | %
TASK DESCRIPTION | Shifts | Tech./Shift | /coil | Complete
VPI Activities (Station 5) | 16 | Total Shifts per Coil
Transfer modular coil to Autoclave -Total Shifts (1)
| 1 | 3 | 24 | 6%
Prepare modular coil for VPI -Total Shifts (3)
(Connect fill lines, manifolds, hookup thermocouples & leak check) | 3 | 3 | 72 | 25%
VPI modular coil -Total Shifts (12) |  |  | 232
Vacuum pumpdown & preheat mold and autoclave | 2 | 3 | 48 | 38%
Epoxy fill coil | 2 | 3 | 48 | 50%
Temperature rampup and Cure | 3 | 2 | 48 | 69%
Temperature rampup and Post cure | 2 | 2 | 32 | 81%
Temperature rampdown | 1 | 1 | 8 | 88%
Cleanup & ready autoclave | 2 | 3 | 48 | 100%
| Total | No. of | Hrs per | %
TASK DESCRIPTION | Shifts | Tech./Shift | Shift | Complete
Post VPI Activities (Station 1) | 9 | Total Shifts per Coil
Transfer MC from Autoclave to Station #1- Total Shifts (1)
| 1 | 3 | 8 | 11%
Remove sprues & structural shell & studs- Total Shifts
| 2 | 2 | 8 | 33%
Finalize coil & install final clamps (40-50 clamps/per coil)-Total Shifts (3)
| 3 | 2 | 8 | 67%
Perform (RT) electrical & Pressure Tests-Total Shifts (1)
| 1 | 2 | 8 | 78%
Remove coil from ring assembly- Total shifts (2)
| 2 | 2 | 8 | 100%
Total Shifts required to complete [1] modular coil [includes 4 shifts of casting rework activities] | 138