- The parties agree Subcontractor will deliver the following, by the date indicated.

| Reference | Description | To Be Received by PPPL |
| --- | --- | --- |
| SOW Para 5.1 | Weekly Status Reports via e-mail | Every Wednesday |
| SOW Para 5.2 | Earned Value Reporting |  |
|  | Resource Loaded Schedule | 3 weeks after the Sub-contract Effective Date |
|  | Monthly Report | End of each Month Beginning with the First Full Month After Subcontract Award |
| SOW Para 3.1.1 and 5.3 | Manufacturing Methods for Fabricating the Vacuum Vessel Sub-Assembly (VVSA) | 23 May 2003 |
| SOW Para 3.1.2 and 5.3 | Subcontractor Recommendations | 23 May 2003 |
| SOW Para 3.1.3 and 5.3 | Preliminary Manufacturing , Inspection and Test (MIT) and Quality Assurance (QA) Plans for the Vacuum Vessel Sub-Assembly (VVSA) | 23 May 2003 |
| SOW Para 3.1.4 and 5.3 | Budgetary Cost and Schedule Estimate for the Vacuum Vessel Sub-Assembly (VVSA) and required tooling | 23 May 2003 |
| SOW Para 3.2.1 and 5.3 | MIT and QA Plans for the Prototype Vacuum Vessel Segment (PVVS) | 2 weeks before Prototype Fabrication Begins |
| SOW Para 3.2.2 and 5.4 | Prototype Vacuum Vessel Segment (PVVS) Manufacture | 15 November 2003 |
| SOW Para 3.3.1 and 5.3 | Final MIT and QA Plans for Vacuum Vessel Sub-Assembly (VVSA) | 30 Calendar Days after Receipt of Final Specif-ication and Drawings |
| SOW Para 3.3.2 and 5.3 | Firm-Fixed Price Cost and Schedule Proposal for Production of three Vacuum Vessel Sub-Assemblies (VVSA) | 30 Calendar Days after Receipt of Final Specif-ication and Drawings |
| SOW 5.4.1 | Shipping Release Form | Prior to Shipment of PVVS |
| SOW 5.4.2 | Process History | Available at the Time Shipping Release Form Submitted to PPPL |
| SOW 5.5 | Tooling | Disposition Will Be Announced Later by PPPL. |

ARTICLE IV - OBLIGATION OF FUNDS/LIMITATION OF FUNDS

1.	PPPL will obligate funding to this Subcontract in increments.  This initial increment of funding is (Major Tool increment different from Rohwedder increment).  The basis for this funding allocation is:

| Reference | Description | Dollars Obligated/ % of Task Cost, No Fee |
| --- | --- | --- |
| SOW Para 5.1 & 2 | Status & Earned Value Reporting | $XXXX |
| SOW Para 3.1.1, 3.1.2, 3.1.3 and 3.1.4 | Manufacturing Methods for Fabricating the Vacuum Vessel Sub-Assembly (VVSA; Subcontractor Recommendations; Preliminary MIT and QA Plans for the VVSA and Budgetary Cost and Schedule Estimate for VVSA | $XXXX (100%) |
| SOW Para 3.2.1 | MIT and QA Plans for the Prototype Vacuum Vessel Segment (PVVS); Manufacture of PVVS; Final MIT and QA | $XXXX (100%) |
| SOW Para 3.2.2, 3.3.1 and 3.3.2 | Funding to permit incurrence of cost for materials, and for initiation of Task performance activities WHEN AUTHORIZED by the Princeton Technical Representative for the Subcontract. | $XXXX (34%) |
|  | Total – First Increment of Funding* | $XXXX (≈XXX%) |