## Sheet1
Date | Name | Issue/Request | Project Response | ECP # | Contract Addendum | ECN # | CSPEC
2004-12-03 | Addendum 3-1 | (1) Re D. McCorkle communication to M. Viola 11/20/2004 9:23 A.M. On drawing SE122-104 section F-F (zone E4) the "2X .63" dimension from the datum -A- surface to the center of the NPT hole is a two place, untoleranced dimension. This requires a lineal location of the hole to be within +/- 0.010" (no problem). The "2X .125" (x .625 deep) would require a depth tolerance of +/- 0.005". It is dimensioned to the center of the NPT hole and cannot be checked. This type of feature would normally be a dimension something like: 2X Dia. 0.125 break through Dia. 0.25 hole. The .625 depth will not have an inspection record in the data book. NCSX Project response: Three place dimensioning was a ProE default; we will change the “2x .125” dimension to two place. This specific dimension does not require verification. | Accepted | ECP-019 | Addendum 3-1 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2004-12-03 | Addendum 3-1 | (2) Re: D. McCorkle communication to M. Viola 11/20/2004 10:21 A.M. The holes located by a basic bolt circle radius are toleranced with a true position feature control frame. NCSX Project response: The .271 typical dimension in Drawing SE122-019 zone G4 (Detail X) will be changed to reference only. | Accepted | ECP-019 | Addendum 3-1 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2004-12-03 | Addendum 3-1 | (3) Vacuum vessel drawings fail to call out the weld detail of the Dome feature. This will be added to the drawings. [120-004 sht 16] | Accepted | ECP-019 | Addendum 3-1 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2004-12-03 | Addendum 3-1 | (4) The Segmentation Scheme, a deliverable required by Section 5.1.1 of the Subcontract Statement of Work, has been received and accepted by the NCSX Project. | Accepted | ECP-019 | Addendum 3-1 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2004-12-17 | Addendum 3-2 | “The zip file tiled VV_Prod_step_Rev1b was added to the production_vessel folder. This file is identical to the Rev 1 Step file posted 24 November 2004 except that the assembly Step files have been updated to allow the Step model parts to open with the part names listed with a revision number. Also, included in the zip file is a spread sheet titled VVSA_Revised_Step_Models.xls that lists the revised Step files along with a change description. The earlier posted zip Step file has been archived.” | Accepted | ECP-019 | Addendum 3-2 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2004-12-17 | Addendum 3-2 | MTM reported some files were blank or empty | Accepted | ECP-019 | Addendum 3-2 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-14 | Addendum 3-3 | (1) Weld Detail for Port 4 Det X on 120-004 SH 5 and 13 per D. McCorkle communication to M. Viola Fri 12/17/2004 5:27 P.M. “Risk mitigation synopsis and three design change recommendation sketches” and the Weld Joint design change sketch.pdf contained. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-14 | Addendum 3-3 | (2) Relax tolerance around 4 ports (#4A, 4B, 12A, 12B) due to estimated local inward distortion (estimating 0.125-0.250”) within 4-8” of the perimeter of the port weld. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-14 | Addendum 3-3 | Reduce the pumpout requirement on each port cover. Allow for pumpouts to be provided at the discretion of the supplier to meet specification requirements. The minimum port connection prescribed by Specification paragraph 4.2.1 must be provided. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-25 | Addendum 3-3 | Re: D. McCorkle communication to M. Viola Fri 12/17/2004 5:27 P.M. “Risk mitigation synopsis, and three design change recommendation sketches.”
2005-01-25 | Addendum 3-3 | (1) Specification Addendum 3-2 provided NCSX project guidance that the greater risk is if the vessel is oversize vs. undersize in the region of the large ports and that Option #1 as proposed, appeared to be the better choice given the scenario provided. Sketches were provided to PPPL for evaluation of a slight modification to the weld joint design where the large ports attach to the vessel which could reduce the anticipated inward distortion by approximately 50%. MTM highly recommended the implementation of these changes. The proposed weld design change for the large ports has been evaluated and deemed acceptable. The three proposed weld detail changes will be included as alternate weld details in the next drawing revisions to SE120-004, sheets 5, 13, and 15. These are expected to accompany Specification Revision 4, projected to be issued before 1 March 2005. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-25 |  | (2) Also in the D. McCorkle communication to M. Viola was a handwritten note questioning the callout for the port 4 seal on drawing SE120-004 Sheet 5 of 19 R1 “#43 should possibly be #53.” The callout is correct as #43, a Viton seal. | Not Accepted
2005-01-25 | Addendum 3-3 | (3) In his synopsis, Mr. McCorkle indicated that MTM believes the welding of the large ports will create additional localized inward distortion within the general area of each port. He further stated that it is anticipated that this localized inward distortion at each port extension will gradually improve as you move away from the port welds, and return to the normal welded profile (estimating within approximately 4.0” - 8.0”). | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-25 |  | (4) Mr. McCorkle listed the expected distortion as follows:
2005-01-25 | Addendum 3-3 | a. This local distortion is expected to be minimal at the round pipe / tubing ports (estimate 0.06” - 0.08”). NCSX RESPONSE: A local contour tolerance of +3/16 -5/16 within 8” of the round port attachment welds will be acceptable and will be shown on the drawings as a tolerance zone. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-25 | Addendum 3-3 | b. The installation / welding of the spherical dome is expected to experience more distortion (estimating 0.08” - 0.125”). NCSX RESPONSE: A local contour tolerance of +3/16 -5/16 within 8” of the dome port attachment weld will be acceptable and will be shown on the drawings as a tolerance zone. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-25 | Addendum 3-3 | c. The installation / welding of the large fabricated ports (made from ½” thick material) is expected to produce the largest amount of local inward distortion (estimate 0.125” -0.250”). NCSX RESPONSE: The regions around the four ports in question (#4A, 4B, 12A, 12B) have been evaluated. Fortunately, the plasma in these regions is sufficiently inboard from the shell. While the original tolerance is preferred to prevent required alterations to components mounted to the inside of the vessel shell, a tolerance deviation of +3/16 -7/16 at the perimeter which returned to the normal shell profile within 8” of the perimeter of the port weld would be acceptable. This will be included as a note on the drawings pertaining to these port weld details in the next revision. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-25 | Addendum 3-3 | d. The estimated inward distortion of the Neutral Beam port is expected to be less than the other large fabricated ports (estimate approximately 0.08” - 0.125”). NCSX RESPONSE: A local contour tolerance of +3/16 -5/16 within 8” of the Neutral Beam port attachment welds will be acceptable and will be shown on the drawings as a tolerance zone. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-25 | Addendum 3-3 | (5) During the review of procedure PS-489 Process Specification – Material Procurement Requirements 65678 PPPL NCSX Vacuum Vessel Sub Assembly, it was discovered that the port covers all had pump out ports requiring the use of 316 material and weld wire. The drawings required the pump out ports to accommodate the leak check associated with the original concept of attaching the ports prior to boring the holes. Should Major Tool avail themselves of the option listed in Specification paragraph 3.1.3 to change the sequence which obviates the need for every blank port cover to have a pump out installed, then the pump out provision is at their discretion. The minimum port connection prescribed by Specification paragraph 4.2.1 must be provided. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-01-25 | Addendum 3-3 | (6) Major Tool requested the final spacer geometry in order to complete their fixturing design. The VV spacer weldment assembly step file (se121-014_asm.stp) and the VV spacer leak check assembly step file (se121-020_asm.stp) have been placed in the production vessel ftp site. The spacer design did not change in the ECN# 4933 revision, posted 24 November 2004. To maintain a complete data set the spacer pdf drawings were placed in the pdf zip file (VV_Prod_pdf_Files_Rev1.zip) but we inadvertently forgot to place the spacer step files in zip file, VV_Prod_step_Rev1b.zip. We will develop a combined data set in the next revision. | Accepted | ECP-019 | Addendum 3-3 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-02-01 | MTM Email | From: McCorkle, Doug Sent: Tuesday, February 01, 2005 2:58 PM It appears there is a slight problem with the model geometry. Please look at the material thickness for the #4 Port Extension. As we measure it, it varies in thickness. We will be manufacturing the fixturing to the inside profile. The material will be 0.50" thick. The variation in the model surface will affect profile measurements [which will be measured on the OUTSIDE surface (see next message)]. Since we are using the model as our inspection standard, it should be precise. Please take a look and provide some feedback. Port 4 thickness correction on se120-004 sheet 5 and its associated STEP file. Model changed to keep constant thickness. | Accepted. |  |  | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-02-09 | MTM Email | From: McCorkle, Doug Sent: Wednesday, February 09, 2005 12:37 PM Since the Laser Tracker profile inspection is performed on the outside surface, it will provide inaccurate measurements. We would be inspecting the profile to an inaccurate surface. It may show a surface that is actually within the tolerance as out, and visa-versa. We couldn't come up with a recommendation other than updating the model. | Accepted - see response to 2/1/2005 issue |  |  | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-02-15 | MTM Email | From: McCorkle, Doug Sent: Tuesday, February 15, 2005 3:49 PM Please look at drawing SE120-005, sheet 2, zone E2. Detail 39 (Tube Clip) is dimensioned as 28 ga and references a tolerance of (.020-.010). The parts list on sheet 1 specifies material grade UNS NO6625. Product Specification NCSX CSPEC-121-02-03 3.3.2.1 requires sheet, strip, and plate to conform to ASTM B443. ASTM B443 does not provide a thickness tolerance for plate less than 0.018-0.025" within the specification. With this in mind, we are moving forward with the plan of using material in the range of 0.010-0.020" for the Tube Clips. Please review and confirm we are making the correct interpretation. | RFD 12-003 will be generated to cover this request
2005-02-21 | PPPL Email | From: Michael E. Viola Sent: Monday, February 21, 2005 3:00 PM Major Tool will need the hard seals by July 1. ---------------------------------------------------------- From: Goranson, Paul L. Sent: Monday, February 21, 2005 10:11 AM Seals are a long lead item. There is only one supplier in the world. We have had drawing commented and are awaiting a preliminary budget quote and delivery time. A master template has to be made for fitting the seals and we expect instructions on how it should be made this week. Good news is that the seal is proper design and can be made with no problem. We could order viton material (0.211”) for preliminary leak checks if desired but it would not be good for bakeout. | Negotiating with Helicoflex? Template complete - order to go out this coming week ACTION - Goranson to advise of Delivery
2005-02-22 | MTM Email | From: McCorkle, Doug Sent: Tuesday, February 22, 2005 10:04 AM Attached is a sketch showing a possible scheme. The dots marked with "A" are representative of the holes we could add to the Port Extension Flanges. I didn't draw them on all flanges, but they could certainly be installed on them all. The dots marked "B" are representative of the monuments we will attach to the vessel exterior. The view in the upper right shows a closer look at what a monument will look like. They will be about a half inch in diameter, and will protrude about a half inch. All holes (on both the flanges and monuments) will be a precise 1/4" hole that will receive a common tooling ball or Laser SMR. If the flange holes are not necessary for PPPL we would prefer not to install them (we won't need them). We will need the vessel wall fiducials for in-process alignment assistance. If the monuments are not desired by PPPL, we can easily remove them prior to shipment. Also, as I mentioned before, it might be possible to make the monuments longer (say 1.375" long) with a precise hole on both ends, drill through the vessel wall and permanently weld them in place. This would provide internal reference datums. | ORNL Generate Drawing locating the fiducials
2005-02-23 | MTM Email | From: McCorkle, Doug Sent: Wednesday, February 23, 2005 11:23 AM (1) Please refer to SE120-004. I need to ensure I'm interpreting the Port Extension length requirements correctly. For example, if you look at sheet 4, zone C6, dimension 45.41 (see note 6). The dimension is not toleranced. Note six explains the dimension should be plus .50". We interpret the plus .50" is for the initial positioning and welding, and the half inch is the allowance for removing and re-fitting (at MTM). I am planning for each port to be plus 1/2" (minimum) at the time of welding. We will then trim, prep, and fit the port to the drawing dimension (45.41 in the example case) temporarily for final inspection. Our final inspection operation will verify the port (temporarily re-attached) checks to the drawing dimension. The ports would be delivered to achieve the drawing dimension (+/- normal weld shrinkage and distortion) at final installation (at PPPL). Now, if this is the correct interpretation, the two place decimal tolerance (according to the general tolerance block (UOS)) is only 0.010". I don't believe this is a realistic expectation for the process. Maintaining a +/- 0.06" would be doing very well for some of the ports. | Accepted |  |  | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-02-23 | MTM Email | (1 - continued) If my interpretation is accurate, please review your requirements and provide an achievable tolerance for each Port Extension length final trimmed and fit at MTM. => Note 6 revised on se120-004 sheet 1 to add +/- 0.125” length tolerances to ports after they are cut off and a .050” tolerance inspection dimension on SE120-004, sht 1. | Accepted |  |  | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-02-23 | MTM Email | (2) Also, Port Extension # 4 poses additional concerns. Note 7 leads me to believe the dimension (and GD&T tolerance) is inspected after welding and prior to cutting and re-fitting (similar to how #12 and NB are dimensioned). There is no provision for re-attachment dimension and tolerance. Some material will be lost in the process. We need to review this and make sure what you expect and what we can accomplish coincide. I'll be reviewing the process of cutting and re-attaching Port # 4 in greater detail with our fabricators later this week. | Accepted |  |  | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-02-24 | MTM Email | From: McCorkle, Doug Sent: Thursday, February 24, 2005 3:30 PM The weld that joins the leak check tube to the leak check block is specified as a 1/32" fillet. We are not able to produce a weld this small. This type of joint seems better suited for a silver solder. Please review this requirement and allow a soldered joint for all leak check tube to block attachments (examples on drawings SE120-005, SE122-006, and SE122-007). | RFD 12-004 will be generated to cover this request
2005-03-01 | MTM Email | From: McCorkle, Doug Sent: Tuesday, March 01, 2005 3:39 PM Subject: VVSA Alternate material request For some time now, we have been working with our material suppliers in developing the tubing and pipe requirements for the Port Extensions. We can now confirm the best approach (considering delivery and quality) will be to manufacture the 6", 8", and 10" tubing (roll and weld from plate). We are still researching the 2.5" and 3.5" pipe. We plan to follow ASTM B705 as a guideline during production, but the material certification will be for ASTM B443. Please review and advise if this approach is acceptable with PPPL. => RFD 12-001 submitted 3/8/2005 & ECP-026 approved 3/15/2005. | Accepted. RFD-12-001 | ECP-026 | Addendum 3-4 (Issued 3/15/2005 although dated 3/11/2005) |  | NCSX-CSPEC-121-02-05 (TBD)
2005-03-08 | RFD-12-001 | DEVIATION: Manufacture the 6", 8", and 10" tubing (roll and weld from plate). Follow ASTM B705 as a guideline during production. The material certification will be for ASTM B443. JUSTIFICATON: For some time now, we have been working with our material suppliers in developing the tubing and pipe requirements for the Port Extensions. We can now confirm the best approach (considering delivery and quality) will be to manufacture the 6", 8", and 10" tubing (roll and weld from plate). We are still researching the 2.5" and 3.5" pipe. We plan to follow ASTM B705 as a guideline during production, but the material certification will be for ASTM B443. Cog Engineer, Paul Goranson DISPOSITION: Drawing calls out tubing which spec calls out to be made per B444 or B705. It(spec) also calls out sheet as B443. A simple approval for substitution should take care of things. | RFD-12-001
2005-03-15 | Addendum 3-4 | NCSX Project approval is hereby granted for the following Deviation to NCSX-CSPEC-121-02 requested by Mr. McCorkle of MTM on 7 March 2005: “Manufacture the 6”, 8”, and 10” tubing (roll and weld from plate). Follow ASTM B705 as a guideline during production. The material certification will be for ASTM B443.” |  |  | Addendum 3-4 | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-03-15 | MTM Email | From: McCorkle, Doug Sent: Tuesday, March 15, 2005 4:40 PM Subject: Missing VVSA drawings It appears the revision 1 download from your FTP site is missing drawing numbers SE120-006 and SE120-007 (derived from SE120-003 parts list). Please review and advise as soon as possible. | Accepted. Correction to the parts list on se120-003, correctly calling out next assemblies se122-006 and se122-007 |  |  | 4945 & 4961 R1 | NCSX-CSPEC-121-02-04
2005-03-16 | RFD-12-002 | DEVIATION: The 2 1/2” Pipe: (1) Request authorizaton to substitute schedule 10 pipe for specified schedule 40 OR (2) Request authorization to substitute Haynes Alloy C-276 for ASYM B705/ASTM B444/ASTM B443. JUSTIFICATION: Excessive material lead time for schedule 40. | RFD-12-002 Approved | ECP-027
Notes: CSPEC (Rev 5) will be revised after RFD-12-002 approved and will add new Section 7 - Approved Deviations