Notes from Trip to Major Tool and J.P. Pattern, April 28-29, 2005

G. H. Neilson

Summary

- Major Tool is on top of both the MCWF and VVSA jobs.

NCSX Modular Coil Winding Forms, April 28, 2005

Major Tool and Machine, Indianapolis, IN

- Schedule: cannot commit to any improvement in the June 24 delivery at this time, but they are “still optimistic.” They are using extended shifts, overtime, and making a best effort.

- They are working 6 days/week, two 10 or 12-hour shifts per day, Sunday when possible.

- They have two machine operators (one per shift) and a programmer dedicated to the job.

- Things are going well, but they have had to experiment to find the most efficient combination of tools, tool paths, etc., for the rough machining. Their original ideas didn’t work out as well as expected but fortunately there are many combinations available and they found a way that is working well now.  Practice machining of the prototype gave them a leg up but didn’t resolve everything.

- The casting has 1-in. of stock. They machine it down to ¼-in., cut the break leaving ¼ in. of stock there also. Make up the break in the relaxed state, machine it down to 0.030-0.050, then finish machine.

- The casting quality is outstanding, no  sand or porosity. NCSX shouldn’t worry so much about weld repairs, they said. It’s a normal part of both the casting and the machining process and does not cause them any problems during machining. It’s more of an economic problem for them and the foundry.

- They have three interchangeable fixtures plus the Remmele Type C fixture. If necessary to handle peak production, they can build a fourth. Takes 3 weeks.

- If we wanted to open up the lead slot, it’s not a problem.

- This is going very well.

- From Nancy Horton, indications that the project has stressed Lawton, resulting in loss of enthusiasm and creating some tension between Lawton and other team members. Hints of budget problems keep recurring but EIO is managing it so far. Hopefully they’ll deliver their last pattern by August, completing their scope.

NCSX VVSA, April 28, 2005

Major Tool and Machine, Indianapolis, IN

- They are behind schedule on the 60-deg. fixture, but the lower half will be ready in time to start welding up panels 1-5, possibly next week.

- The 60-deg. fixture is critical and has been the subject of intense focus internally.  It is being fabricated now. Parts of it are scattered about the facility.

- The production panels have come in from the supplier without the expected finish, apparently a “misunderstanding” between MTM and the supplier. Their problem not ours.  MTM will finish the plates themselves or get it done by an outside source. Today’s problem, but not a big deal.

- They will probably not use the development panels for production because of the finish issue.

- Forming is going well.  I was amazed that they stick pieces of ¼ inch plywood (looks like trash swept up from my garage floor) between the panel and the die to make local contour adjustments. We’re talking 3/8-in. inconel and a 500-ton press!!

- Also amazing: the inspection gages. As Brad noted, they look like a third grade science project (all rubber and glue and Al honeycomb sandwich panels) but are amazingly simple, lightweight, and effective.

- The ball is in PPPL’s court on process outlines Lots 1, 2, and 3 (the 120-deg. segments). We are not delinquent. Just noted.

- They only material availability issue is the 3½  in. ports.

- Regarding the magnetized 304 stainless conflat flanges.  We accept mu<1.2 in the welds.  The flanges may not make that much difference, if the permeability is localized.  Mike V. is looking into serviceability of 316 flanges, I understand.

- Brad and MTM agreed on placement of landmarks on the inside of the vessel.

- Risks: problems not confronted on the prototype may potentially arise when they form “Panel 5” (large and deep) or in welding up the 60- or 120-degree segments.

- This is going very well.

QPS MCWF, April 29, 2005

J.P. Pattern

- .

QPS MCWF, April 29, 2005

Waukesha Kramer International

- .