## Sheet1
Task me | Contract Start | Contract Finish | Plan start | Plan Finish | Dur | Slack | MEV Finish | was start Feb 1 | was finish feb 1 | was start dec 14 | was finish dec 14 | Actual Start | Actual Finish | % complete | Milestone payment | prorated amount
0
Submit Proposal | 2004-07-22 08:00 | 2004-07-22 08:00 |  |  | 0 | [8 empty] | 100 |  | 0
Teleconference to discuss Proposal | 2004-07-26 08:00 | 2004-07-30 17:00 |  |  | 0 | [6 empty] | 2004-07-26 08:00 | 2004-07-30 17:00 | 100 |  | 0
Receive Order | 2004-09-24 17:00 | 2004-09-24 17:00 |  |  | 0 | [6 empty] | 2004-08-13 08:00 | 2004-09-24 17:00 | 100 |  | 0
WO# 65678 PPPL VVSA Lot # 14 | 1999-01-01 08:00 | 2006-01-26 17:00 |  |  | 0 | [10 empty] | 0
Start Up/Engineering QLI#1 | 2004-09-24 08:00 | 2005-11-04 17:00 |  |  | 0 | [10 empty] | 0
Process Order | 2004-09-24 08:00 | 2005-05-20 17:00 | 2004-09-24 08:00 | 2005-07-30 | 308.6667 | [6 empty] | 2004-09-24 08:00 | 2005-07-30 | 100 |  | 0
Sect 5.1 Segmentation Scheme | 2004-11-04 08:00 | 2004-11-19 17:00 |  |  | 0 | [6 empty] | 2004-11-04 08:00 | 2004-11-20 | 100 | 75000 | 75000
Sect 5.1.2 Fiducials | 2005-11-04 08:00 | 2005-11-04 17:00 | 2006-02-23 17:00 | 2006-02-24 17:00 | 1 | [8 empty] | 98 |  | 0
Sect 5.1.3 Proc Outline & Asc Proc. | 2004-09-24 08:00 | 2005-04-29 17:00 | 2004-09-24 08:00 | 2005-05-31 17:00 | 249.375 | [6 empty] | 2004-09-24 08:00 | 2005-05-31 17:00 | 100 | 95000 | 95000
Special Tooling QLI# 2 | 2004-09-20 08:00 | 2005-07-22 17:00 |  |  | 0 | [10 empty] | 0
Dies & Gages Lot # 10 | 2004-09-20 08:00 | 2005-05-12 17:00 |  |  | 0 | [10 empty] | 0
Engineering | 2004-09-20 08:00 | 2005-01-28 17:00 |  |  | 0 | [6 empty] | 2004-09-20 08:00 | 2005-01-29 | 100 |  | 0
Procure Materials | 2004-11-15 08:00 | 2005-03-11 17:00 |  |  | 0 | [6 empty] | 2004-11-15 08:00 | 2005-03-11 17:00 | 100 | 315000 | 315000
Machine Complete | 2005-02-21 08:00 | 2005-04-07 17:00 |  |  | 0 | [6 empty] | 2005-02-21 08:00 | 2005-04-07 17:00 | 100 |  | 0
Deburr | 2005-02-28 08:00 | 2005-04-08 17:00 |  |  | 0 | [6 empty] | 2005-02-28 08:00 | 2005-04-08 17:00 | 100 |  | 0
Inspection | 2005-03-01 08:00 | 2005-04-11 17:00 |  |  | 0 | [6 empty] | 2005-03-01 08:00 | 2005-04-11 17:00 | 100 | 340644 | 340644
Development Panels | 2005-03-31 08:00 | 2005-05-12 17:00 | 2005-04-08 08:00 | 2005-06-10 17:00 | 63.375 | [6 empty] | 2005-03-31 08:00 | 2005-06-10 17:00 | 100 |  | 0
Fixtures (2) 60 degree Lot # 11 | 2004-10-25 08:00 | 2005-05-13 17:00 |  |  | 0 | [10 empty] | 0
Engineering | 2004-10-25 08:00 | 2005-03-04 17:00 |  |  | 0 | [6 empty] | 2004-10-25 08:00 | 2005-03-04 17:00 | 100 |  | 0
Procure Materials | 2005-03-06 08:00 | 2005-03-30 17:00 |  |  | 0 | [6 empty] | 2005-03-06 08:00 | 2005-03-30 17:00 | 100 |  | 0
Fab & Machine Complete | 2005-03-13 08:00 | 2005-04-15 17:00 | 2005-04-15 17:00 | 2005-06-10 17:00 | 56 | [6 empty] | 2005-03-13 08:00 | 2005-06-10 17:00 | 100 |  | 0
Assemble | 2005-03-28 08:00 | 2005-04-29 17:00 | 2005-04-29 17:00 | 2005-06-17 17:00 | 49 | [6 empty] | 2005-03-28 08:00 | 2005-06-17 17:00 | 100 |  | 0
Deburr | 2005-04-12 08:00 | 2005-05-06 17:00 | 2005-05-06 17:00 | 2005-06-20 17:00 | 45 | [6 empty] | 2005-04-12 08:00 | 2005-06-20 17:00 | 100 |  | 0
Inspection | 2005-04-22 08:00 | 2005-05-13 17:00 | 2005-05-13 17:00 | 2005-06-23 17:00 | 41 | [6 empty] | 2005-04-22 08:00 | 2005-06-23 17:00 | 100 |  | 0
Fixture (3) 120 degree Lot # 12 | 2005-01-31 08:00 | 2005-07-22 17:00 |  |  | 0 | [10 empty] | 0
Engineering | 2005-01-31 08:00 | 2005-05-06 17:00 | 2005-04-15 08:00 | 2005-06-08 17:00 | 54.375 | [6 empty] | 2005-01-30 08:00 | 2005-06-08 17:00 | 100 |  | 0
Procure Materials | 2005-04-29 08:00 | 2005-05-13 17:00 | 2005-06-08 17:00 | 2005-06-13 17:00 | 5 | [6 empty] | 2005-06-08 17:00 | 2005-06-13 17:00 | 100 | 220000 | 220000
Fab & Machine Complete | 2005-05-13 08:00 | 2005-06-23 17:00 | 2005-06-13 17:00 | 2005-07-29 17:00 | 46 | [6 empty] | 2005-06-13 17:00 | 2005-07-29 17:00 | 100 |  | 0
Assemble | 2005-05-20 08:00 | 2005-07-22 17:00 | 2005-06-22 08:00 | 2005-07-29 17:00 | 37.375 | [6 empty] | 2005-07-01 08:00 | 2005-07-29 17:00 | 100 |  | 0
Deburr | 2005-07-04 08:00 | 2005-07-14 17:00 | 2005-07-04 08:00 | 2005-07-29 17:00 | 25.375 | [6 empty] | 2005-07-04 08:00 | 2005-07-29 17:00 | 100 |  | 0
Inspection | 2005-07-04 08:00 | 2005-07-14 17:00 | 2005-09-04 08:00 | 2005-07-29 17:00 | -36.625 | [6 empty] | 2005-07-07 08:00 | 2005-07-15 17:00 | 100 |  | 0
Procure Vessel Material | 2004-10-29 08:00 | 2005-04-22 17:00 | 2004-10-29 08:00 | 2005-05-31 17:00 | 214.375 | [6 empty] | 2004-10-29 08:00 | 2005-05-31 17:00 | 100 | 390000 | 390000
Production Panels Period #1 Lot # 4 | 2005-04-22 08:00 | 2005-05-23 17:00 | 2005-06-10 08:00 | 2005-08-12 17:00 | 63.375 | [6 empty] | 2005-06-10 08:00 | 2005-08-12 17:00 | 100 | 260000 | 260000
Production Panels Period #2 Lot # 5 | 2005-05-24 08:00 | 2005-06-24 17:00 | 2005-06-24 17:00 | 2005-09-12 17:00 | 80 | [6 empty] | 2005-06-24 17:00 | 2005-09-12 17:00 | 100 | 240000 | 240000
Production Panels Period #3 Lot # 6 | 2005-05-30 08:00 | 2005-07-05 17:00 | 2005-06-28 17:00 | 2005-09-16 17:00 | 80 | [6 empty] | 2005-06-30 08:00 | 2005-09-16 17:00 | 100 | 240000 | 240000
Port Ext,Misc Hardware Period #1 Lot # 7 | 2005-03-23 08:00 | 2005-07-12 17:00 | 2005-04-04 08:00 | 2005-12-09 17:00 | 249.375 | [6 empty] | 2005-03-23 08:00 | 2005-12-09 17:00 | 100 |  | 0
Port Ext,Misc Hardware Period # 2 Lot # 8 | 2005-03-23 08:00 | 2005-08-16 17:00 | 2005-04-04 08:00 | 2005-12-12 17:00 | 252.375 | [6 empty] | 2005-03-23 08:00 | 2005-12-12 17:00 | 100 |  | 0
Port Ext,Misc Hardware Period # 3 Lot # 9 | 2005-03-23 08:00 | 2005-09-13 17:00 | 2005-04-04 08:00 | 2006-01-23 17:00 | 294.375 | [6 empty] | 2005-04-04 08:00 | 2006-01-23 17:00 | 100 |  | 0
(1) Spacer (3) Port Ext. Fixtures Lot # 13 | 2005-06-06 08:00 | 2005-09-16 17:00 | 2005-09-16 17:00 | 2006-01-28 17:00 | 134 | [6 empty] | 2005-09-16 17:00 | 2006-01-28 17:00 | 100 |  | 0
First 120 deg seg QLI #3 Lot # 1 | 1999-01-01 08:00 |  | 2005-06-10 08:00 | 2005-09-23 17:00 | 105.375 | [10 empty] | 0
1st 60 deg segment | 2005-05-02 08:00 | 2005-06-13 17:00 | 2005-06-10 08:00 | 2005-08-12 17:00 | 63.375 | [6 empty] | 2005-06-17 08:00 | 2005-08-12 17:00 | 100 |  | 0
2nd 60 deg segment | 2005-05-23 08:00 | 2005-07-08 17:00 | 2005-06-23 08:00 | 2005-08-15 17:00 | 53.375 | [6 empty] | 2005-07-07 08:00 | 2005-08-15 17:00 | 100 |  | 0
Join two pieces | 2005-07-10 08:00 | 2005-08-02 17:00 | 2005-08-12 08:00 | 2005-09-08 17:00 | 27.375 | [6 empty] | 2005-08-12 08:00 | 2005-09-12 17:00 | 100 | 400000 | 400000
Machine for Ports | 2005-08-03 08:00 | 2005-08-18 17:00 | 2005-09-08 08:00 | 2005-09-23 17:00 | 15.375 | -0.375 | [5 empty] | 2005-09-12 08:00 | 2005-10-01 17:00 | 100 |  | 0
Weld Ports | 1999-01-01 08:00 | 2005-09-16 17:00 | 2005-10-05 08:00 | 2006-01-17 17:00 | 104.375 | 11.625 | [5 empty] | 2005-10-05 08:00 | 2005-12-01 17:00 |  |  | 0
Round Ports (less dome ports) | 1999-01-01 08:00 |  | 2005-10-05 08:00 | 2005-12-09 17:00 | 65.375 | [6 empty] | 2005-10-05 08:00 | 2005-12-07 17:00 | 100 |  | 0
Dome Ports 17 & 18 | 1999-01-01 17:00 |  | 2005-12-09 17:00 | 2005-12-16 17:00 | 7 | 0 | [5 empty] | 2005-12-07 17:00 | 2005-12-12 17:00 | 100 |  | 0
(8) Bosses | 1999-01-01 17:00 |  | 2005-12-16 08:00 | 2005-12-20 17:00 | 4.375 | -0.375 | [5 empty] | 2005-12-12 17:00 | 2005-12-20 17:00 | 100 |  | 0
100% Laser Scan Layout and Weld Flanges | 1999-01-01 17:00 |  | 2005-12-20 08:00 | 2006-01-09 17:00 | 20.375 | -0.375 | [5 empty] | 2005-12-20 08:00 | 2006-01-09 17:00 | 100 |  | 0
Polish and Rough Clean Interior | 1999-01-01 17:00 |  | 2006-01-09 08:00 | 2006-01-16 17:00 | 7.375 | -0.375 | [5 empty] | 2006-01-09 08:00 | 2006-01-16 17:00 | 100 |  | 0
Weld on Spacer and Covers | 1999-01-01 17:00 |  | 2006-01-16 08:00 | 2006-01-17 17:00 | 1.375 | -0.375 | [5 empty] | 2006-01-16 08:00 | 2006-01-17 17:00 | 100 |  | 0
Vacuum Test | 1999-01-01 08:00 | 2005-10-21 17:00 | 2006-01-17 08:00 | 2006-02-17 17:00 | 31.375 | -0.375 | [9 empty] | 0
First Vacuum Test | 1999-01-01 08:00 |  | 2006-01-17 08:00 | 2006-01-24 17:00 | 7.375 | 0 | [5 empty] | 2006-01-17 08:00 | 2006-01-24 17:00 | 100 |  | 0
Heat Blankets | 1999-01-01 08:00 |  | 2006-01-24 17:00 | 2006-01-30 17:00 | 6 | 0 | [5 empty] | 2006-01-24 17:00 | 2006-01-30 17:00 | 100 |  | 0
Thermal Cycle | 1999-01-01 08:00 |  | 2006-01-30 17:00 | 2006-02-08 17:00 | 9 | 0 | [5 empty] | 2006-01-30 17:00 | 2006-02-08 17:00 | 100 |  | 0
Final Vacuum Test | 1999-01-01 08:00 |  | 2006-02-08 17:00 | 2006-02-15 17:00 | 7 | 0 | [5 empty] | 2006-02-08 17:00 | 2006-02-15 17:00 | 100 |  | 0
Laser check after Vacuum Test | 1999-01-01 08:00 |  | 2006-02-15 17:00 | 2006-02-17 17:00 | 2 | 0 | [5 empty] | 2006-02-15 17:00 | 2006-02-17 17:00 | 100 |  | 0
Cut Off Ports | 2005-10-24 08:00 | 2005-11-04 17:00 | 2006-02-17 17:00 | 2006-03-06 17:00 | 17 | 0 | [5 empty] | 2006-02-17 17:00 | 2006-03-06 17:00 | 100 |  | 0
Final Machine | 2005-09-19 08:00 | 2005-10-07 17:00 | 2006-03-06 17:00 | 2006-03-15 17:00 | 9 | 0 | 2006-03-15 | 2006-03-06 17:00 | 2006-03-13 17:00 |  |  |  |  | 100 |  | 0
Tack on Ports, weld on tube and block (NEW) | 1999-01-01 08:00 |  | 2006-03-15 17:00 | 2006-04-20 17:00 | 36 | 0 | 2006-04-20 | [6 empty] | 20 |  | 0
Final Inspection | 1999-01-01 08:00 | 1999-01-01 17:00 | 2006-04-20 17:00 | 2006-04-24 17:00 | 4 | 0 | 2006-04-24 | 2006-03-13 17:00 | 2006-03-20 17:00 | [6 empty] | 0
Pack for Shipping #1 | 2005-11-07 08:00 | 2005-11-11 17:00 | 2006-04-24 17:00 | 2006-04-28 17:00 | 4 | 0 | 2006-04-28 | 2006-03-20 17:00 | 2006-03-24 17:00 | [6 empty] | 0
Receive at PPPL | 2005-11-14 08:00 | 2005-11-15 17:00 | 2006-04-28 17:00 | 2006-05-01 17:00 | 3 | 0 | 2006-05-01 | 2006-03-24 17:00 | 2006-03-27 17:00 | [5 empty] | 375560 | 0
Second 120 deg seg QLI# 3 Lot # 2 | 1999-01-01 08:00 |  | 2005-08-12 08:00 | 2005-12-30 17:00 | 140.375 | [10 empty] | 0
60 deg segment | 2005-06-24 08:00 | 2005-07-22 17:00 | 2005-08-12 08:00 | 2005-09-09 17:00 | 28.375 | [6 empty] | 2005-08-12 08:00 | 2005-09-09 17:00 | 100 |  | 0
60 deg segment | 2005-07-25 08:00 | 2005-08-19 17:00 | 2005-08-26 08:00 | 2005-10-07 17:00 | 42.375 | [6 empty] | 2005-08-26 08:00 | 2005-10-07 17:00 | 100 |  | 0
Join two pieces | 2005-08-22 08:00 | 2005-09-05 17:00 | 2005-10-07 17:00 | 2005-11-16 08:00 | 39.625 | 0 | [5 empty] | 2005-10-07 17:00 | 2005-11-16 08:00 | 100 | 405000 | 405000
Machine for Ports | 2005-09-05 08:00 | 2005-09-23 17:00 | 2006-01-04 08:00 | 2006-01-19 17:00 | 15.375 | 49 | [5 empty] | 2005-12-27 08:00 | 2006-01-19 17:00 | 100 |  | 0
Weld Ports | 1999-01-01 08:00 | 2005-10-21 17:00 | 2006-01-20 08:00 | 2006-03-03 17:00 | 42.375 | 0.625 | [9 empty] | 0
NB Port | 1999-01-01 08:00 |  | 2006-01-20 08:00 | 2006-01-25 17:00 | 5.375 | 0 | [5 empty] | 2006-01-20 08:00 | 2006-01-25 17:00 | 100 |  | 0
Port 4 | 1999-01-01 08:00 |  | 2006-01-25 17:00 | 2006-01-31 17:00 | 6 | 0 | [5 empty] | 2006-01-25 17:00 | 2006-01-31 17:00 | 100 |  | 0
Port 12 | 1999-01-01 08:00 |  | 2006-01-31 17:00 | 2006-02-06 17:00 | 6 | 0 | [5 empty] | 2006-01-31 17:00 | 2006-02-06 17:00 | 100 |  | 0
Domes | 1999-01-01 08:00 |  | 2006-02-06 17:00 | 2006-02-09 17:00 | 3 | 0 | [5 empty] | 2006-02-06 17:00 | 2006-02-09 17:00 | 100 |  | 0
Round Ports (less dome ports) | 1999-01-01 08:00 |  | 2006-02-09 17:00 | 2006-02-15 17:00 | 6 | 0 | [5 empty] | 2006-02-09 17:00 | 2006-02-15 17:00 | 100 |  | 0
Dome Ports 17 & 18 | 1999-01-01 17:00 |  | 2006-02-15 17:00 | 2006-02-20 17:00 | 5 | 0 | [5 empty] | 2006-02-15 17:00 | 2006-02-20 17:00 | 100 |  | 0
(8) Bosses | 1999-01-01 17:00 |  | 2006-02-20 17:00 | 2006-03-03 17:00 | 11 | 0 |  | 2006-02-20 17:00 | 2006-02-23 17:00 |  |  | 2006-02-20 17:00 | 2006-02-23 17:00 | 100 |  | 0
100% Laser Scan Layout and Weld Flanges | 1999-01-01 17:00 |  | 2006-03-06 08:00 | 2006-03-10 17:00 | 4.375 | 2.625 | 2006-04-06 | 2006-02-23 17:00 | 2006-03-06 17:00 |  |  |  |  | 80 |  | 0
Polish and Rough Clean Interior | 1999-01-01 17:00 |  | 2006-03-13 08:00 | 2006-03-15 17:00 | 2.375 | 2.625 | 2006-04-08 09:00 | 2006-03-06 17:00 | 2006-03-09 08:00 | [6 empty] | 0
Weld on Spacer and Covers | 1999-01-01 17:00 |  | 2006-03-16 08:00 | 2006-03-17 17:00 | 1.375 | 0.625 | 2006-04-09 18:00 | 2006-03-09 08:00 | 2006-03-13 17:00 | [6 empty] | 0
Vacuum Test | 1999-01-01 08:00 | 2005-11-25 17:00 | 2006-03-20 08:00 | 2006-03-31 17:00 | 11.375 | 2.625 | 2006-04-21 03:00 | 2006-03-14 08:00 | 2006-04-12 17:00 | [6 empty] | 0
First Vacuum Test | 1999-01-01 08:00 |  | 2006-03-20 08:00 | 2006-03-24 17:00 | 4.375 | -11.375 | 2006-04-25 12:00 | 2006-03-14 08:00 | 2006-03-21 08:00 | [6 empty] | 0
Heat Blankets (deleted) | 1999-01-01 08:00 |  |  |  | 0 |  | 2006-04-25 12:00 | 2006-03-21 08:00 | 2006-03-24 08:00 | [6 empty] | 0
Thermal Cycle (deleted) | 1999-01-01 08:00 |  |  |  | 0 |  | 2006-04-25 12:00 | 2006-03-24 08:00 | 2006-03-30 08:00 | [6 empty] | 0
Final Vacuum Test | 1999-01-01 08:00 |  | 2006-03-27 08:00 | 2006-03-28 17:00 | 1.375 |  | 2006-04-26 21:00 | 2006-03-30 08:00 | 2006-04-10 08:00 | [6 empty] | 0
Laser check after Vacuum Test | 1999-01-01 08:00 |  | 2006-03-29 08:00 | 2006-03-31 17:00 | 2.375 | 0.625 | 2006-04-29 06:00 | 2006-04-10 08:00 | 2006-04-12 17:00 | [6 empty] | 0
Cut Off Ports | 2005-11-28 08:00 | 2005-12-09 17:00 | 2006-04-03 08:00 | 2006-04-11 17:00 | 8.375 | 2.625 | 2006-05-07 15:00 | 2006-04-12 17:00 | 2006-04-26 17:00 | [6 empty] | 0
Final Machine | 2005-10-24 08:00 | 2005-11-11 17:00 | 2006-04-12 08:00 | 2006-04-21 17:00 | 9.375 | 0.625 | 2006-05-17 | 2006-04-26 17:00 | 2006-05-03 17:00 | [6 empty] | 0
Tack on Ports, weld on tube and block (NEW) | 1999-01-01 08:00 |  | 2006-04-24 08:00 | 2006-05-02 17:00 | 8.375 | 2.625 | 2006-05-25 09:00 | [8 empty] | 0
Final Inspection | 1999-01-01 08:00 |  | 2006-05-03 17:00 | 2006-05-09 17:00 | 6 | 1 | 2006-05-31 09:00 | [8 empty] | 0
Pack for Shipping #2 | 2005-12-12 08:00 | 2005-12-16 17:00 | 2006-05-09 17:00 | 2006-05-12 17:00 | 3 | 0 | 2006-06-03 09:00 | [8 empty] | 0
Receive at PPPL | 2005-12-19 08:00 | 2005-12-22 17:00 | 2006-05-12 17:00 | 2006-05-15 17:00 | 3 | 0 | 2006-06-06 09:00 | [7 empty] | 375000 | 0
Third 120 deg seg QLI# 3 Lot # 3 | 1999-01-01 08:00 |  | 2005-09-30 08:00 | 2006-05-12 17:00 | 224.375 | [10 empty] | 0
60 deg segment | 2005-08-01 08:00 | 2005-08-26 17:00 | 2005-09-30 08:00 | 2006-01-23 08:00 | 115 | [5 empty] | 2006-01-06 17:00 | 2005-09-30 08:00 | 2006-01-23 08:00 | 100 |  | 0
60 deg segment | 2005-09-04 08:00 | 2005-09-30 17:00 | 2005-12-01 08:00 | 2006-01-31 17:00 | 61.375 | [5 empty] | 2006-01-06 17:00 | 2005-12-01 08:00 | 2006-01-31 17:00 | 100 |  | 0
Join two pieces | 2005-10-03 08:00 | 2005-10-17 17:00 | 2006-01-23 08:00 | 2006-02-10 17:00 | 18.375 | -8.375 |  |  |  | 2006-01-09 08:00 | 2006-01-19 17:00 | 2006-01-23 08:00 | 2006-02-10 17:00 | 100 | 375000 | 375000
Machine for Ports | 2005-10-17 08:00 | 2005-10-28 17:00 | 2006-03-16 08:00 | 2006-04-21 17:00 | 36.375 | 33.625 | 2006-04-21 | 2006-02-02 17:00 | 2006-02-16 17:00 | 2006-01-19 17:00 | 2006-02-02 17:00 |  |  | 55 |  | 0
Weld Ports | 1999-01-01 08:00 | 2005-11-18 17:00 | 2006-03-13 08:00 | 2006-04-06 17:00 | 24.375 | -39.375 | 2006-05-15 09:00 | 2006-02-16 17:00 | 2006-03-30 17:00 | 2006-02-06 08:00 | 2006-03-30 17:00 |  |  |  |  | 0
NB | 1999-01-01 08:00 |  | 2006-03-13 08:00 | 2006-03-17 08:00 | 4 | -24.375 | 2006-05-19 09:00 | 2006-02-16 17:00 | 2006-02-22 17:00 | 2006-02-06 08:00 | 2006-02-10 08:00 |  |  |  |  | 0
Port 4 | 1999-01-01 08:00 |  | 2006-03-17 08:00 | 2006-03-22 08:00 | 5 | 0 | 2006-05-24 09:00 | 2006-02-22 17:00 | 2006-02-28 17:00 | 2006-02-10 08:00 | 2006-02-17 08:00 |  |  |  |  | 0
Port 12 | 1999-01-01 08:00 |  | 2006-03-22 08:00 | 2006-03-27 08:00 | 5 | 0 | 2006-05-29 09:00 | 2006-03-01 17:00 | 2006-03-07 17:00 | 2006-02-17 08:00 | 2006-02-24 08:00 |  |  |  |  | 0
Domes | 1999-01-01 08:00 |  | 2006-03-27 08:00 | 2006-03-29 08:00 | 2 | 0 | 2006-05-31 09:00 | 2006-03-08 08:00 | 2006-03-15 17:00 | 2006-02-24 08:00 | 2006-03-01 08:00 |  |  |  |  | 0
Round Ports (less dome ports) | 1999-01-01 08:00 |  | 2006-03-29 08:00 | 2006-04-03 17:00 | 5.375 | 0 | 2006-06-05 18:00 | 2006-03-16 08:00 | 2006-03-23 17:00 | 2006-03-01 08:00 | 2006-03-09 08:00 |  |  |  |  | 0
Dome Ports 17 & 18 | 1999-01-01 17:00 |  | 2006-04-03 08:00 | 2006-04-06 17:00 | 3.375 | -0.375 | 2006-06-09 03:00 | 2006-03-24 08:00 | 2006-03-29 17:00 | 2006-03-09 08:00 | 2006-03-15 08:00 |  |  |  |  | 0
(8) Bosses | 1999-01-01 17:00 |  | 2006-04-07 08:00 | 2006-04-14 17:00 | 7.375 | 0.625 | 2006-06-16 12:00 | 2006-03-30 08:00 | 2006-04-04 17:00 | 2006-03-15 08:00 | 2006-03-21 08:00 |  |  |  |  | 0
100% Laser Scan Layout and Weld Flanges | 1999-01-01 17:00 |  | 2006-04-17 08:00 | 2006-04-20 17:00 | 3.375 | 2.625 | 2006-06-19 21:00 | 2006-04-05 08:00 | 2006-04-12 17:00 | 2006-03-21 08:00 | 2006-03-20 17:00 |  |  |  |  | 0
Polish and Rough Clean Interior | 1999-01-01 17:00 |  | 2006-04-21 08:00 | 2006-04-26 08:00 | 5 | 0.625 | 2006-06-24 21:00 | 2006-04-13 08:00 | 2006-04-17 17:00 | 2006-03-21 08:00 | 2006-03-24 17:00 |  |  |  |  | 0
Weld on Spacer and Covers | 1999-01-01 17:00 |  | 2006-04-26 08:00 | 2006-04-28 17:00 | 2.375 | 0 | 2006-06-27 06:00 | 2006-04-17 08:00 | 2006-04-21 17:00 | 2006-03-27 08:00 | 2006-03-30 17:00 |  |  |  |  | 0
Vacuum Test | 1999-01-01 08:00 | 2005-12-17 17:00 | 2006-05-01 08:00 | 2006-05-12 17:00 | 11.375 | 2.625 | 2006-07-08 15:00 | 2006-04-24 08:00 | 2006-05-09 17:00 | 2006-03-31 08:00 | 2006-05-09 17:00 |  |  |  |  | 0
First Vacuum Test | 1999-01-01 08:00 |  | 2006-05-01 08:00 | 2006-05-08 17:00 | 7.375 | -11.375 |  | 2006-04-24 08:00 | 2006-05-01 17:00 | 2006-03-31 08:00 | 2006-04-07 17:00 |  |  |  |  | 0
Heat Blankets (deleted) | 1999-01-01 08:00 |  |  |  | 0 | -38845.7083 |  |  |  | 2006-04-10 08:00 | 2006-04-12 17:00 |  |  |  |  | 0
Thermal Cycle (deleted) | 1999-01-01 08:00 |  |  |  | 0 | 0 |  |  |  | 2006-04-13 08:00 | 2006-04-19 17:00 |  |  |  |  | 0
Final Vacuum Test | 1999-01-01 08:00 |  | 2006-05-09 08:00 | 2006-05-10 17:00 | 1.375 | 38846.3333 |  | 2006-05-05 17:00 | 2006-05-12 17:00 | 2006-04-20 08:00 | 2006-05-04 17:00 |  |  |  |  | 0
Laser check after Vacuum Test | 1999-01-01 08:00 |  | 2006-05-11 08:00 | 2006-05-12 17:00 | 1.375 | 0.625 | 2006-07-09 | 2006-05-15 08:00 | 2006-05-19 17:00 | 2006-05-05 08:00 | 2006-05-09 17:00 |  |  |  |  | 0
Cut Off Ports | 2006-01-05 08:00 | 2006-01-17 17:00 | 2006-05-15 08:00 | 2006-05-19 17:00 | 4.375 | 2.625 | 2006-07-13 09:00 | 2006-05-22 08:00 | 2006-05-29 17:00 | 2006-05-10 08:00 | 2006-05-24 17:00 |  |  |  |  | 0
Final Machine | 2005-11-21 08:00 | 2005-12-02 17:00 | 2006-05-22 08:00 | 2006-05-26 17:00 | 4.375 | 2.625 | 2006-07-17 18:00 | 2006-05-29 08:00 | 2006-06-05 17:00 | 2006-05-25 08:00 | 2006-06-01 17:00 |  |  |  |  | 0
Tack on Ports, weld on tube and block (NEW) | 1999-01-01 08:00 |  | 2006-05-29 08:00 | 2006-06-05 17:00 | 7.375 | 2.625 | 2006-07-25 03:00 | [8 empty] | 0
Final Inspection | 1999-01-01 08:00 |  | 2006-06-06 08:00 | 2006-06-09 17:00 | 3.375 | 0.625 | 2006-07-28 12:00 |  |  | 2006-06-02 08:00 | 2006-06-08 17:00 |  |  |  |  | 0
Pack for Shipping #3 | 2006-01-17 08:00 | 2006-01-20 17:00 | 2006-06-09 08:00 | 2006-06-12 17:00 | 3.375 | -0.375 | 2006-07-31 21:00 | MTM Date: |  | 2006-06-09 08:00 | [5 empty] | 0
Receive at PPPL | 2006-01-23 08:00 | 2006-01-26 17:00 | 2006-06-13 08:00 | 2006-06-16 17:00 | 3.375 | 0.625 | 2006-08-04 06:00 | 2006-07-25 17:00 | [6 empty] | 375000 | 0
Tooling Deliveries | 2006-01-23 08:00 | 2006-02-01 17:00 | 2006-06-13 08:00 | 2006-06-23 17:00 | 10.375 | -3.375 | [9 empty] | 0
Pack for PPPL - Tooling | 2006-01-23 08:00 | 2006-01-27 17:00 | 2006-06-13 08:00 | 2006-06-19 17:00 | 6.375 | -10.375 | [9 empty] | 0
Receive at PPPL - Tooling | 2006-01-30 08:00 | 2006-02-01 17:00 | 2006-06-20 08:00 | 2006-06-23 17:00 | 3.375 | 0.625 | [8 empty] | 486000 | 0
Total value of work performed | [15 empty] | 3355644
Formulas:
MEV Finish = [MEV Finish, row above]+[Dur]
was start Feb 1 = [Plan Finish]+39