| Projected Date | Performance Description | Performance Based Payment | Payments unchanged on 2/4/05 schedule | Line Item on 2/4/05 schedule | Planned Finish per 2/4/05 schedule |
| --- | --- | --- | --- | --- | --- |
| 11/19/04 | Segmentation Scheme (*Line 10 of Reference) | $ 75,000 | $ 75,000 | 7 | Complete & Invoiced |
| 12/10/04 | Procedure Outline & Assoc Procedure (*Line 6 of Reference) | $ 95,000 | $ 95,000 | 9 | 3/4/05 |
| 12/17/04 | Fiducials (*Line 29 of Reference) | $ 55,000 | $ 55,000 | 8 | Complete |
| 1/07/05 | Die material procured (*Line 11 of Reference) | $ 215,000 | $ 215,000 | 13 | 3/9/05 |
| 2/04/05 | Procure Material (120° Fixture) (*Line 24 of Reference) | $ 220,000 | $ 220,000 | 27 | 5/13/05 |
| 2/11/05 | Dies fabricated (*Line14 of Reference) | $ 239,000 | $ 239,000 | 16 | 3/30/05 |
| 2/25/05 | Vessel material procured (*Line 30 of Reference) | $ 290,000 | $ 290,000 | 32 | 3/21/05 |
| 4/26/05 | Development panels (9 panels) (*Line 31 of Reference) | $ 260,000 | $ 260,000 | 33 | 5/2/05 |
| 5/17/05 | Production panels (9 – 18 panels) (*Line 32 of Reference) | $ 200,000 | $ 200,000 | 34 | 6/10/05 |
| 6/14/05 | One VVSA fabricated (*Line 37 of Reference) | $ 350,000 | $ 350,000 | 43 | 7/5/05 |
| 6/28/05 | Production panels (36 – 45 panels) (*Line 33 of Reference) | $ 200,000 | $ 200,000 | 35 | 7/5/05 |
| 7/19/04 | Second VVSA fabricated (*Line 48 of Reference) | $ 350,000 | $ 350,000 | 54 | ? |
| 8/23/05 | Third VVSA fabricated (*Line 59 of Reference) | $ 375,000 | $ 375,000 | 65 | ? |
| 10/19/05 | Receipt by PPPL of 1st VVSA (Subcontract Art I) | $ 375,560 | $ 375,560 | 50 | 11/7/05 |
| 10/31/05 | Receipt by PPPL of 2nd VVSA (Subcontract Art I) | $ 375,000 | $ 375,000 | 61 | ? |
| 11/22/05 | Receipt by PPPL of 3rd VVSA (Subcontract Art I) | $ 375,000 | $ 375,000 | 72 | ? |
| 12/01/05 | Delivery to PPPL of tooling (nine die sets, nine Inspection Gages for the formed panels, two 60° build fixtures, one 120° cradle to support the two 60° segments and one Field joint weldment fixture) (Subcontract Article I) | $ 486,000 | $ 486,000 | 74 | ? |
|  | Total | $4,535,560.00 | $4,535,560.00 |  |  |

* Reference:  Major Tool & Machine Gantt Chart, titled NCSX VVSA for PPP, Subcontract S005243-F, MTM WO# 65678, prepared by Mike Manual, dated 11/09/04 (2 pages)”