Major Tool & Machine, Inc.

Page: 1

1458 East 19th Street

MTM N/C: 18888

Date: 12/19/05

Indianapolis, IN 46218-4289

User ID: MCCORKLE

PRINCETON PLASMA PHYSICS LAB

Customer:

Telephone:

609-243-2441

Contact:

Mike Viola

S-04286-F

E-Mail:

609-243-2021

Fax:

S005243-F/Ln:1

Customer P.O.:

/

Part:

Lot 1 Vessel

Serial No./Qty:

2

Revision:

SE120-004

Drawing ID:

317-636-6433

Telephone:

DOUG MCCORKLE

Reported By:

Fax:

317-634-9420

E-Mail:

dMcCorkle@MajorTool.com

Problem:

The true position of lifting boss "a" on half "a" of the vessel checks 0.275 or 0.025 out of tolerance.

The true position of lifting boss "c" on half "a" of the vessel checks 0.451 of 0.201 out of tolerance.

The true position of lifting boss "c" on half "b" of the vessel checks 0.361 or 0.111 out of tolerance.

Proposed Disposition:

CONTINUE MANUFACTURING

SUBMITTING TO PPPL FOR DISPOSITION

0

Number of additional pages:

Customer Disposition:       [   ] Use As Is          [  ] Rework          [  ] Repair          [  ] Scrap          [  ] Replace

Date:

Title:

Technical Contact Approval:

Date:

Title:

Buyer Approval:

Title:

Date:

Major Tool Implemented By:

/Open

n:\mtmapps\Mtnonc14.qrp

Major Tool and Machine, Inc.  1458 East 19th Street, Indianapolis, IN 46218-4289  Tel: 317-636-6433  Fax: 317-634-9420

Nonconformance Report: Major Tool NC18888

This is for SE122-004 Bosses

Mike, please review the attached Non-conformance and provide disposition.  According to our fabricators, the Clevis Boss details have proven to be much more difficult to control (position) than we expected.

Problem:

The true position of lifting boss "a" on half "a" of the vessel checks 0.275 or 0.025 out of tolerance.

The true position of lifting boss "c" on half "a" of the vessel checks 0.451 of 0.201 out of tolerance.

The true position of lifting boss "c" on half "b" of the vessel checks 0.361 or 0.111 out of tolerance.

Best Regards, 
Doug McCorkle

Clarification (Viola):

Per SE122-004 Sheet 1, Bosses labeled “A” thru “D” correspond to Items 48-51 respectively.  Half “a” and “b” refer to half of the 120 degree section.  The values indicated are maximums relative to TPT of datum B and C (X Y Plan view).  I have asked if there is any tilt involved and they will get back to me.

Project Disposition:

Bosses A & B are alignment features. If the hole has been bored in the boss, the boss will have to be redone; otherwise we can accept the correctly drilled hole in a misplaced boss.

Boss C is a handling hole and may be used as is.

Project Disposition Revision 1:

After further consideration Boss A may be accepted as is because it is just slightly out of tolerance and the risk to repair it is greater than the alignment risk.  Major Tool stated that additional care will be placed on the remaining boss installations.

Boss C is a handling hole and may be used as is.

Approvals:

___________________________________________

Procurement Technical Representative

____________________________________________

Responsible Line Manager: