## Sheet1
NCSX Contract Plan and Reporting
Contract- S-04345-F
Date: | April 2, 2004 (revised to reflect cost overrun)
Schedule
A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X
Schedule D: Baseline; Schedule F: Forecast or Actual; Schedule H: Total; Schedule I: %; Schedule J: BCWP; Schedule K: Monthly Cost Baseline Plan (loaded $k); Schedule X: Estimate at | Calculation for cost overrun
Task Num. | Task Name w/ SOW Reference Number | Prerequisites (list task numbers) | Start | Finish | Start | Finish | Budget | Complete | (budget x %) | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | Completion | Precision PO 338 302 | 125000
Task 1 | 3.1.1 Mfg Methods for Fab VVSA (100%) |  | 2003-05-01 | 2003-05-30 | 2003-05-01 | 2003-05-30 | 12500 | 100% | 12500 | Monthly Cost Baseline Plan (loaded $k) May: 11.1; Monthly Cost Baseline Plan (loaded $k) Jun: 1.4 | 12.5 | Precision PO 338 400 | 10100
Task 2 | 3.1.3 Prelim MIT & QA Plans VVSA (100%) |  | 2003-05-01 | 2003-05-30 | 2003-05-01 | 2003-05-30 | 6900 | 100% | 6900 | Monthly Cost Baseline Plan (loaded $k) May: 2.8; Monthly Cost Baseline Plan (loaded $k) Jun: 4.1 | 6.9 | Total | 135100
Task 3 | 3.1.2 Sub Recommendations (50%) |  | 2003-05-01 | 2003-05-30 | 2003-05-01 | 2003-05-30 | 7100 | 100% | 7100 | Monthly Cost Baseline Plan (loaded $k) May: 1.9; Monthly Cost Baseline Plan (loaded $k) Jun: 4.9; Monthly Cost Baseline Plan (loaded $k) Jul: 0.3 | 7.1 | Precision Cost to date 3/31/04 | -179299
Task 4 | 3.1.4 Budgetary Cost & Schedule Est VVSA-3 units (50%) |  | 2003-05-14 | 2003-06-06 | 2003-05-01 | 2003-06-06 | 11900 | 100% | 11900 | Monthly Cost Baseline Plan (loaded $k) May: 1.5; Monthly Cost Baseline Plan (loaded $k) Jun: 10.4 | 11.9 | Precision Cost Estimated to completion | -42320
Task 5 | 3.3.1 Final MIT & QA Plans VVSA-3 units (30%) | 1 to 4, 7 to 9 | 2003-11-24 | 2003-02-16 | 2003-07-03 | 2004-03-01 | 14100 | 15% | 2115 | Monthly Cost Baseline Plan (loaded $k) Jul: 1.7; Monthly Cost Baseline Plan (loaded $k) Nov: 0; Monthly Cost Baseline Plan (loaded $k) Dec: 0; Monthly Cost Baseline Plan (loaded $k) Jan: 0; Monthly Cost Baseline Plan (loaded $k) Feb: 0; Monthly Cost Baseline Plan (loaded $k) Mar: 12.4; Monthly Cost Baseline Plan (loaded $k) Apr: 0 | 14.1 | Total Projected Cost from Precision | -221619
Task 6 | 3.3.2 Firm Fix Cost & Schedule Proposal (100%) | 1 to 4, 7 to 9 | 2003-02-23 | 2003-03-24 | 2004-02-01 | 2004-04-01 | 12300 | 0% | 0 | Monthly Cost Baseline Plan (loaded $k) Feb: 2.4; Monthly Cost Baseline Plan (loaded $k) Mar: 2.4; Monthly Cost Baseline Plan (loaded $k) Apr: 7.5 | 12.3 | Cost Overrun | -86519
Task 7 | 3.2.1 MIT & QA Plans for PVVS (100%) | 1 to 4 | 2003-06-16 | 2003-08-25 | 2003-06-09 | 2004-02-01 | 42400 | 90% | 38160 | Monthly Cost Baseline Plan (loaded $k) Jun: 8.4; Monthly Cost Baseline Plan (loaded $k) Jul: 14.2; Monthly Cost Baseline Plan (loaded $k) Aug: 1; Monthly Cost Baseline Plan (loaded $k) Dec: 9.9; Monthly Cost Baseline Plan (loaded $k) Jan: 6.4; Monthly Cost Baseline Plan (loaded $k) Feb: 2.5 | 42.4 | Est of Rohwedder Engineering/Admin support increase | -8651.9
Task 8 | 3.2.2 PVVS Manufacturing (100%) | 1 to4, 7, 9 | 2003-09-15 | 2003-11-24 | 2003-05-01 | 2004-04-01 | 252800 | 70% | 176960 |  | 44 |  |  |  | 0 | 0 | 0 |  | 9.1 | 11.6 | 4.4 | 183.7 | 252.8 | Total | -95170.9
Task 9a | PVVS Special Tooling Design(60%) | 1 to 4 | 2003-06-16 | 2003-09-08 | 2003-05-01 | 2004-02-01 | 93900 | 95% | 89205 |  | 6.8 | 2.2 | 5.5 | 13.1 | 13.8 |  | 11.2 | 36.2 | 2.5 | 2.6 |  |  | 93.9 | Rounded | -100000
Task 9b | PVVS Special Tooling Fabrication(100%) | 1 to 4, 7, 9a | 2003-07-21 | 2003-10-13 | 2003-05-01 | 2004-02-01 | 5300 | 45% | 2385 | Monthly Cost Baseline Plan (loaded $k) May: 2.3; Monthly Cost Baseline Plan (loaded $k) Jul: 0; Monthly Cost Baseline Plan (loaded $k) Aug: 0; Monthly Cost Baseline Plan (loaded $k) Sep: 0; Monthly Cost Baseline Plan (loaded $k) Oct: 0; Monthly Cost Baseline Plan (loaded $k) Jan: 1.5; Monthly Cost Baseline Plan (loaded $k) Feb: 1.5 | 5.3
Task 10 | 5.4.2 Process History (60%) |  | 2003-11-25 | 2003-12-10 | 2003-07-01 | 2004-04-01 | 3900 | 10.26% | 400 | Monthly Cost Baseline Plan (loaded $k) Jul: 0.4; Monthly Cost Baseline Plan (loaded $k) Nov: 0; Monthly Cost Baseline Plan (loaded $k) Mar: 1.8; Monthly Cost Baseline Plan (loaded $k) Apr: 1.7 | 3.9
Task 11 | 5.1 Weekly Reports |  |  |  | 2003-06-01 | 2004-04-01 | 2700 |  | 300 | Monthly Cost Baseline Plan (loaded $k) Jun: 0.2; Monthly Cost Baseline Plan (loaded $k) Aug: 0.1; Monthly Cost Baseline Plan (loaded $k) Jan: 0.6; Monthly Cost Baseline Plan (loaded $k) Feb: 0.6; Monthly Cost Baseline Plan (loaded $k) Mar: 0.6; Monthly Cost Baseline Plan (loaded $k) Apr: 0.6 | 2.7
Task 12 | 5.2 Monthly Earned Value Reports |  |  |  | 2003-07-01 | 2004-04-01 | 2900 |  | 1300 | Monthly Cost Baseline Plan (loaded $k) Jul: 0.7; Monthly Cost Baseline Plan (loaded $k) Aug: 0.6; Monthly Cost Baseline Plan (loaded $k) Jan: 0.4; Monthly Cost Baseline Plan (loaded $k) Feb: 0.4; Monthly Cost Baseline Plan (loaded $k) Mar: 0.4; Monthly Cost Baseline Plan (loaded $k) Apr: 0.4 | 2.9
Task 13 | [8 empty] | 0 | [13 empty] | 0
Task 14 | [8 empty] | 0 | [13 empty] | 0
0
| Total | [5 empty] | 468700 |  | 349225 | 0 | 70.4 | 31.6 | 22.8 | 14.8 | 13.8 | 0 | 11.2 | 46.1 | 20.5 | 21.6 | 22 | 193.9 | 468.7
| Actual Cost Incurred ($k) | [9 empty] | 70.4 | 31.6 | 22.8 | 14.8 | 13.8 | 0 | 11.2 | 46.1 | 35 | 21 | 41.9
| Accumulated Actual Cost Incurred ($k) | [9 empty] | 70.4 | 102 | 124.8 | 139.6 | 153.4 | 153.4 | 164.6 | 210.7 | 245.7 | 267 | 308
Note: | We have an increased cost of $100,000 in Task 8 for cost overrun by our vendor (Precision) and additional support from Rohwedder. We have received the details in hours and material but still waiting for the line item justification.
The additional $100,000 is included in April 2004 (column w) and Estimate at completion (column x). It is anticipated that some cost might occur in May 2004.
Instructions:
1) INITIAL PLAN - Identify all contract task deliverables and provide ;
a) List all contract deliverables and intermediate tasks. Break long duration task into smaller duration (1-2 months) tasks. [column B]
b) Start and finish schedule dates [column D & E]
c) estimated cost values (along with appropriate burdens, G&A and fees) [column H]
d) provide cost profile for each task by distributing cost by month. This represents your anticipated costing profile. [columns K - V]
e) identify significant prerequisites to tasks [column C]
f) transmit via e-mail attachment by MARCH 27th to Ron Strykowsky at rstrykow@pppl.gov phone 609-243-2674
g) provide any supplemental information, clarifications, assumptions, or basis as necessary.
2) MONTHLY PROGRESS ASSESSMENT - Each month by the 4th working day before the end of each month transmit progress status for the contract by;
a) indicating actual start and actual finish dates for each task [column F & G]
b) indicating forecast starts and finish dates (if planned dates will not be met) column [F & G]
c) providing percent complete for each task [column I]
d) Note; the BCWP (budgeted cost of work performed i.e. earned value) will be calculated by multiplying
the percent complete by the budget for each task unless you provide an alternate methodology that PPPL accepts. [column J]
e) providing an updated estimate at completion for each task. This will provide a "heads-up" to PPPL of potential cost increases) [column W]
f) providing ESTIMATED accrued cost for the entire contract by the 4th working day before the end of each month . It is not necessary to provide accruals at the detailed task level, however,
this cost should be reasonably consistent with the cost to be invoiced to PPPL on a monthly basis. [columns K - V}
g) transmit via e-mail attachment by the 4th working day before month end to Ron Strykowsky at rstrykow@pppl.gov phone 609-243-2674
h) provide any supplemental information, clarifications, assumptions, or basis as necessary.
3) MONTHLY INVOICING -
a) Provide a cost invoice to PPPL that specifies all work and tasks performed. Please identify your expected transmittal date to PPPL.