## Sheet1
NCSX Contract Plan and Reporting
Contract: S-
Date: | December 2003
Schedule
A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X
|  |  | Baseline |  | Forecast or Actual |  | Total | % | BCWP | Monthly Cost Baseline Plan (loaded $k) | [12 empty] | Estimate at
Task Num. | Task Name w/ SOW Reference Number | Prerequisites (list task numbers) | Start | Finish | Start | Finish | Budget | Complete | (budget x %) | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | Completion
Task 1 | 3.1.1 Mfg Methods for Fab VVSA (100%) |  | 2003-05-01 | 2003-05-30 | 2003-05-01 | 2003-05-30 | 12500 | 100% | 12500 | Monthly Cost Baseline Plan (loaded $k) May: 11.1; Monthly Cost Baseline Plan (loaded $k) Jun: 1.4 | 12.5
Task 2 | 3.1.3 Prelim MIT & QA Plans VVSA (100%) |  | 2003-05-01 | 2003-05-30 | 2003-05-01 | 2003-05-30 | 6900 | 100% | 6900 | Monthly Cost Baseline Plan (loaded $k) May: 2.8; Monthly Cost Baseline Plan (loaded $k) Jun: 4.1 | 6.9
Task 3 | 3.1.2 Sub Recommendations (50%) |  | 2003-05-01 | 2003-05-30 | 2003-05-01 | 2003-05-30 | 7100 | 100% | 7100 | Monthly Cost Baseline Plan (loaded $k) May: 1.9; Monthly Cost Baseline Plan (loaded $k) Jun: 4.9; Monthly Cost Baseline Plan (loaded $k) Jul: 0.3 | 7.1
Task 4 | 3.1.4 Budgetary Cost & Schedule Est VVSA-3 units (50%) |  | 2003-05-14 | 2003-06-06 | 2003-05-01 | 2003-06-06 | 11900 | 100% | 11900 | Monthly Cost Baseline Plan (loaded $k) May: 1.5; Monthly Cost Baseline Plan (loaded $k) Jun: 10.4 | 11.9
Task 5 | 3.3.1 Final MIT & QA Plans VVSA-3 units (30%) | 1 to 4, 7 to 9 | 2003-11-24 | 2003-02-16 | 2003-07-03 | 2004-03-01 | 14100 | 12.06% | 1700 | Monthly Cost Baseline Plan (loaded $k) Jul: 1.7; Monthly Cost Baseline Plan (loaded $k) Nov: 0; Monthly Cost Baseline Plan (loaded $k) Dec: 0; Monthly Cost Baseline Plan (loaded $k) Jan: 0; Monthly Cost Baseline Plan (loaded $k) Feb: 0; Monthly Cost Baseline Plan (loaded $k) Mar: 12.4; Monthly Cost Baseline Plan (loaded $k) Apr: 0 | 14.1
Task 6 | 3.3.2 Firm Fix Cost & Schedule Proposal (100%) | 1 to 4, 7 to 9 | 2003-02-23 | 2003-03-24 | 2004-02-01 | 2004-04-01 | 12300 | 0% | 0 | Monthly Cost Baseline Plan (loaded $k) Feb: 2.4; Monthly Cost Baseline Plan (loaded $k) Mar: 2.4; Monthly Cost Baseline Plan (loaded $k) Apr: 7.5 | 12.3
Task 7 | 3.2.1 MIT & QA Plans for PVVS (100%) | 1 to 4 | 2003-06-16 | 2003-08-25 | 2003-06-09 | 2004-02-01 | 42400 | 79.01% | 33500 | Monthly Cost Baseline Plan (loaded $k) Jun: 8.4; Monthly Cost Baseline Plan (loaded $k) Jul: 14.2; Monthly Cost Baseline Plan (loaded $k) Aug: 1; Monthly Cost Baseline Plan (loaded $k) Dec: 9.9; Monthly Cost Baseline Plan (loaded $k) Jan: 6.4; Monthly Cost Baseline Plan (loaded $k) Feb: 2.5 | 42.4
Task 8 | 3.2.2 PVVS Manufacturing (100%) | 1 to4, 7, 9 | 2003-09-15 | 2003-11-24 | 2003-05-01 | 2004-04-01 | 152800 | 28.8% | 44000 |  | 44 |  |  |  | 0 | 0 | 0 |  | 9.1 | 11.6 | 4.4 | 83.7 | 152.8
Task 9a | PVVS Special Tooling Design(60%) | 1 to 4 | 2003-06-16 | 2003-09-08 | 2003-05-01 | 2004-02-01 | 57700 | 91.16% | 52600 |  | 6.8 | 2.2 | 5.5 | 13.1 | 13.8 |  | 11.2 |  | 2.5 | 2.6 |  |  | 57.7
Task 9b | PVVS Special Tooling Fabrication(100%) | 1 to 4, 7, 9a | 2003-07-21 | 2003-10-13 | 2003-05-01 | 2004-02-01 | 5300 | 43.4% | 2300 | Monthly Cost Baseline Plan (loaded $k) May: 2.3; Monthly Cost Baseline Plan (loaded $k) Jul: 0; Monthly Cost Baseline Plan (loaded $k) Aug: 0; Monthly Cost Baseline Plan (loaded $k) Sep: 0; Monthly Cost Baseline Plan (loaded $k) Oct: 0; Monthly Cost Baseline Plan (loaded $k) Jan: 1.5; Monthly Cost Baseline Plan (loaded $k) Feb: 1.5 | 5.3
Task 10 | 5.4.2 Process History (60%) |  | 2003-11-25 | 2003-12-10 | 2003-07-01 | 2004-04-01 | 40100 | 91.27% | 36600 | Monthly Cost Baseline Plan (loaded $k) Jul: 0.4; Monthly Cost Baseline Plan (loaded $k) Nov: 0; Monthly Cost Baseline Plan (loaded $k) Dec: 36.2; Monthly Cost Baseline Plan (loaded $k) Mar: 1.8; Monthly Cost Baseline Plan (loaded $k) Apr: 1.7 | 40.1
Task 11 | 5.1 Weekly Reports |  |  |  | 2003-06-01 | 2004-04-01 | 2700 | 11.11% | 300 | Monthly Cost Baseline Plan (loaded $k) Jun: 0.2; Monthly Cost Baseline Plan (loaded $k) Aug: 0.1; Monthly Cost Baseline Plan (loaded $k) Jan: 0.6; Monthly Cost Baseline Plan (loaded $k) Feb: 0.6; Monthly Cost Baseline Plan (loaded $k) Mar: 0.6; Monthly Cost Baseline Plan (loaded $k) Apr: 0.6 | 2.7
Task 12 | 5.2 Monthly Earned Value Reports |  |  |  | 2003-07-01 | 2004-04-01 | 2900 | 44.83% | 1300 | Monthly Cost Baseline Plan (loaded $k) Jul: 0.7; Monthly Cost Baseline Plan (loaded $k) Aug: 0.6; Monthly Cost Baseline Plan (loaded $k) Jan: 0.4; Monthly Cost Baseline Plan (loaded $k) Feb: 0.4; Monthly Cost Baseline Plan (loaded $k) Mar: 0.4; Monthly Cost Baseline Plan (loaded $k) Apr: 0.4 | 2.9
Task 13 | [8 empty] | 0 | [13 empty] | 0
Task 14 | [8 empty] | 0 | [13 empty] | 0
0
| Total | [5 empty] | 368700 |  | 210700 | 0 | 70.4 | 31.6 | 22.8 | 14.8 | 13.8 | 0 | 11.2 | 46.1 | 20.5 | 21.6 | 22 | 93.9 | 368.7
| Actual Cost Incurred ($k) | [9 empty] | 70.4 | 31.6 | 22.8 | 14.8 | 13.8 | 0 | 11.2 | 46.1
Instructions:
1) INITIAL PLAN - Identify all contract task deliverables and provide ;
a) List all contract deliverables and intermediate tasks. Break long duration task into smaller duration (1-2 months) tasks. [column B]
b) Start and finish schedule dates [column D & E]
c) estimated cost values (along with appropriate burdens, G&A and fees) [column H]
d) provide cost profile for each task by distributing cost by month. This represents your anticipated costing profile. [columns K - V]
e) identify significant prerequisites to tasks [column C]
f) transmit via e-mail attachment by MARCH 27th to Ron Strykowsky at rstrykow@pppl.gov phone 609-243-2674
g) provide any supplemental information, clarifications, assumptions, or basis as necessary.
2) MONTHLY PROGRESS ASSESSMENT - Each month by the 4th working day before the end of each month transmit progress status for the contract by;
a) indicating actual start and actual finish dates for each task [column F & G]
b) indicating forecast starts and finish dates (if planned dates will not be met) column [F & G]
c) providing percent complete for each task [column I]
d) Note; the BCWP (budgeted cost of work performed i.e. earned value) will be calculated by multiplying
the percent complete by the budget for each task unless you provide an alternate methodology that PPPL accepts. [column J]
e) providing an updated estimate at completion for each task. This will provide a "heads-up" to PPPL of potential cost increases) [column W]
f) providing ESTIMATED accrued cost for the entire contract by the 4th working day before the end of each month . It is not necessary to provide accruals at the detailed task level, however,
this cost should be reasonably consistent with the cost to be invoiced to PPPL on a monthly basis. [columns K - V}
g) transmit via e-mail attachment by the 4th working day before month end to Ron Strykowsky at rstrykow@pppl.gov phone 609-243-2674
h) provide any supplemental information, clarifications, assumptions, or basis as necessary.
3) MONTHLY INVOICING -
a) Provide a cost invoice to PPPL that specifies all work and tasks performed. Please identify your expected transmittal date to PPPL.