Originators:	B. Williams PM

J. Gass ME

# Accomplishments for Last Week

- Continued to develop details and procedural order of MIT and QA steps for reports (deliverables 3.1.1, 3.1.2 and 3.1.3).

- Coordinated with sub-contractor Nu Vacuum on respective tasks for preparation of deliverables 3.1.1, 3.1.2 and 3.1.3.

- Researched measurement and verification systems and techniques.

- Continued to develop structure for report format.

Plan for Next Week

- Continue research of measurement and verification systems and techniques.

- Continue coordinating with sub-contractor Nu Vacuum for completion of deliverables 3.1.1, 3.1.2 and 3.1.3.

- Continue assessing and compiling expected costs determined through action items above in order to develop deliverable 3.1.4.

Issues and Concerns

- Rohwedder would like to confirm the due date of 5/30/03 for deliverables 3.1.1, 3.1.2, and 3.1.3 of NCSX-SOX-121-01-01 and a due date of 6/6/03 for 3.1.4.