Originators:	D. Thompson RI PM

J. Budd ME

D. Rioux PMW PM

T. Gilmore PMW ME

# Accomplishments for Last Week

- Completion of MITP, Magnetic Permeability Inspection Procedure, US thickness inspection procedure, and comments to first round of procedures. RI organized and completed travel.

- Received inconel scab plate material

- Received first shipment of die ribs

- Began machining of die A enclosure

Plan for Next Week

- Machining of Die A enclosure.

- Receipt of Faro Arm

- Completion of development of CMM Measurement procedures.

- Inspection of Die Ribs.

- Submit welding and weld related inspection procedures to Rohwedder.

Issues and Concerns

- Forming operation capacity requirement uncertain.