Originators:	D. Thompson RI PM

J. Budd ME

D. Rioux PMW PM

T. Gilmore PMW ME

# Accomplishments for Last Week

- Received Faro Arm

- Selected Forming Vendor.

- Received all of Die A ribs.

- Began machining of die A enclosure – 75% complete.

- Submitted welding and weld related inspection procedures to Rohwedder/PPPL.

- Submitted final approved copies of procedures P01, P02, P03, P05, P06, P07, P08, P09, P11, P12 and MITP01.

- Finalized die reinforcement concept.

Plan for Next Week

- Complete Machining of Die A enclosure.

- Complete drilling/tapping of Die A.

- Assemble and Inspect Die A

- Complete of development of CMM Measurement procedures.

- Inspect of Die A.

- Submit weld inspection procedures.

- Design and Fabricate Die / Press connection and screw press mounts.

- Conduct welding of weld coupons for PQR

Issues and Concerns

- Forming operation capacity requirement uncertain.