Originators:	D. Thompson RI PM

J. Budd ME

D. Rioux PMW PM

T. Gilmore PMW ME

# Accomplishments for Week of 2/16/04

- Completed initial integration of Die A assemblies.

- Completed initial measurements on Die A assemblies.

- Performed modifications to the Die A assemblies necessary to bring critical surface into tolerance (+/- .050 each die).

- Refined scab plate procedure.

- Installed scab plates on Die A assemblies.

- Performed final measurements on Die A full assemblies (with scab plate).

- Prepped material for Segment forming operation (timesaver operation).

- Prepped material for parallel project forming operation.

- Completed press locking and alignment devices.

- Die B enclosure machining progress.

- Inconel .120 8” tube was rolled – for PVVS and parallel project.

Plan for Week of 2/23/04

- Complete Machining of Die B enclosure.

- Complete drilling/tapping of Die B ribs.

- Assemble and Inspect Die B assemblies including scab plates.

- Form and inspect Segment A.

- Conduct welding of weld coupons for PQR

Issues and Concerns

- Proficiency on FARO arm impacting schedule.

- Rib water jet supplier delivery dates impacting schedule.

- Still have technical risks associated with forming operation.