Originators:	D. Thompson RI PM

J. Budd ME

P. Allen-LeBlanc PMW PM

T. Gilmore PMW ME

# Accomplishments for Week of 2/27/04

- Completed heat treating segment A.

- Completed initial measurements on Die B ribs.

- Completed machining all die B ribs and die B enclosures.

- Generated welding coupons, forwarded to RPC for testing.

- Water jet cut the majority of Die C ribs.

- Measuring die A for re-work prior to second press attempt.

- Began assembling die B and assembly inspections.

- Began machining Die C enclosure & ribs.

- Procedures complete and soon to be released:  03-8083-P04, 03-8083-P05, 03-8083, 03-8083-P07, 03-8083-P12.

- Parallel project.  Working with FARO on reverse engineering on full surface.

Plan for Week of 3/05/04

- Complete assembly of Die B.

- Attach scab plate on Die B.

- Inspect Die B.

- Rework Die A.

- Fabricate and integrate Die B Alignment guides

- Evaluate segment A-1.

- Complete water jet of Die C ribs.

- Measure Die C ribs.

- Begin Machining of Die C ribs.

- Complete machining of Die C enclosure.

- Receive test results from weld tests.

- Submit completed procedures and finalize outstanding procedures.

- Form segment B and A-2.

- Cut parallel project segment, weld assy, and port per model.

Issues and Concerns

- FARO software not as easy to work with as “demonstrated”

- Still have technical risks associated with forming and welding operations.