Originators:	D. Thompson RI PM

J. Budd ME

D. Rioux PMW PM

T. Gilmore PMW ME

# Accomplishments for Week of 3/05/04

- Completed water jet of Die C ribs.

- Received and began machining of 22 of 44 die C ribs.

- Completed machining of Die C enclosure.

- Completed reverse engineering on parallel project.

- Ordered new welding equipment.

- Completed and distributed procedures 03-8083-P04, 03-8083-P05, 03-8083-P07, 03-8083-P12

- Measured and modified upgraded Die A for A-2 press operation (replaced guide rails cut during disassembly).

- Completed Die B assemblies - scab plate on one half..

- Completed fabrication of Die B alignment guides.

- Measured Segment A-1 and verified part in tolerance.

Plan for Week of 3/12/04

- Complete Die B scab plate installation.

- Form and heat treat segment B and second half of segment A (A-2).

- Perform weld tests with new equipment.

- Complete assembly of Die C and prep for forming.

- Measure/evaluate segment A-2 and B after heat treat.

- Complete following work on parallel project.

  - Cut surface.

  - Weld tube

  - Measure 2 surface halves with FARO

  - Design assy.

  - Weld two surface halves.

  - Install port.

Issues and Concerns

- Still have technical risks associated with welding operations.