Originators:	D. Thompson RI PM

J. Budd ME

D. Rioux PMW PM

T. Gilmore PMW ME

# Accomplishments for Week of 3/26/04

- Die C top and bottom ribs assembled.

- Die C top and bottom assemblies measured.

- Die C top assembly scab plate installed.

- Segments A2 and B brought back to PMW from heat treatment.

- New weld head ordered and received - to replace the one that failed.

Plan for Week of 3/26/04

- Measure Segments A2 and B with CMM (post forming and heat treating).

- Make decision on the sending of a Faro Applications Engineer to PMW (Apps Eng available Wed. and Thurs., 4/1 & 4/2)

- Finish install of scab plate on Die C bottom assembly.

- Measure Die C top and bottom assemblies with scab plates with CMM.

- Prep Die C assemblies for forming and heat treatment (reinforcements, guides, etc.).

- Machine some of the excess material off of segments A1, A2, and B.

- Perform weld experiments and tests with new equipment.

- Weld new coupons and send out for destructive testing.

- Design fixture for holding segments together.

- Address comments to procedures 10 and MITP4.

- Develop additional stress relief procedure for PVVS minus inert gas use.

- Complete following work on parallel project.

  - Cut surface and weld back together

  - Reverse engineer new part and position port tube with Pro-E

  - Place and weld port tube on new surface

  - Cut port tube to length

  - Weld port flange to port tube end

  - Cut port assembly away from surface and perform reintegration

Issues and Concerns

- Still have technical risks associated with welding operations.

- Proper alignment of segments still a risk.