Originators:	D. Thompson RI PM

J. Budd ME

D. Rioux PMW PM

T. Gilmore PMW ME

# Accomplishments for Week of 4/02/04

- Completed Die C installation of scab plates.

- Completed Die C scab plate inspections and recorded reference points.

- Completed reinforcing of Die C ribs

- Completed installation of Die C alignment tubes

- Completed inspection of segment A2

- Collected inspection data on Die B

- Submitted revised procedure 03-8083-P10 for visual weld inspection as well as new procedure 03-8083-P15 for Non-Inert Stress relief

- Performed welding experiments using new equipment

- Designed fixture for holding segments for assembly

- Pressing of Segment C

Plan for Week of 4/09/04

- Heat treatment of segment C

- Submit MITP for PVVS assembly

- Complete Welding PQR testing

- Begin Fabrication of components for assembly fixture

- Complete inspections of Segment B

- Trim excess material from Segments A1, A2, and B

- Inspect Segment C

Issues and Concerns

- Still have technical risks associated with welding operations.

- Proper alignment of segments still a risk.

Lessons Learned

Start next week