Originators:	D. Thompson RI PM

J. Budd ME

P. Allen-LeBlanc PMW PM

T. Gilmore PMW ME

# Accomplishments for Week of 4/12/04

- Marked reference points on segment C and removed from die.

- Reshaped segment B to bring into tolerance.

- Began manufacture of port and port tube for PVVS.

- Submitted draft MITP for PVVS manufacture and assembly to RI.

- Continued inspections of trimmed segments A1 and A2, however was unable to make much progress due to lack of repeatability of "best fit" inspection process.

HIGHLIGHTS for week of 4/12/04

Following 3 items were key to reduction of welding risks:

- Cut Parallel project surface and welded curved section with negligible distortion.

- Performed further testing on welding curved joints resulting in negligible distortion.

- Weld coupons passed testing.

Plan for Week of 4/19/04

- Progress on second round of inspections of segments A1, A2, and B and identify concrete reference point to ensure positive realignment in the future

- Plans for Faro to be onsite this week to aid with inspections.

- Inspect segment C and trim

- Complete fabrication of PVVS port and tube

- Finalize MITP05 and all outstanding procedures.

- Once inspected, begin tacking segments together

Issues and Concerns

- FARO Support is limited and the application is pushing the limits of the tool.

- Alignment and welding is still a risk.

Lessons Learned

- Stable repeatable reference forms are required on the segments to provide repeatable relocation of the parts.  The parts include a lot of 3-D information, but the convergence on solutions has too great of a variance to be reliable from operation to operation.  The added time of including the reference shapes is easily offset by the measurement activity required if shapes not included.