Originators:	D. Thompson RI PM

J. Budd ME

P. Allen-LeBlanc PMW PM

T. Gilmore PMW ME

# Accomplishments for Week of 4/19/04

- Faro applications engineer on site is expediting the inspection process and helping us nail down alignment issues and progress with future requirements of inspecting PVVS.

- Manufactured “permanent” reference points to be attached to exterior of PVVS.  Permanent reference points are for PVVS only.

- Completed multiple iterations of inspections and rework bringing slightly out of tolerance areas of segments into tolerance after adding concrete reference geometry to aid in expediting inspections.

- Built custom dies for reworking out of tolerance areas of segments. Segments progressing into tolerance.

- Completed final MITP and stress relieve procedure.

- Successful weld coupons, awaiting final WPS's and weld repair procedure from weld engineer.

- Submitted updated schedule and costs to reflect delay caused by lack of repeatability in previous faro setup.

- Manufactured new fixture plate to allow fitting of segments.

HIGHLIGHTS for week of 4/19/04

No major highlights.

Plan for Week of 4/19/04

- Make final trims to segments and begin fitting and tacking together.

- Inspect fitted and tacked segments.

- Complete manufacture of port.

- Submit finalized weld procedures.

- Work towards completion of remaining procedures

Issues and Concerns

- FARO Support is limited and the application is pushing the limits of the tool.

- Alignment is still a risk