## PMW Costs incurred to date:  March 31/04 Rohwedder/Princeton PVVS project

|  | Original quote | Actual costs |
| --- | --- | --- |
| 1. Non-recurring Expenses | 320 @ $42 13,440.00 | 1,116 @ $42 46,872.00 |
| 2. Direct Labour | 560 @ $42 23,520.00 | 850 @ $42 35,700.00 sub contract mach. 5,000.00 40,700.00 |
| 3. Indirect Labour | 120 @ $42 5,040.00 | 490 @ $42 20,580.00 |
| 4. Direct Material | 31,500.00 + Pro E 14,000.00 45,500.00 | 74,585.00 |
| 5. Indirect Material | 2,500.00 | 4,200.00 |
| 6. - Sub-contractor - Dies & pressing - Stress relief - Rolling - Welding | 65,200.00 | 8,250.00 135.00 1,200.00 2,900.00 700.00 13,185.00 |
| 7. Shipping | 1,800.00 | 900 |
| Sub-total | $157,000.00 | 201.022 Pro-E 11,809 Faro ($3000 US/mo @ 4mo. X 1.32 Cdn.) 15,840.00 Weld equipment ($600/mo @ 2mo.) 1,200.00 $229,871.00 |
| Markup | (2%) 3,140.00 | (0%) |
| Total | Cdn. $160,140.00 | Cdn. $229,871.00 |
| Exchange | 0.78 | 0.78 |
|  | US $124,909.00 | $179,299.00 |

Please note, on the Costing breakdown tables, all sections are marked with their corresponding number for this table.

## Projection Estimate of remaining costs:

Engineering		260 @ 42		10,920.00

Quality Assurance	240 @ 42		10,080.00

Direct Labour		400 @	42		16,800.00

Machining		168 @ 42		  7,056.00

Direct Material				  2,000.00

Sub-contractors:

- RPC				     300.00

- Trenton Works			  1,500.00

- Thechnico				  1,500.00

Shipping

- Trenton Works			     600.00

- To Customer			  1,500.00

Equipment						  0

Consumables					  2,000.00

Sub-total					54,256.00

Exchange					         0.78

# TOTAL					$42,320.00