## Tracking
Item # | Document # | Description | Need Date | Req Approval Date (2 wks prior to need date) | Action/Status | Actionee
Procedures
1 | 03-8083-P01 | Inspection & Test | 2004-01-01 | Past Due | Done. Signed off version dist 1/28/04 | DONE
2 | 03-8083-P02 | Control of Inspection, Measuring, and Test | 2004-01-01 | Past Due | Done. Signed off version dist 1/28/04 | DONE
3 | 03-8083-P03 | Nonconformance & Corrective Action Procedure | 2004-01-01 | Past Due | Done. Signed off version dist 1/28/04 | DONE
4 | 03-8083-P04 | Radiographic Examination | 2004-03-11 | 2004-02-26 | Est sign off and final dist 1/27/04 | PMW
5 | 03-8083-P05 | Helium Leak Detection | 2004-03-01 | 2004-02-16 | Done. Signed off version dist 1/28/04 | DONE
6 | 03-8083-P06 | Cleaning | 2004-01-23 | Past Due | Done. Signed off version dist 1/28/04 | DONE
7 | 03-8083-P07 | Interior Surface Finish | 2004-03-01 | 2004-02-16 | Done. Signed off version dist 1/28/04 | DONE
8 | 03-8083-P08 | Exterior Surface Finish | 2004-03-01 | 2004-02-16 | Done. Signed off version dist 1/28/04 | DONE
9 | 03-8083-P09 | Magnetic Permeability | 2004-02-17 | 2004-02-03 | Done. Signed off version dist 1/28/04 | DONE
10 | 03-8083-P010 | Weld Inspection | 2004-03-11 | 2004-02-26 | Est date of dist for review 1/28/04 | PMW
11 | 03-8083-P011 | CMM Dimensions & Tolerance Verification | 2004-01-27 | Past Due | Done. Signed off version dist 1/28/04 | DONE
12 | 03-8083-P012 | Thickness Inspection | 2004-02-17 | 2004-02-03 | Done. Signed off version dist 1/28/04 | DONE
13 | 03-8083-P013 | Weld Repair | 2004-03-11 | 2004-02-26 | Need update from PMW | PMW
14 | 03-8083-P014 | Stress Relief | 2004-02-20 | 2004-02-06 | Est date of dist for review 2/04/04 | PMW
15 | MITP01 | Die A manufacture | 2004-01-22 | Past Due | Est sign off and final dist 1/27/04 | PMW
16 | MITP02 | Die B manufacture | 2004-02-02 | Past Due | In development | PMW
17 | MITP03 | Die C manufacture | 2004-02-10 | 2004-01-27 | In development | PMW
18 | MITP04 | PVVS Forming | 2004-02-13 | 2004-01-30 | Est date of dist for review 1/30/04 | PMW
19 | MITP05 | PVVS assembly | 2004-03-11 | 2004-02-26 | In development | PMW
Forms
1 | F006 | Material Control Sheet | NA | NA | No activity required. RI/PMW use approved until further notice from PPPL | NA
2 | F025 | Document Control Log | NA | NA |  | NA
3 | F026 | Change Notice | NA | NA |  | NA
4 | F027 | Change Notice Record | NA | NA |  | NA
5 | F029 | Incoming Inspection Report | NA | NA |  | NA
6 | F030 | Identification Tags | NA | NA |  | NA
7 | F031 | Route Cards | NA | NA |  | NA
8 | F034 | Dimensional Inspection Report | NA | NA |  | NA
9 | F039 | Calibration Record | NA | NA |  | NA
10 | F040 | Calibration Identifier | NA | NA |  | NA
11 | F042 | Signature Record | NA | NA |  | NA
12 | F043 | Nonconformance Report | NA | NA |  | NA
13 | F044 | Nonconformance Record | NA | NA |  | NA
14 | F045 | Corrective and Preventive Action Request | NA | NA |  | NA
15 | F046 | Corrective and Preventive Action Record | NA | NA |  | NA
16 | F047 | Return Material Authorization | NA | NA |  | NA
17 | F048 | Return Material Authorization Record | NA | NA |  | NA
18 | F055 | Summary of Final Inspection - Vacuum Chamber | NA | NA |  | NA
19 | F056 | Helium Leak Test Report | NA | NA |  | NA
20 | F057 | Preventive Maintenance Record | NA | NA |  | NA
21 | F058 | Maintenance Check List | NA | NA |  | NA
22 | F061 | Customer Complaint | NA | NA |  | NA
23 | F099 | General Test Report | NA | NA |  | NA
Welding Procedures
1 | 03-8083-WPS01 | PVVS Segment Tack & Final Weld | 2004-03-11 | 2004-02-26 | Est dist date 01/27/2004 | PMW
2 | 03-8083-WPS02 | Port Extens Tube to Segment Tack & Final Weld | 2004-03-11 | 2004-02-26 | Est dist date 01/27/2004 | PMW
3 | 03-8083-WPS03 | Flange to Tube Tack & Final Weld | 2004-03-11 | 2004-02-26 | Est dist date 01/27/2004 | PMW