## Sheet1
Procedures and Forms Development and Tracking
| Document # | Description | Time of Implementation | Date to be Approved | Tracking
Procedures
| 03-8083-P01 | Inspection & Test | 2004-01-01 | Past Due | In Final PPPL Review
| 03-8083-P02 | Control of Inspection, Measuring, and Test | 2004-01-01 | Past Due | In Final PPPL Review
| 03-8083-P03 | Nonconformance & Corrective Action Procedure | 2004-01-01 | Past Due | In Final PPPL Review
| 03-8083-P04 | Radiographic Examination | 2004-03-01 | 2004-02-16 | In Development
| 03-8083-P05 | Helium Leak Detection | 2004-03-01 | 2004-02-16 | In Final PPPL Review
| 03-8083-P06 | Cleaning | 2004-01-23 | Past Due | In Final PPPL Review
| 03-8083-P07 | Interior Surface Finish | 2004-03-01 | 2004-02-16 | In Final PPPL Review
| 03-8083-P08 | Exterior Surface Finish | 2004-03-01 | 2004-02-16 | In Final PPPL Review
| 03-8083-P09 | Magnetic Permeability | 2004-01-26 | Past Due | In Development
| 03-8083-P010 | Weld Inspection | 2004-01-23 | Past Due | In Development
| 03-8083-P011 | CMM Dimensions & Tolerance Verification | 2004-01-19 | Past Due | In Development
| 03-8083-P012 | Thickness Inspection | 2004-01-26 | Past Due | In Development
| 03-8083-P013 | Weld Repair | 2004-01-23 | Past Due | In Development
| 03-8083-P014 | Stress Relief | 2004-01-26 | Past Due | In Development
| MITP | MITP | 2004-01-16 | Past Due | In Development
Forms
| F006 | Material Control Sheet | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F025 | Document Control Log | 2004-01-01 | Past Due | In Final PPPL Review
| F026 | Change Notice | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F027 | Change Notice Record | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F029 | Incoming Inspection Report | 2004-01-16 | Past Due | In Final PPPL Review
| F030 | Identification Tags | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F031 | Route Cards | 2004-01-16 | Past Due | In Final PPPL Review
| F034 | Dimensional Inspection Report | 2004-01-01 | Past Due | In Final PPPL Review
| F039 | Calibration Record | 2004-01-01 | Past Due | In Final PPPL Review
| F040 | Calibration Identifier | 2004-01-01 | Past Due | In Final PPPL Review
| F042 | Signature Record | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F043 | Nonconformance Report | 2004-01-01 | Past Due | In Final PPPL Review
| F044 | Nonconformance Record | 2004-01-01 | Past Due | In Final PPPL Review
| F045 | Corrective and Preventive Action Request | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F046 | Corrective and Preventive Action Record | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F047 | Return Material Authorization | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F048 | Return Material Authorization Record | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F055 | Summary of Final Inspection - Vacuum Chamber | 2004-03-10 | 2004-02-23 | First Iteration of PPPL Approval
| F056 | Helium Leak Test Report | 2004-03-01 | 2004-02-16 | In Final PPPL Review
| F057 | Preventive Maintenance Record | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F058 | Maintenance Check List | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F061 | Customer Complaint | 2004-01-01 | Past Due | First Iteration of PPPL Approval
| F099 | General Test Report | 2004-01-01 | Past Due | In Final PPPL Review
Welding Procedures
| 03-8083-WPS01 | PVVS Segment Tack & Final Weld | 2004-03-01 | 2004-02-16 | In Development
| 03-8083-WPS02 | Port Extension Tube to Segment Tack & Final Weld | 2004-03-01 | 2004-02-16 | In Development
| 03-8083-WPS03 | Flange to Tube Tack & Final Weld | 2004-03-01 | 2004-02-16 | In Development
| 03-8083-WPS04 | Reinforcement Sleeve Stitch Weld | 2004-03-01 | 2004-02-16 | In Development
| 03-8083-WPS05 | Port Tube to PVVS Stub Tack & Final Weld | 2004-03-01 | 2004-02-16 | In Development
| 03-8083-WPS06 | Scab Plate Tack & Final Weld | 2004-01-23 | Past Due | In Development