## Cover Sheet
PPPL PVVS
Lessons Learned
Rev: 2004-04-28

## Lessons Learned
Item | Name | Challenge Description | Resolution
1 | CMM Training and support | The FARO measurement tool was utilized for part/assy measurements throughout the processes. During the measurement of the ribs, die assemblies, and segments, it became very clear that the tool was not something that can be quickly integrated into the team and used on parts of this complexity. | One of the more experienced talented FARO technical support engineers was brought into the operation at key times (die assembly and segment measurement), but the QA team had lost many days working independently and with phone support from RI and FARO to try to become proficient with the tool. During the second iteration of segment operations in which FARO on-site was utilized, the QA team became very quick on the tool. There were two major contributing factors - experience on the tool and more importantly the addition of the reference geometries.
2 | Reference geometry (location features) approach | RI worked with several CMM vendors and selected the FARO arm for the measurement support. In working with the FARO technical specialists , the team was convinced that the segments would not require any additional geometrical features be added to register the part throughout fab/integration processes. During the forming and rough cutting of the segments, the team learned that the re-registering of the parts was very sensitive to the technique employed. | Key FARO technical personnel were brought onto the team to support the operation. During these supported operations, it became very clear that the registration geometries (simple cylinders or cones) need to be included on the parts (including the dies) from the beginning.
3 | Oversized dies (overlapping material) | There seemed to be a trend of the segments having errors at the edges while being in tolerance everywhere else. It is suspected that this is due to the edge effects during heating. | The situation was resolved in the PVVS program by post-forming working. It is recommended that the segment dies be designed oversized (overlapping) and the excess material removed following verification after forming operations are complete.
4 | Forming process steps | From the experience gained, it appears that the large curvature surface and multiple curve surface ("double hump") prevents single press forming. | The recommendation of the team is to make the parts as large as possible to reduce the amount of welding operations. It is not conclusive from the results obtained during the PVVS phase, but the team recommends that the attempt should be made on the first operations in he VVSA program to perform multiple press/heat relieve operations to get the part in tolerance.????????????
5 | Rib cutting | Large curvature hard to hold tolerance on ribs
6 | Die flexibility | The approach to flexible dies appears to be a good one. The next iteration should include provisions for easier adjustment vs. shimming, trimming ops.
7 | Procurement of inconel - lead time | The large inconel sheets can be purchased with finish specified. The mill can supply the material prepolished or unpolished. The preference is a schedule vs. cost decision.
8 | Procurement of inconel - pitting | Needs to be considered during procurement
9 | Procurement of inconel | The large inconel sheets can be purchased with finish specified. The mill can supply the material prepolished or unpolished. The preference is a schedule vs. cost decision.
10 | Heat treatment flexibility | The lack of convenience to perform multiple iterations of forming/heat treating has prevented the team from experimenting with the multiple form approach. | To meet the tight schedule requirements of the VVSA, the process equipment for the forming and heat treating should be located very conveniently with a necessary flexibility to timely use the equipment.
11 | Engineering location relative to fabrication | RI and PMW are located very far from each other. The transfer of information obtained when RI not at PMW has caused schedule delays | Quote for VVSA will include a full time RI engineer on site at PMW during first 60° section (includes die fab, segment forming, and section integration) and during system integration.
12 | Die stiffness | It appears that the dies may have flexed on the ends under the present approach. | The stiffness at the ends needs to be addressed during the design process for the VVSA dies. The flexing could have been due to overagressiveness in accomplishing a single-press form.
13 | Number of CMM tools/operators | To support schedule, the number of trained operators and tools will have to be increased for the VVSA. Recommended that there be a tool to support rib cutting, die assy, forming and integration. (3 or 4 total) Need to look closer at part flow.
14 | Hand working dies | Still in work. No conclusive results
15 | Segment integration | Still in work. No conclusive results
16 | Material property management (permeability) | Still in work. No conclusive results
17 | Material property management (permeability) | Still in work. No conclusive results