## Sheet1
VVSA EVALUATION CONFIDENTIAL 7/23/2004
The selection of a company for subcontract award will be based upon the evaluation of technical and management factors pertaining to the Company’s performance of their NCSX Vacuum Vessel Manufacturing Develop and Prototype Fabrication Subcontract and their perceived technical and management capability to perform the requirements of the Request for Proposals (RFP) for the NCSX Vacuum Vessel Production Subcontract. Technical and management factors will be rated and ranked through the use of adjectival ratings. The evaluation is broken into two general categories (1) the Subcontractor’s past performance in fabricating the PVVS and (2) the Offeror’s proposal for fabricating the VVSA.
NOTE: The general format is as below.
| Lawrence E. Dudek |  | Paul Goranson |  | Frank A. Malinowski |  | Brad Nelson |  | Larry L. Sutton |  | Mike Viola |  | MEAN
CRITERIA | MAJOR TOOL | ROHWEDDER | MAJOR TOOL | ROHWEDDER | MAJOR TOOL | ROHWEDDER | MAJOR TOOL | ROHWEDDER | MAJOR TOOL | ROHWEDDER | MAJOR TOOL | ROHWEDDER | MAJOR TOOL | ROHWEDDER
Past Performance of PVVS FABRICATION (60%)
A. Prototype compliance with Subcontract Statement of Work and Specification Requirements in order of descending importance (40%)
The offeror shall relate the experience gained through the fabrication of the prototype to their techniques, achievements, and understanding in the key technical areas listed below. The offeror shall
o identify areas where the prototype did not meet criteria listed in the specification,
o identify by how much and
o present plans for corrective actions for those areas which did not meet the specification:
1. Dimensional tolerances: The achieved dimensional tolerances shall be compared to those identified in Spec. Para. 3.3.1. Since the shape of the VVSA is critical to the NCSX component assembly, detailed discussion and planning must be provided relating to any corrective actions required in this area.
2. Vacuum Integrity: The offeror’s techniques for measuring the leak rate shall be compared to the requirements identified in Spec. Para. 3.2.1.1. The actual leak rate achieved shall be discussed relative to the requirements, along with planned corrective actions if the leak rate was not achieved.
3. Magnetic permeability: The offeror’s techniques and understanding and achieved permeability results shall be compared to the requirements identified in Spec. Para. 3.2.1.3.
4. Other:
a. Surface Finish: The offeror’s techniques and understanding for achieving the surface finish requirements shall be compared to the requirements identified in Spec. Para. 3.2.1.2. 32 micro inch finish
b. Material Consistency: the offeror’s performance on maintaining traceability and controlling material consistency as documented in material certification documents shall be discussed.
c. Welding: The offeror’s proposed weld and radiography techniques and achieved results shall be discussed and compared relative to the requirements identified in Spec. Para. 3.3.2.2 and 4.2.6. The offeror shall also discuss in detail any corrective actions or improvements proposed as a consequence of their prototype experience.
d. Non-conformances: The offeror shall discuss in detail how non-conformances were handled, including corrective actions.
B. Management (Performance relative to SOW) (20%)
1. Communication
a. Responsiveness, and promptness / completeness in reporting problems, including non-conformances.
b. Quality and timeliness of performance reports.
2. Adequacy of Project Management Staff
3. Response to technical issues & problems (Risk Management)
4. Reliability of estimates
a. Cost growth
b. Schedule growth
5. Adequacy of QA oversight.
6. Quality of the Subcontractor’s Manufacturing, Inspection, Test, and Quality Assurance Plans for the PVVS. (SOW 4.5)
7. Adequacy and Quality of Process History (SOW 5.4.2).
Capability for VVSA FABRICATION (40%)
A. Technical capability for VVSA (25%)
1. Adequacy and commitment of facilities and personnel (including qualifications/resume) and / or subcontractual arrangements to support the production effort in the following areas:
a. Floor space (for material storage and control, fabrication, inspection, cleaning and preparation for shipment.)
b. Forming
c. NDT testing (visual; dye penetrant; radiography)
d. Vacuum leak testing.
e. Ability to make vacuum quality welds in UNS N06625.
f. Magnetic permeability measuring and monitoring.
g. Heat treatment/stress relieving.
h. Metrology
i. Machining
j. QA/QC
2. Technical Approach
Evaluate proposed manufacturing methods with respect to quality of the product, risk; proposed methods; identification of areas of particular strength.
3. Risk Management
Evaluate the technical and managerial risk mitigation methods proposed. Examples of problems and solutions associated with the PVVS to help clarify this approach are encouraged.
B. Management for VVSA (15%)
The Offeror shall:
1. Provide Company Annual Financial Reports for the past two years.
2. Proposed organizational structure and reporting relationships. Include a corporate organization chart that shows the designated Project Manager, and the individual to whom that person reports. Include proposed lower-tier Subcontractors, their proposed assigned responsibilities and the type of lower-tier Subcontract you propose.
3. Identify key personnel, their commitment (% of their time that will be devoted to Subcontract), their resume (use attached format) and past experience with the Project. Provide similar information for lower-tier Subcontractor’s Project Manager, other personnel considered key.
4. Provide a letter of commitment from management of lower-tier Subcontractor’s proposed to perform the VV work, if Subcontract is awarded.
5. Provide in written form, not to exceed 2 pages, a descriptive response to the following:
a. Evidence that your team has sufficient machine, skilled labor and floor space capability to produce the VV on the schedule proposed.
b. Document control program
6. If the Offeror is a domestic large business, submit a Small Business Subcontracting Plan in full compliance with General Provisions Clause C9-2 (FAR Reference 52.219-9) including proposed goals in dollars and percentages for each socio-economic category. The format for a Small Business Subcontracting Plan is included in the RFP.
7. Describe any changes to their QA program since the performance of the Prototype Subcontract.
SCORING OF PROPOSALS
In evaluating Offeror’s Proposals, other than the Price Proposal, an adjectival rating system shall be used. The following are the definitions that apply to each rating.
3. Superior. A unique and feasible approach that exceeds PPPL requirements in almost all areas, in a way that is beneficial to PPPL. The details of the approach are comprehensive and thorough, and show an absolute understanding of the efforts to be completed, with virtually no risk in meeting the PPPL requirements. No weaknesses or deficiencies exist.
2. Excellent. An approach which satisfies all of the PPPL requirements, and exceeds the requirements in some areas in a way that is beneficial to PPPL, with extensive detail to indicate how the approach is not only feasible, but desirable, and shows a thorough understanding of the problem with minimal risk in meeting PPPL requirements. Minimal overall risk.
1. Acceptable. An approach that satisfies all PPPL requirements, with minimum supporting details provided to indicate feasibility of the approach and an understanding of the problem. May include minor weakness or deficiencies that can be corrected by the offeror in a timely manner. Moderate overall risk.
0. Unacceptable. Proposal fails to meet minimum requirements. Approach as proposed cannot be rated "ACCEPTABLE" because of errors, omissions or deficiencies that are not capable of being corrected without a major effort or in a timely manner. High overall risk.