| Days Before 08/24/04 | Project Schedule | SPEB Schedule | Task | Responsibility |
| --- | --- | --- | --- | --- |
| 203 |  | 03 Feb 04 | Initial meeting of SPEB – Introduction, status of PVVS fabrication, review/refine schedule | SPEB Chairperson |
| 196 |  | 10 Feb 04 | 2nd meeting of SPEB - Begin development of Evaluation Criteria | SPEB Chairperson |
| 176 | 01 Mar 04 |  | Finalize VV Model | Mike Cole |
| 176 | 01 Mar 04 |  | Begin review/development of SOW and SPEC for Production VV | Paul Goranson |
| 134 | 12 Apr 04 |  | Advance copy of Production SOW/Specification released | NCSX Project |
| 133 |  | 13 Apr 04 | Finalize Evaluation Criteria / Weighting for Production RFP (PPPL Only) | SPEB |
| 132 |  | 14 Apr 04 | Scheduled delivery to PPPL of both PVVS | Major Tool & Rohwedder |
| 125 |  | 21 Apr 04 | Advance copy of SOW/SPEC to PVVS Subcontractors for comments | Procurement Rep |
| 120 |  | 26 Apr 04 | Complete “Draft” of VV Production RFP | Procurement Rep |
| 116 | 30 Apr 04 |  | Complete inspection of MTM PVVS | Steve Raftopoulos |
| 113 |  | 3 May 04 | Receive Comments from PVVS Suppliers |  |
| 112 |  | 4 May 04 | Review “Draft” VV Production RFP | SPEB |
| 110 |  | 6 May 04 | Draft RFP to DOE –Princeton Site Office for review/approval | Procurement Rep |
| 109 | 07 May 04 |  | Deliver report on project evaluation of the prototypes to SPEB | NCSX Project |
| 96 | 20 May 04 |  | NCSX VV Final Design Review | NCSX Project |
| 88 | 28 May 04 |  | VV SOW and SPEC for Production Subcontract revised, if needed, signed | NCSX Project |
| 85 | 31 May 04 |  | Complete inspection of Rohwedder PVVS | Steve Raftopoulos |
| 84 |  | 01 Jun 04 | VV Production RFP issued | Procurement Rep |
| 60 |  | 25 Jun 04 | Fixed-Price Vacuum Vessel Production Proposals received | Procurement Rep |
| 35 |  | 20 Jul 04 | Complete evaluation of Proposals | SPEB |
| 32 |  | 23 Jul 04 | SPEB recommendation submitted to Source Selection Official (SSO) | SPEB |
|  |  |  | SSO approval received |  |
|  |  |  | Negotiations completed | Procurement Rep |
| 21 |  | 03 Aug 04 | Proposed VV Production Subcontract submitted to DOE - Princeton Site Office for approval | Procurement Rep |
| 7 |  | 17 Aug 04 | Receive DOE - Princeton Site Office approval of proposed VV Production Subcontract |  |
| 0 |  | 24 Aug 04 | Vacuum Vessel Production Subcontract signed | Procurement Rep |

Note:  Shadowing identifies Project Responsibilities